## Slide 1: UNC Modification 0531 Provision of Industry Testing System
23rd February 2016

## Slide 2
Background
Modification 0531 has been proposed to provide a testing environment for Transporter to Shipper flows in three phases:
  Phase 1 – Conclusion of Market Trials (CoMT) phase to Project Nexus Implementation Date (PNID)
  Phase 2 – PNID to SAP Stabilisation
  Phase 3 – Enduring following SAP Stabilisation

## Slide 3
Phase 1 – CoMT to PNID
Xoserve are not able to provision a new environment for this Phase
  The testing modification was raised after environments were procured. This requirement had not been identified therefore no capability had been provisioned.
  Provision of a new environment is unachievable due to time and resource constraints.
    The data team are focussed on DMTC3 and then data Bulk Load when we commence the data transition activities to production
    Data load to a new environment will require 7-8 weeks to be “found” within the plan
  The environment that MT is conducted upon will be used for support of the Production System.

## Slide 4
Phase 1 – CoMT to PNID
Market Trials (core) was planned from 1st February 2016 to 31st May 2016. This period was recommended to PNSG following a consultation with the industry on their requirements for MT
  PNSG has been the vehicle to extend the MT window as challenges have been faced
  PNSG is monitoring progress through the MT stage.
  MT has gated stage criteria that have been agreed with PNSG including the exit criteria.
  Any extension to MT past 30th June or 31st July is the responsibility of PNSG

## Slide 5
Phase 1 – CoMT to PNID - Conclusion
The environment currently being used for MT will form part of the production stack at go live and therefore activities are required post MT to ensure the environments are ready
PNSG, primarily through PwC and Xoserve, are considering the possible programme contingency scenarios and actions.
This includes whether MT could be continued into August if required and any impacts this could have on downstream transition activities.
Code freeze for iDR’s and transition needs to be considered.
PNSG is the correct place for these decisions to be taken

## Slide 6
Phase 2 and 3 – PNID - Enduring
Xoserve recognise the requirement for an industry test environment from 1st October to test defects prior to them being deployed into the production environment
Xoserve are assessing the viability of providing an environment for this purpose (not the current MT environment)
We are balancing the requirement for this environment alongside the other environment needs, including those required for Release 2 and MT for RAASP
Challenges with the distinct needs of the two phases.
  Criteria for the two stages seems relevant to assist UKLC, for example, support requirements.
  Data management principles need to be carefully constructed.