## Sheet1
Task Name | Duration | Start | Baseline Finish | Finish | % Complete | Predecessors | Resource Names
Overall Performance Assurance Plan | 727 days | Wed 20/03/13 | Wed 31/12/14 | Thu 31/12/15 | 9%
Independent Study of Performance Risk | 334 days | Wed 20/03/13 | Wed 31/12/14 | Mon 30/06/14 | 60%
Create scope for an independent study of the settlement process (incl consultation with Workgroup) | 89 days | Wed 20/03/13 | Mon 22/07/13 | Mon 22/07/13 | 100% |  | PAW
Determine possible level of funding for the independent study | 29 days | Wed 12/06/13 | Mon 22/07/13 | Mon 22/07/13 | 100% |  | PAW
Determine how the independent study will be funded | 36 days | Mon 16/09/13 | Mon 04/11/13 | Mon 04/11/13 | 100% |  | Ofgem
Ofgem to write to EUK, ICOSS and ENA | 56 days | Fri 04/10/13 | Fri 04/10/13 | Fri 20/12/13 | 100% |  | Ofgem
Responses from EUK, ICOSS and ENA | 55 days | Mon 11/11/13 | Mon 04/11/13 | Fri 24/01/14 | 100% |  | EUK/ICOSS/ENA
Agree mechanism for paying for independent study | 5 days | Mon 11/11/13 | Mon 04/11/13 | Fri 15/11/13 | 100% |  | Ofgem
Identify possible service providers for independent study | 76 days | Mon 22/07/13 | Mon 04/11/13 | Mon 04/11/13 | 100% |  | Ofgem
Tender for independent study | 65 days | Mon 02/12/13 | Fri 29/11/13 | Fri 28/02/14 | 0% |  | Ofgem
Undertake tender evaluation (including mtgs with tenderers) | 70 days | Mon 02/12/13 | Mon 09/12/13 | Fri 07/03/14 | 0% |  | Ofgem
Agree party for independent study | 3 days | Mon 10/03/14 | Mon 09/12/13 | Wed 12/03/14 | 0% | 11 | Ofgem
Contract with independent study party | 11 days | Thu 13/03/14 | Tue 24/12/13 | Thu 27/03/14 | 0% | 12 | Ofgem
Commence independent study | 1 day | Fri 28/03/14 | Wed 01/01/14 | Fri 28/03/14 | 0% | 13 | Ofgem
Conclude independent study (including risk register of "theoretical process") | 1 day | Fri 18/04/14 | Fri 18/04/14 | Fri 18/04/14 | 0% | 14 | Ofgem
PAF Group to consider independent study and any reporting required from Xoserve/SPAA | 1 day | Thu 01/05/14 | Thu 01/05/14 | Thu 01/05/14 | 0% | 15 | Ofgem
Xoserve/SPAA to provide reporting | 67 days | Thu 16/01/14 | Wed 31/12/14 | Fri 18/04/14 | 0% |  | Xoserve/SPAA
PAF Group to consider reporting and agree materiality | 1 day | Tue 18/02/14 | Fri 31/01/14 | Tue 18/02/14 | 0% |  | PAW
PAF Group to consider ongoing data elements for PAF | 7 days | Fri 14/02/14 | Fri 14/02/14 | Mon 24/02/14 | 0% |  | PAW
1st cut of data elements for PAF and performance monitoring to be reviewed by the PAF Group | 1 day | Mon 30/06/14 | Mon 30/06/14 | Mon 30/06/14 | 0% |  | PAW
Performance Assurance Framework Development | 266 days | Wed 25/09/13 | Wed 01/10/14 | Wed 01/10/14 | 0%
Reporting | 134 days | Wed 25/09/13 | Mon 31/03/14 | Mon 31/03/14 | 1%
Consider reporting that Xoserve currently does | 1 day | Wed 25/09/13 | Wed 25/09/13 | Wed 25/09/13 | 100% |  | PAW
Determine appropriateness of existing reporting | 1 day | Wed 25/09/13 | Wed 25/09/13 | Wed 25/09/13 | 100% |  | PAW
Consider any additional reporting/controls necessary for post Nexus functionality/market model | 105 days | Wed 25/09/13 | Fri 29/11/13 | Tue 18/02/14 | 0% |  | PAW
Agree future reporting required, in line with Project Nexus Workgroup | 105 days | Wed 25/09/13 | Fri 29/11/13 | Tue 18/02/14 | 0% |  | PAW/PNUNC
Determine individual elements and timings of reporting | 46 days | Tue 17/12/13 | Tue 31/12/13 | Tue 18/02/14 | 0% |  | PAW
Determine individual elements and timings of performance monitoring | 75 days | Tue 17/12/13 | Mon 31/03/14 | Mon 31/03/14 | 0% |  | PAW
Overall Governance Arrangements | 155 days | Mon 11/11/13 | Fri 13/06/14 | Fri 13/06/14 | 0%
Agree main parties to the PAF - e.g. Transporters, Shippers, Xoserve | 1 day | Mon 11/11/13 | Fri 31/01/14 | Mon 11/11/13 | 100% |  | PAW
Agree what current governance arrangements will be impacted by the PAF and if anything new will be required | 108 days | Tue 17/12/13 | Thu 15/05/14 | Thu 15/05/14 | 0% |  | PAW
Commence discussions with other governance bodies (if required) | 54 days | Tue 17/12/13 | Fri 28/02/14 | Fri 28/02/14 | 0% |  | PAW
Agree the funding parties for PAF | 75 days | Tue 17/12/13 | Mon 31/03/14 | Mon 31/03/14 | 0% |  | PAW
Agree if an annual budget is required | 75 days | Tue 17/12/13 | Mon 31/03/14 | Mon 31/03/14 | 0% |  | PAW
Determine how funding, budget and apportionments are agreed | 1 day | Wed 30/04/14 | Wed 30/04/14 | Wed 30/04/14 | 0% |  | PAW
Discuss and agree spilt of duties/resposibilities between SPAA and the UNC | 1 day | Wed 30/04/14 | Wed 30/04/14 | Wed 30/04/14 | 0% |  | PAW
Agree how the PAFA features in the PAF and interfaces with the UNC and SPAA | 1 day | Wed 30/04/14 | Wed 30/04/14 | Wed 30/04/14 | 0% |  | PAW
Consider Ofgem's involvement/oversight | 1 day | Wed 30/04/14 | Wed 30/04/14 | Wed 30/04/14 | 0% |  | PAW
Agree, in principle, the basis for the settlement risk premium | 1 day | Fri 02/05/14 | Wed 30/04/14 | Fri 02/05/14 | 0% | 16 | PAW
Agree frequency (at least initial frequency) of the analysis of settlement risk and how often methodology needs to be updated (if at all) | 1 day | Fri 02/05/14 | Wed 30/04/14 | Fri 02/05/14 | 0% | 16 | PAW
Agree governance around reporting - how to request new reports | 1 day | Wed 14/05/14 | Wed 14/05/14 | Wed 14/05/14 | 0% | 26 | PAW
Decide if there is any consultation needed with Parties/Ofgem following the determination of a settlement risk penalty | 1 day | Wed 14/05/14 | Wed 14/05/14 | Wed 14/05/14 | 0% | 37 | PAW/Ofgem
Determine individual elements and timings of incentive regime and invoicing (if deemed required under action 1) | 1 day | Fri 13/06/14 | Fri 13/06/14 | Fri 13/06/14 | 0% | 42 | PAW
Determine individual elements and timings of assurance (if deemed required under action 1) | 1 day | Fri 13/06/14 | Fri 13/06/14 | Fri 13/06/14 | 0% | 28 | PAW
Day to Day Governance Arrangements | 108 days | Mon 02/12/13 | Wed 30/04/14 | Wed 30/04/14 | 0%
Determine the need for an "oversight" workgroup/comiittee and, if necessary, its remit, frequency of meetings and if it could make decisions | 108 days | Mon 02/12/13 | Wed 30/04/14 | Wed 30/04/14 | 0% |  | PAW
Determine role of Joint Office, Xoserve, Ofgem and SPAA and involvement in PAF | 108 days | Mon 02/12/13 | Wed 30/04/14 | Wed 30/04/14 | 0% |  | PAW
Consider inclusion in UNC directly or via ancillary document | 108 days | Mon 02/12/13 | Wed 30/04/14 | Wed 30/04/14 | 0% |  | PAW
Introducing the PAF | 233 days | Mon 11/11/13 | Wed 01/10/14 | Wed 01/10/14 | 0%
Develop business rules for PAF MOD | 210 days | Mon 11/11/13 | Fri 29/08/14 | Fri 29/08/14 | 0% |  | PAW
Raise MOD for Performance Assurance Framework, in line with agreed parameters/objectives (more than 1 Mod may be req.) | 1 day | Wed 01/10/14 | Wed 01/10/14 | Wed 01/10/14 | 0% |  | PAW
Performance Assurance Framework Administrator (PAFA) | 563 days | Tue 05/11/13 | Wed 31/12/14 | Thu 31/12/15 | 0%
Consider Elexon Tools | 29 days | Tue 21/01/14 | Fri 28/02/14 | Fri 28/02/14 | 0% |  | PAW
Determine scope for the work on the PAF Administrator, based on model of assurance and performance requirements | 163 days | Tue 17/12/13 | Thu 31/07/14 | Thu 31/07/14 | 0% |  | PAW
Determine the scope of the PAFA performance reporting and analysis role | 163 days | Tue 17/12/13 | Thu 31/07/14 | Thu 31/07/14 | 0% |  | PAW
Consider if the PAFA will have an assurance role, as well as performance monitoring | 163 days | Tue 17/12/13 | Thu 31/07/14 | Thu 31/07/14 | 0% |  | PAW
Agree if the PAFA will provide "training services" for new entrants | 163 days | Tue 17/12/13 | Thu 31/07/14 | Thu 31/07/14 | 0% |  | PAW
Agree if the PAFA will provide "education" to parties performing poorly | 163 days | Tue 17/12/13 | Thu 31/07/14 | Thu 31/07/14 | 0% |  | PAW
Consider options for the contracting of the PAF administrator | 138 days | Tue 21/01/14 | Fri 29/08/14 | Thu 31/07/14 | 0% |  | PAW
Should the PAFA have a statutory role? | 193 days | Tue 05/11/13 | Fri 29/08/14 | Thu 31/07/14 | 0% |  | PAW
Who should contract the PAFA (a) initially and (b) ongoing? | 138 days | Tue 21/01/14 | Fri 29/08/14 | Thu 31/07/14 | 0% |  | PAW
Determine route to agree appointment, tender and award of PAFA | 138 days | Tue 21/01/14 | Fri 29/08/14 | Thu 31/07/14 | 0% |  | PAW
Identify possible service providers for PAFA | 21 days | Fri 01/08/14 | Fri 29/08/14 | Fri 29/08/14 | 0% |  | PAW
Prepare tender for PAFA appointment | 21 days | Mon 01/09/14 | Mon 29/09/14 | Mon 29/09/14 | 0% |  | PAW
Issue tender for the provision of PAFA | 1 day | Tue 30/09/14 | Tue 30/09/14 | Tue 30/09/14 | 0% |  | TBC
Undertake tender evaluation (including mtgs with tenderers) | 23 days | Wed 01/10/14 | Fri 31/10/14 | Fri 31/10/14 | 0% |  | TBC
Agree successful party who will do the PAFA work | 1 day | Fri 14/11/14 | Fri 14/11/14 | Fri 14/11/14 | 0% |  | PAW
Contract party for PAFA work | 11 days | Fri 14/11/14 | Fri 28/11/14 | Fri 28/11/14 | 0% | 15 | TBC
PAFA commences work - preparation (including meeting industry parties) | 23 days | Mon 01/12/14 | Wed 31/12/14 | Wed 31/12/14 | 0% |  | TBC
PAFA takes model from the independent study and supporting documentation and becomes familiar with it | 23 days | Mon 01/12/14 | Wed 31/12/14 | Wed 31/12/14 | 0% |  | TBC
PAFA establishes links with Xoserve (and possibily SPAA) to gain data necessary to run risk model | 23 days | Mon 01/12/14 | Wed 31/12/14 | Wed 31/12/14 | 0% |  | TBC
PAFA creates reporting on the agreed parameters deemed most material for settlement accuracy | 45 days | Mon 01/12/14 | Wed 31/12/14 | Fri 30/01/15 | 0% |  | TBC
PAFA issues reports to industry and Ofgem on a monthly basis to update on progress | 218 days | Mon 01/12/14 | Wed 31/12/14 | Wed 30/09/15 | 0% |  | TBC
PAFA liaises with Xoserve on monthly charges and re-distribution to be applied | 66 days | Thu 01/10/15 | Wed 31/12/14 | Thu 31/12/15 | 0% |  | TBC
PAFA issues first performance reports against Risk Register | 218 days | Mon 01/12/14 | Wed 31/12/14 | Wed 30/09/15 | 0% |  | TBC