## Sheet1
Updated following 24th January 2012 workgroup meeting
Topic | Planned No. of Sessions | Planned Start Date | Planned End date | Actual Start Date | Actual End Date | 2011-08-02 | 2011-08-03 | 2011-08-22 | 2011-08-23 | 2011-09-06 | 2011-09-19 | 2011-09-20 | 2011-10-04 | 2011-10-24 | 2011-10-25 | 2011-11-01 | 2011-11-21 | 2011-11-22 | 2011-12-06 | 2011-12-07 | 2012-01-10 | 2012-01-24 | 2012-02-07 | 2012-03-06 | 2012-04-03 | 2012-05-08 | 2012-06-06 | 2012-07-03 | Actual No. of Sessions | Topic
Settlement (incl AMR) | 4 | 2010-03-31 | 2011-08-22 | 2011-03-31 | 2011-11-01 | [23 empty] | 9 | Settlement | bar: 2011-08-02; 2011-08-22; 2011-10-04; 2011-11-01
Resync | 2 | 2011-08-23 | 2011-09-19 | 2011-06-21 | 2011-06-21 | [23 empty] | 1 | Re-synch
Reconciliation | 5 | 2011-08-02 | 2011-09-19 | 2011-06-01 | 2011-11-22 | [23 empty] | 7 | Rec | bar: 2011-08-02; 2011-08-22; 2011-09-19; 2011-10-24; 2011-11-22
AQ | 5 | 2011-08-23 | 2011-11-01 | 2011-06-20 | 2011-11-21 | [23 empty] | 8 | AQ | bar: 2011-08-03; 2011-09-06; 2011-09-20; 2011-10-25; 2011-11-21
Invoicing | 6 | 2011-09-19 | 2011-12-06 | 2011-09-19 | 2012-01-10 | [23 empty] | 6 | Invoicing | bar: 2011-09-19; 2011-10-04 to 2011-10-24; 2011-11-22; 2011-12-07 to 2012-01-10
Supply Point Register | 3 | 2011-08-03 | 2011-11-21 | 2011-08-03 | 2012-01-10 | [23 empty] | 6 | SP Register | bar: 2011-08-03; 2011-08-23; 2011-10-25; 2011-11-21; 2011-12-07 to 2012-01-10
Retrospective Updates | 3 | 2011-10-25 | 2011-12-06 | 2011-08-23 | [24 empty] | 7 | Retro Updates | bar: 2011-08-23; 2011-09-20 to 2011-10-04; 2011-11-01; 2011-12-06; 2012-01-10 to 2012-02-07
Market Diff (Part 2) | 2 | 2011-11-22 | 2011-12-07 | included in Supply Point Register topic | [24 empty] | 0 | Market Diff
Non-functional | 3 | 2011-12-07 | 2012-02-07 | 2011-11-22 | 2012-01-24 | [23 empty] | 4 | Non-Func | bar: 2011-11-22 to 2011-12-06; 2012-01-10 to 2012-01-24
iGT services | 7 | 2012-01-24 | 2012-07-03 | 2012-01-24 | [24 empty] | 7 | iGT services | bar: 2012-01-24 to 2012-07-03
Topics per day | [5 empty] | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 1
| 40 | [27 empty] | 48
Assumptions: the 4 UNC Modifications (0357, 0359, 0377 and 0380) can be covered within this timetable and still leave time for 2 other "sessions" per meeting date
[12 empty] | 1 | = re-scheduled since previous version
[12 empty] | 1 | = completed
Note: Meeting dates pre 02/08/2011 have been removed from the plan.