## Slide 1: Senior Stakeholder Forum
04/02/2014

## Slide 2: Agenda
UK-Link Programme Update
  Including Data Cleansing Update
Nexus Modification Update
Faster Switching
EU Reform Programme Update
Industry Change Programme 2015
  Delivery implications
  Dependencies & risk profile
Review of Actions

## Slide 3: UK Link Programme Update
Significant Progress made since last SSF in October
Design, Build, Implement & Operate (DBIO) sourcing phase completed
Preferred supplier – Wipro
Independent assurance report – Baringa
Indicative Plan shared in December and updated in January
Logical Analysis completed
High level design commenced
Continued engagement through Project Nexus Workgroup

## Slide 4
Data Cleansing Progress Update @ 22nd Jan’14

## Slide 5: Update on Nexus Modifications
Workgroup report consultation completed (432 & 434)
  Modification Panel unanimously recommended implementation of 432 & 434
  Modifications (432 & 434) sent to Ofgem for - decision expected 21st February
  Modification 440 due at February Modification Panel
Consultation responses were broadly supportive of the modifications
  12 supported, 3 qualified support, 1 neutral
Additional Comments were made, summarised as follows:
  Requirement to implement suite of “Nexus” modifications as a package
  Supportive Performance Assurance Framework required to ensure effective settlement regime
  Risk of multiple industry changes in Q4 2015
  Requirement for managed co-ordination of wider industry change programme
  Suggestion of a 2016 implementation
  Data is required to be fit for purpose

## Slide 6: Faster Switching
Xoserve are working with the industry to reduce the confirmation period
Aspiration to deliver by the end of 2014
Project team established to undertake analysis
Industry discussions on detailed requirements taking place in parallel
  Modification 477
Detailed requirements are being fed into the High Level Design workshops for UKLink Programme to determine any impacts
  Logical analysis already completed

## Slide 7: EU Reform Programme Update
UNC European Workgroup Established
Key areas of reform required for October 2015
UNC Modifications to be raised
Xoserve Project Team established
Analysis commenced 6th January 2014
Requirements not fully defined
Plan in place for requirements to be fed into the project
Working closely with UK Link Programme

## Slide 8: Industry Change Roadmap
2014
2016
2015
2017
EU Legislative Change
DCC Launch
UK Link Implementation
IGT SPA
UK Link Settlement Reform
Oct 2015
Last chance for Data Cleanse for Oct 2015 target
UK Link Programme Implementation
Gemini Change Programme
UKL Transition Options
Settlement Reform
Data Cleanse
SMART DCC Launch
Large scale industry benefits of settlement reform only provided by increasing SMART read volumes
Cleansed data required for Data migration activities
Early opportunities to support meter read validation will drive further cleansing activity
EU Changes required for 2015
Under licence
Delivery of requirements within Nexus BRDs as part of October 2015 release
SMART Meter Roll Out
Sep/Oct 2015 deployment conflict
SMART meter technology and roll out delays may reduce benefits of UKL Oct 2015 Go Live
Rolling AQ and meter point reconciliation benefits derived from more frequent meter reads
Gemini Change Freeze Window Oct 2015 to April 2016
Industry Modifications (AUGE & Faster Switching)
Mods to support Go Live (e.g. Acceptable # non working days)
Nexus Mods target effective Oct 2015
AUGE (Mod 473) required before Settlement Reform
Faster switching scoped into UK Link HLD (impact unknown)
IGT SPA
Faster Switching
Industry Change Roadmap
Dependency Map
Market Trials
Transition & Cutover
Integration Testing
Testing & Trials
UK Link Programme Industry Interaction
EU
Reform

## Slide 9: Delivery Dependencies
2014
2016
2015
2017
EU Legislative Change
DCC Launch
UK Link Implementation
IGT SPA
UK Link Settlement Reform
Oct 2015
Last chance for Data Cleanse for Oct 2015 target
UK Link Programme Implementation
Gemini Change Programme
UKL Transition Options
Settlement Reform
Data Cleanse
SMART DCC Launch
Large scale industry benefits of settlement reform only provided by increasing SMART read volumes
Cleansed data required for Data migration activities
Early opportunities to support meter read validation will drive further cleansing activity
EU Changes required for 2015
Under licence
Delivery of requirements within Nexus BRDs as part of October 2015 release
SMART Meter Roll Out
Sep/Oct 2015 deployment conflict
SMART meter technology and roll out delays may reduce benefits of UKL Oct 2015 Go Live
Rolling AQ and meter point reconciliation benefits derived from more frequent meter reads
Gemini Change Freeze Window Oct 2015 to April 2016
Industry Modifications (AUGE & Faster Switching)
Mods to support Go Live (e.g. Acceptable # non working days)
Nexus Mods – target effective Oct 2015
AUGE (Mod 473) required before Settlement Reform
Faster switching scoped into UK Link HLD (impact unknown)
IGT SPA
Faster Switching
Industry Change Roadmap
Dependency Map
Market Trials
Transition & Cutover
Integration Testing
Testing & Trials
UK Link Programme Industry Interaction
EU
Reform

## Slide 10: Dependency and Risk
EU Reform is required for delivery for October 2015
Nexus mods are targeted for October 2015
Both will require changes to Gemini
Single coordinated release
Problems with one element => risk on both
Each element has its own significant risks
=>
=>
Dependency results in likelihood multiplying
Single release results in impact doubling
=>
=>

## Slide 11: UK Link Industry Engagement: Building Stakeholder Confidence
Business Sign off of HLD & DD
Stakeholder Confidence
Build completion
Early visibility of System Test results
UAT Acceptance
Confirmation of Functional Fit %
Programme Confidence Curve
Industry Confidence Curve
The UK Link Programme aims to build industry confidence in line with the programme delivery team through regular engagement and communications:
End of High level design – Communication of industry impacts, engagement strategy & test strategy
End of detailed design – Final view of SAP functional fit, finalised interface specifications, data migration plans
Throughout Build & Test phases – Programme Status reporting, Training needs analysis, planning and roll out for required industry participants, planning, preparation and execution of market trials. Tracking of data cleanse activities. Defect resolution an ongoing change management notifications
Implementation – Engagement over transition mods required, iterative development of cutover and migration plans, preparation for rehearsals and communication of transition arrangements.
Go-Live
Employed engagement mechanisms will include:
Senior Stakeholder Forum comms (Quarterly)
UNC PN work Group (2 weekly/monthly)
UKLC – Formal Governance (Sub Committee of UNC Committee, Voting Body)
Industry Engagement Forum – Xoserve Quarterly ‘operational’ level liaison
121 Meetings (including Ofgem)
CMSG (GTs)
IGTs
Newsletter
ICOSS/EUK
Customer Day
Data Cleansing Forum
GPSG
Informal calls / contacts
Engagement Mechanisms
Key Engagement points within the lifecycle:
Confidence profiles aligned through engagement approach implementation
Market Test Acceptance