## FF Control Sheet
Phase | File Format | Hierarchies | Hierarchy Published | Hierarchy Approval | Published File Hierarchies within Zip Folder | Record | Record Published. | Published File Formats/Records within Zip Folder | Record Name | Revised Version Post UKLP | UKLC Approval Status | Deferral Reason | UKLC 8th Jan Supporting Information
1 | AQI | AQI | AQI | Approved | Zip 9 | C41 | C41 | Zip 1 | RT_C41_AQ_CORRECTION | V1 | Approved | PAPER
1 | AQI |  |  |  |  | C42 | C42 | Zip 1 | RT_C42_AQ_CORRECTION_CANCELLATION | V1 | Approved | PAPER
1 | AQR | AQR | AQR | Approved | Zip 9 | C43 | C43 | Zip 1 | RT_C43_AQ_CORRECTION_RESPONSE | V1 | Approved | PAPER
1 | AQR |  |  |  |  | C45 | C45 | Zip 1 | RT_C45_AQ_CORRECTION_CAN_RESPONSE | V1 | Approved | PAPER
1 | AQR |  |  |  |  | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS | V1 | Approved | iGT
1 | AQR |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Not required
1 | BIS | BIS | Not required | Not required | Not required | Q06 | Q06 | Zip 6 | RT_Q06_BID_INFO_SHI | V5 | Approved
1 | CDN | CDN | Not required | Not required | Not required | M79 | M79 | Zip2 | RT_M79_PRE_CD_NOTFN | V6 | Approved
1 | CDN |  |  |  |  | M82 | M82 | Zip2 | RT_M82_POST_CD_NOTFN | V6 | Approved
1 | CDR | CDR | Not required | Not required | Not required | M80 | M80 | Zip2 | RT_M80_ACPTD_PRE_CD_NOTFN | V5 | Approved
1 | CDR |  |  |  |  | M81 | M81 | Zip2 | RT_M81_RJCTD_PRE_CD_NOTFN | V6 | Approved
1 | CDR |  |  |  |  | M82 | M82 | Zip2 | RT_M82_POST_CD_NOTFN | V6 | Approved
1 | CDR |  |  |  |  | M83 | M83 | Zip2 | RT_M83_ACPTD_POST_CD_NOTFN | V6 | Approved
1 | CDR |  |  |  |  | M84 | M84 | Zip2 | RT_M84_RJCTD_POST_CD_NOTFN | V6 | Approved
1 | CDR |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Not required
1 | CNC | CNC | CNC | Approved | Zip 9 | C37 | C37 | Zip 1 | RT_C37_CUSTOMER_END_DATE_REQUEST | V1 | Caveated Approval
1 | CNC |  |  |  |  | S66 | S66 | Zip5 | RT_S66_CONTACT_DETAILS | V2 | Approved
1 | CNC |  |  |  |  | S81 | S81 | Zip 4 | RT_S81_CUSTOMER_NAME_CHANGE_REQ | V2 | Approved
1 | CNC |  |  |  |  | S82 | S82 | Zip 4 | RT_S82_END_CONSUMER_CHANGE_REQ | V2 | Approved
1 | CNC |  |  |  |  | S83 | S83 | Not required | RT_S83_END_CONSUMER_DETAILS | V1 | Not required
1 | CNC |  |  |  |  | S84 | S84 | Zip 6 | RT_S84_SPECIAL_CONDITIONS | V2 | Approved
1 | CNC |  |  |  |  | C50 | C50 | Zip 1 | RT_C50_CUSTOMER_END_DATE_RESPONSE | V1 | Approved
1 | CNR | CNR | CNR | Approved | Zip 9 | S66 | S66 | Zip5 | RT_S66_CONTACT_DETAILS | V2 | Approved
1 | CNR |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Not required
1 | CNR |  |  |  |  | S83 | S83 | Not required | RT_S83_END_CONSUMER_DETAILS | V1 | Not required
1 | CNR |  |  |  |  | S66 | S66 | Zip5 | RT_S84_SPECIAL_CONDITIONS | V2 | Approved
1 | CNR |  |  |  |  | S85 | S85 | Zip 4 | RT_S85_CUSTOMER_NAME_CHANGE | V2 | Approved
1 | CNR |  |  |  |  | S86 | S86 | Zip 4 | RT_S86_END_CONSUMER_CHANGE | V2 | Approved
1 | CTR | CTR | Not required | Not required | Not required | S24 | S24 | Zip 3 | RT_S24_SP_CONTACTS_AMENDMENTS | V2 | Approved
1 | CTR |  |  |  |  | S66 | S66 | Zip5 | RT_S66_CONTACT_DETAILS | V2 | Approved
1 | CTR |  |  |  |  | S67 | S67 | Zip 6 | RT_S67_ELECTRONIC_DEVICE | V2 | Approved
1 | CTR |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Not required
1 | DPP | DPP | Not required | Not required | Not required | N11 | N11 | Zip2 | RT_N11_DOMESTIC_PREPAYMENT_METER | V2 | Approved
1 | DPS | DPS | Not required | Not required | Not required | M93 | M93 | Zip2 | RT_M93_DOMESTIC_PORTFOLIO_RECORD | V2 | Approved
1 | DRS | DRS | Not required | Not required | Not required | N95 | N95 | Zip2 | RT_N95_DATASET_READ_NOTFN | V4 | Approved
1 | EMC | EMC | Not required | Not required | Not required | S51 | S51 | Zip 3 | RT_S51_CONTACT_CHANGE_REQ | V2 | Approved
1 | EMC |  |  |  |  | S66 | S66 | Zip5 | RT_S66_CONTACT_DETAILS | V2 | Approved
1 | EMC |  |  |  |  | S67 | S67 | Zip 6 | RT_S67_ELECTRONIC_DEVICE | V2 | Approved
1 | EPS | EPS | Not required | Not required | Not required | Q01 | Q01 | Zip 3 | RT_Q01_ ELIGIBLE_SUPPLY_POINT | V6 | Approved
1 | EUC | EUC | Not required | Not required | Not required | T67 | T67 | Zip 7 | RT_T67_NTFN_EUC_DEFN | V3 | Approved
1 | JOB | JOB | Not required | Not required | Not required | ADDRS | ADDRS | Zip 1 | ADDRS (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | APPNT | APPNT | Not required | APPNT (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | ASSET | ASSET | Zip 1 | ASSET (DATASET-RGMA) | V13 | Approved | RETRO
1 | JOB |  |  |  |  | CONTM | CONTM | Not required | CONTM (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | CONVE | CONVE | Not required | CONVE (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | HEADR | HEADR | Not required | HEADR (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | METER | METER | Not required | METER (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | MKPRT | MKPRT | Not required | MKPRT (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | MTPNT | MTPNT | Not required | MTPNT (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | NAME | NAME | Not required | NAME (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | READG | READG | Not required | READG (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | REGST | REGST | Not required | REGST (DATASET-RGMA) | V13 | Not required
1 | JOB |  |  |  |  | TRAIL | TRAIL | Not required | TRAIL (DATASET-RGMA) | V13 | Not required
1 | LPA | LPA | Not required | Not required | Not required | I68 | I68 | Zip 1 | RT_I68_RECON_VAR_PROFILE_ALLO | V3 | Approved
1 | MAI | MAI | Not required | Not required | Not required | S93 | S93 | Zip 4 | RT_S93_METER_ACCESS_INST_UPD_REQ | V2 | Caveated Approval
1 | MAM | MAM | Not required | Not required | Not required | K08 | K08 | Zip 1 | RT_K08_MAM_GAO_DETAILS | V6 | Approved
1 | MAS | MAS | Not required | Not required | Not required | K09 | K09 | Zip 1 | RT_K09_MAM_GAO_DETAILS_RESPONSE | V6 | Approved
1 | MAS |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Not required
1 | MDR | MDR | Not required | Not required | Not required | M00 | M00 | Zip 6 | RT_M00_DAILY_DATALOGGER_READINGS | V6 | Approved | PAPER
1 | MID | MID | Not required | Not required | Not required | N44 | N44 | Zip2 | RT_N44_METER_INSPECTION_DATE | V2 | Not required
1 | MIO | MIO | Not required | Not required | Not required | N45 | N45 | Zip2 | RT_N45_METER_INSPECTION_RESPONSE | V2 | Approved
1 | MIO |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Approved
1 | MIR | MIR | Not required | Not required | Not required | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Approved
1 | MIR |  |  |  |  | S94 | S94 | Zip 4 | RT_S94_METER_ACC_INSTR_UPD_RESP | V2 | Caveated Approval
1 | MPE | MPE | Not required | Not required | Not required | S04 | S04 | Zip 11 | RT_S04_SP_MRF_AND_BATCH_FREQ_CANCELLATION | V3 | Re-approved
1 | MPE |  |  |  |  | S06 | S06 | Zip5 | RT_S06_SP_CAPACITY_CANCELLATION | V2 | Approved
1 | MPE |  |  |  |  | S08 | S08 | Zip 6 | RT_S08_LAPSED_CONFIRMATION_DETS | V2 | Approved
1 | MPE |  |  |  |  | S31 | S31 | Zip 3 | RT_S31_INVALID_OFFER_DETAILS | V2 | Approved
1 | MPE |  |  |  |  | S88 | S88 | Zip 4 | RT_S88_CEASED_RESPONSIBILITY | V2 | Approved
1 | MRI | MRI | Not required | Not required | Not required | K15 | K15 | Zip2 | RT_K15_ADDTNL_MET_READ_INSTRCT | V4 | Approved | PAPER
1 | MRI |  |  |  |  | N90 | N90 | NA | RT_N90_ASSET_DETAILS | V6 | Deferred | PAPER | Domain Questions Outstanding
1 | MRI |  |  |  |  | S98 | S98 | Zip 4 | RT_S98_SMART_DATA | V2 | Approved
1 | MRI |  |  |  |  | U06 | U06 | NA | RT_U06_METER_READ_INSTRUCTIONS | V10 | Deferred | PAPER | Domain Questions Outstanding
1 | MSI | MSI | Not required | Not required | Not required | T73 | T73 | Zip5 | RT_T73_MARKET_SECT_CODE_CHG_REQ | V2 | Caveated Approval
1 | MSO | MSO | Not required | Not required | Not required | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Not required
1 | MSO |  |  |  |  | T74 | T74 | Zip5 | RT_T74_MARKET_SECT_CODE_CHG_RESP | V2 | Caveated Approval
1 | NAC | NAC | Not required | Not required | Not required | T08 | T08 | Zip 4 | RT_T08_NTFN_ADDRESS_CHANGE | V2 | Caveated Approval
1 | NMS | NMS | NMS | Approved | Zip 10 | N99 | N99 | Zip2 | RT_N99_MP_STATUS_CHANGE_NOTIFICATION | V1 | Approved | PAPER
1 | PAC | PAC | Not required | Not required | Not required | K15 | K15 | Zip2 | RT_K15_ADDTNL_MET_READ_INSTRCT | V4 | Approved | PAPER
1 | PAC |  |  |  |  | N90 | N90 | NA | RT_N90_ASSET_DETAILS | V6 | Deferred | PAPER | Domain Questions Outstanding
1 | PAC |  |  |  |  | S98 | S98 | Zip 4 | RT_S98_SMART_DATA | V2 | Approved
1 | PAC |  |  |  |  | U06 | U06 | NA | RT_U06_METER_READ_INSTRUCTIONS | V10 | Deferred | PAPER | Domain Questions Outstanding
1 | PIR | PIR |  | Not required | Not required | Q02 | Q02 | Zip 3 | RT_Q02_PUBLISH_INTR_RQTMT | V3 | Approved
1 | PPN | PPN |  | Not required | Not required | G39 | G39 | Not required | RT_G39_PORTFOLIO_EXTRACT_DATE | V1 | Not required
1 | PPN |  |  |  |  | G40 | G40 | Zip 1 | RT_G40_PORTFOLIO_DETAIL | V2 | Approved
1 | PRN | PRN | Not required | Not required | Not required | N93 | N93 | Zip2 | RT_N93_PROVISIONAL_RATCHET_NOTFN | V3 | Approved
1 | PRN |  |  |  |  | N94 | N94 | Zip2 | RT_N94_CONFIRMATION_DETAILS | V3 | Approved
1 | RAT | RAT | Not required | Not required | Not required | M12 | M12 | Zip2 | RT_M12_RATCHET_DETAILS | V3 | Approved
1 | RAT |  |  |  |  | M15 | M15 | Zip2 | RT_M15_CONFIRMATION_NOTIFICATION | V2 | Caveated Approval
1 | RAT |  |  |  |  | S31 | S31 | Zip 3 | RT_S31_INVALID_OFFER_DETAILS | V2 | Approved
1 | RFA | RFA | Not required | Not required | Not required | S89 | S89 | Zip 6 | RT_S89_SHIPPER_REFERENCE_CHG_REQ | V2 | Caveated Approval
1 | RFR | RFR | Not required | Not required | Not required | S90 | S90 | Zip5 | RT_S90_SHIPPER_REFERENCE_CHANGE | V2 | Caveated Approval
1 | RFS | RFS | Not required | Not required | Not required | Q05 | Q05 | Zip 6 | RT_Q05_RESPONSE_FILE_SHIPPER_BID_ACC | V6 | Approved
1 | RFS |  |  |  |  | Q23 | Q23 | Zip 3 | RT_Q23_ RESPONSE_FILE_SHIPPER_BID-REJ | V6 | Approved
1 | RFS |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Not required
1 | SBF | SBF | Not required | Not required | Not required | Q03 | Q03 | Zip 6 | RT_Q03_SHIPPER_BID_FILE | V6 | Approved
1 | SBF |  |  |  |  | Q04 | Q04 | Zip 6 | RT_Q04_CNCL_WTH_BID | V6 | Not Required
1 | SFN | SFN | SFN | Approved | Zip 10 | O15 | O15 | Zip2 | RT_O15_SITE_VISIT_DETAILS | V1 | Approved | PAPER
1 | SFN |  |  |  |  | O17 | O17 | Zip2 | RT_O17_ASSET_FAULT_DETAILS | V1 | Approved | PAPER
1 | SFR | SFR | SFR | Approved | Zip 10 | O20 | O20 | Zip2 | RT_O20_SITE_VISIT_READ_RESPONSE | V1 | Approved | PAPER
1 | SFR |  |  |  |  | O22 | O22 | Zip2 | RT_O22_ASSET_FAULT_RESPONSE | V1 | Approved | PAPER
1 | SFR |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Not required
1 | SWN | SWN | SWN | Approved | Zip 10 | C52 | C52 | REJECT | RT_C52_SHIPPER_WARNING_NOTIFICATION | V1 | Reject | IGT | Referred to UNCC.
1 | TAP | TAP | Not required | Not required | Not required | P17 | P17 | Zip 3 | RT_P17_TRANSCO_ASSET_PORTFOLIO | V3 | Approved
1 | UBR | UBR | UBR | Approved | Zip 10 | U13 | U13 | Zip 4 | RT_U13_SMP_DETAIL | V1 | Caveated Approval
1 | UBR |  |  |  |  | U14 | U14 | Zip 4 | RT_U14_METER_READS | V1 | Caveated Approval
1 | UDR | UDR | UDR | Approved | Zip 10 | U12 | U12 | Zip 4 | RT_U12_CLASS2_METER_READ | V1 | Caveated Approval
1 | UMR | UMR | Not required | Not required | Not required | U01 | U01 | Zip 4 | RT_U01_UNBUNDLED_METER_READ | V5 | Caveated Approval
1 | UPD | UPD | Not required | not required | Not required | ADDRS | ADDRS | Not required | ADDRS (DATASET-RGMA) | V13 | Not required
1 | UPD |  |  |  |  | APPNT | APPNT | Not required | APPNT (DATASET-RGMA) | V13 | Not required
1 | UPD |  |  |  |  | ASSET | ASSET | Zip 6 | ASSET (DATASET-RGMA) | V13 | Approved | RETRO
1 | UPD |  |  |  |  | CONVE | CONVE | Not required | CONVE (DATASET-RGMA) | V13 | Not required
1 | UPD |  |  |  |  | HEADR | HEADR | Not required | HEADR (DATASET-RGMA) | V13 | Not required
1 | UPD |  |  |  |  | METER | METER | Not required | METER (DATASET-RGMA) | V13 | Not required
1 | UPD |  |  |  |  | MKPRT | MKPRT | Not required | MKPRT (DATASET-RGMA) | V13 | Not required
1 | UPD |  |  |  |  | MTPNT | MTPNT | Not required | MTPNT (DATASET-RGMA) | V13 | Not required
1 | UPD |  |  |  |  | READG | READG | Not required | READG (DATASET-RGMA) | V13 | Not required
1 | UPD |  |  |  |  | REGST | REGST | Not required | REGST (DATASET-RGMA) | V13 | Not required
1 | UPD |  |  |  |  | TRAIL | TRAIL | Not required | TRAIL (DATASET-RGMA) | V13 | Not required
1 | URN | URN | Not required | Not required | Not required | U03 | U03 | Zip 4 | RT_U03_OPNG_UNBD_READ_NOTICE | V5 | Approved | PAPER
1 | URN |  |  |  |  | U04 | U04 | Zip 4 | RT_U04_FINAL_UNBD_READ_NOTICE | V5 | Approved
1 | URS | URS | Not required | Not required | Not required | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL | V2 | Not required
1 | URS |  |  |  |  | U02 | U02 | Zip 4 | RT_U02_UNBUNDLED_READ_REJECTION | V5 | Approved
1 | URS |  |  |  |  | U10 | U10 | Zip 4 | RT_U10_UNBUNDLED_READ_ACCEPTANCE | V5 | Approved
2 | AES | AES | AES | Approved | Zip 9 | C71 | C71 | Zip 1 | RT_C71_APPOINTED_ELECTED_SHIPPER_NOTFN | V1 | Approved | iGT
2 | AES |  |  |  |  | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS | V1 | Approved | iGT
2 | AES |  |  |  |  | S70 | S70 | Zip 6 | RT_S70_ADDRESS | V2 | Approved
2 | COI | COI | COI | Approved | Zip 9 | K43 | K43 | Zip 11 | RT_K43_STANDARD_INDIVIDUAL_SMP_FILE_DETAIL |  | Re-approved
2 | COI |  |  |  |  | K44 | K44 | Zip 11 | RT_K44_COMM_INDIVIDUAL_SMP_INVOICE_DETAIL_CLASS_3_AND_4 |  | Re-approved
2 | COM | COM | COM | Approved | Zip 9 | J30 | J30 | Zip 11 | RT_J30_ENERGY_SUMMARY_DETAIL |  | Re-approved
2 | COM |  |  |  |  | K42 | K42 | Zip 11 | RT_K42_COMM_CHARGE_ITEM |  | Re-approved
2 | COM |  |  |  |  | K78 | K78 | Zip 11 | RT_K78_COMM_INVOICE_DETAIL_CLASS_1_AND_2 |  | Re-approved
2 | COM |  |  |  |  | K79 | K79 | Zip 11 | RT_K79_COMM_INV_AGGREGATE_DETAIL_CLASS_3_AND_4 |  | Re-approved
2 | COM |  |  |  |  | Q28 | Q28 | Zip 11 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Re-approved
2 | COM |  |  |  |  | R15 | R15 | Zip 11 | RT_R15_COMM_LSEC_DAILY_LDZ_ENTRY_CHARGE |  | Re-approved
2 | CZI | CZI | CZI | Approved | Zip 9 | K43 | K43 | Zip 11 | RT_K43_STANDARD_INDIVIDUAL_SMP_FILE_DETAIL |  | Re-approved
2 | CZI |  |  |  |  | K47 | K47 | Zip 11 | RT_K47_CAP_INVOICE_LOW_DETAIL_CLASS_3_AND_4 |  | Re-approved
2 | DES | DES | DES | Approved | Zip 9 | C70 | C70 | Zip 1 | RT_C70_DEAPPNTD_ELCTD_SHIP_NOTFN | V1 | Approved | iGT
2 | DES |  |  |  |  | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS | V1 | Approved | iGT
2 | DES |  |  |  |  | S70 | S70 | Zip 6 | RT_S70_ADDRESS | V2 | Approved
2 | EOI | EOI | Not required | Not required | Not required | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
2 | EOI |  |  |  |  | Q29 | Q29 | Zip8 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Approved
2 | EOI |  |  |  |  | Q30 | Q30 | Zip8 | RT_Q30_INTERRUPTION_OPTION_DETAIL |  | Approved
2 | EOI |  |  |  |  | Q31 | Q31 | Zip8 | RT_Q31_INTERRUPTION_EXERCISE_DETAIL |  | Approved
2 | EOI |  |  |  |  | Q32 | Q32 | Zip8 | RT_Q32_INTERRUPTION_OPTION_ADJUSTMENT_DETAIL |  | Approved
2 | EOI |  |  |  |  | Q33 | Q33 | Zip8 | RT_Q33_INTERRUPTION_EXERCISE_ADJUSTMENT_DETAIL |  | Approved
2 | FSI | FSI | FSI | Approved | Zip 9 | K29 | K29 | Zip 11 | RT_K29_DNO_FSG_SUPPORTING_DOC_SUMMARY_DIRECT_CONNECTS |  | Re-approved
2 | FSI |  |  |  |  | K30 | K30 | Zip 11 | RT_K30_DNO_FSG_LDZ_PAID_DIRECT_FOR_DIRECT_CONNECTS |  | Re-approved
2 | FSI |  |  |  |  | K31 | K31 | Zip 11 | RT_K31_DNO_FSG_SUPPORTING_DOC_SUMMARY_CSEPS |  | Re-approved
2 | FSI |  |  |  |  | K32 | K32 | Zip 11 | RT_K32_DNO_FSG_LDZ_PAID_DIRECT_FOR_CSEPS |  | Re-approved
2 | FSI |  |  |  |  | Q28 | Q28 | Zip 11 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
2 | FSI |  |  |  |  | Q29 | Q29 | Zip 11 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Approved
2 | GEA | GEA | Not required | Not required | Not required | S96 | S96 | Zip 4 | RT_S96_GENERIC_ORGANISATION_ENTITY_AMENDMENT | V2 | Caveated Approval
2 | GEO | GEO | Not required | Not required | Not required | S97 | S97 | Zip5 | RT_S97_GENERIC_ORGANISATION_ENTITY_AMENDMENT_RESPONSE | V2 | Caveated Approval
2 | IIS | IIS | IIS | Approved | Zip 9 | K76 | K76 | Zip8 | RT_K76_ONE_OFF_CHARGE_SUMMARY |  | Approved
2 | IIS |  |  |  |  | K77 | K77 | Zip8 | RT_K77_INTEREST_DETAIL |  | Approved
2 | IIS |  |  |  |  | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
2 | IIS |  |  |  |  | Q29 | Q29 | Zip8 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Approved
2 | INV | INV | Re-approved | Approved | Zip 11 | I05 | I05 | Zip 11 | RT_I05_INVOICE_CLAUSE |  | Approved
2 | INV |  |  |  |  | I56 | I56 | Zip 11 | RT_I56_INVOICE_DETAIL |  | Caveated Approval
2 | INV |  |  |  |  | I57 | I57 | NA | RT_I57_ANCILLARY _INV_SUPP_INFO |  | Approved | Update needed | Shippers need to assess internally insertion of new record.
2 | INV |  |  |  |  | I58 | I58 | NA | RT_I58_INVOICE_REMITTANCE |  | Approved |  | Process clarification to follow
2 | INV |  |  |  |  | I59 | I59 | NA | RT_I59_INVOICE_ITEM_DETAIL |  | Approved |  | Allowable values, questions outstanding
2 | INV |  |  |  |  | I60 | I60 | Zip 11 | RT_I60_INVOICE_REMIT_DETAIL |  | Approved
2 | LIA | LIA | LIA | Approved | Zip 9 | K46 | K46 | Zip 11 | RT_K46_SSL_FSG_SUPPORTING_INFO_DETAIL |  | Re-approved
2 | LIA |  |  |  |  | K69 | K69 | Zip 11 | RT_K69_SSL_SUPPORTING_INFO_DETAIL |  | Re-approved
2 | LIA |  |  |  |  | K82 | K82 | Zip 11 | RT_K82_SSL_ONE_OFF_DETAIL |  | Approved
2 | LIA |  |  |  |  | K83 | K83 | Zip 11 | RT_K83_SSL_NETWORK_PAYMENT_DETAIL |  | Approved
2 | LIA |  |  |  |  | Q28 | Q28 | Zip 11 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
2 | LIA |  |  |  |  | Q29 | Q29 | Zip 11 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Approved
2 | MBR | MBR | Not required | Not required | Not required | M03 | M03 | Zip 6 | RT_M03_BILLREADS | V9 | Approved | PAPER
2 | MIF | MIF | MIF | Approved | Zip 9 | K49 | K49 | Zip8 | RT_K49_METER_ASSETS_DETAIL |  | Approved
2 | MIF |  |  |  |  | K50 | K50 | Zip8 | RT_K50_METER_PORTFOLIO_DETAIL |  | Approved
2 | MIF |  |  |  |  | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
2 | MIF |  |  |  |  | Q29 | Q29 | Zip8 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Approved
2 | MPD | MPD | Not required | Not required | Not required | S04 | S04 | Zip 11 | RT_S04_SP_MRF_AND_BATCH_FREQ_CANCELLATION | V3 | Re-approved
2 | MPD |  |  |  |  | S06 | S06 | Zip5 | RT_S06_SP_CAPACITY_CANCELLATION | V2 | Approved
2 | MPD |  |  |  |  | S08 | S08 | Zip 6 | RT_S08_LAPSED_CONFIRMATION_DETS | V2 | Approved
2 | MPD |  |  |  |  | S13 | S13 | Zip 3 | RT_S13_OBJECTION_CANCELLATION | V2 | Approved
2 | MPD |  |  |  |  | S31 | S31 | Zip 3 | RT_S31_INVALID_OFFER_DETAILS | V2 | Approved
2 | MPD |  |  |  |  | S88 | S88 | Zip 4 | RT_S88_CEASED_RESPONSIBILITY | V2 | Approved
2 | NMR | NMR | NMR | Approved | Zip 10 | K12 | K12 | Zip 1 | RT_K12_MAM_GAO_DETAIL | V7 | Approved
2 | NMR |  |  |  |  | K14 | K14 | Zip2 | RT_K14_ADDITIONAL_METERING INFORMATION | V4 | Caveated Approval
2 | NMR |  |  |  |  | K85 | K85 | Zip2 | RT_K85_GENERIC_ORG_NOTIFICATION | V1 | Caveated Approval
2 | NMR |  |  |  |  | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS | V1 | Approved | iGT
2 | NMR |  |  |  |  | Q51 | Q51 | Zip 3 | RT_Q51_CONSUMPTION_INFORMATION | V1 | Caveated Approval
2 | NMR |  |  |  |  | S21 | S21 | Zip5 | RT_S21_CUR_SP_NOM_REJ_OR_REF | V3 | Caveated Approval
2 | NMR |  |  |  |  | S59 | S59 | NA | RT_S59_ACCEPT_SMP_ENQUIRY | V5 | Deferred | PAPER | Allowable values, questions outstanding
2 | NMR |  |  |  |  | S64 | S64 | NA | RT_S64_OFFER_DETAILS | V6 | Caveated Re-Approval |  | Allowable values, questions outstanding
2 | NMR |  |  |  |  | S68 | S68 | Zip5 | RT_S68_ENQ_SUPPLY_METER_POINT | V2 | Approved | PAPER
2 | NMR |  |  |  |  | S69 | S69 | Zip 3 | RT_S69_NOM_SUPPLY_METER_POINT | V3 | Approved
2 | NMR |  |  |  |  | S70 | S70 | Zip 6 | RT_S70_ADDRESS | V2 | Approved
2 | NMR |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL |  | Not required
2 | NMR |  |  |  |  | S75 | S75 | Zip 11 | RT_S75_METER_POINT_DETAILS | V6 | Re-approved
2 | NMR |  |  |  |  | S78 | S78 | Zip 7 | RT_S78_REJECT_SMP_ENQUIRY | V2 | Approved
2 | NMR |  |  |  |  | S98 | S98 | Zip 4 | RT_S98_SMART_DATA | V2 | Approved
2 | NMR |  |  |  |  | U70 | U70 | Zip5 | RT_U70_NTS_OPTIONAL_RATE_REQ |  | Approved
2 | NMR |  |  |  |  | U71 | U71 | Zip 6 | RT_U71_NTS_OPTIONAL_RATE_DET | V1 | Caveated Approval
2 | NMR |  |  |  |  | U72 | U72 | Zip 7 | RT_U72_LDZ_OPTIONAL_RATE_REQ |  | Approved
2 | NMR |  |  |  |  | U73 | U73 | Zip 7 | RT_U73_LDZ_OPTIONAL_RATE_DET | V1 | Caveated Approval
2 | NMR |  |  |  |  | U74 | U74 | Zip 6 | RT_U74_CSO_DETAILS | V1 | Caveated Approval
2 | NMR |  |  |  |  | U75 | U75 | Zip 4 | RT_U75_METER_ASSET_DETAILS | V1 | Approved
2 | NOM | NOM | NOM | Approved | Zip 10 | S21 | S21 | Zip5 | RT_S21_CUR_SP_NOM_REJ_OR_REF | V3 | Caveated Approval
2 | NOM |  |  |  |  | S47 | S47 | Zip 3 | RT_S47_SUPPLY_POINT_ENQUIRY_REQ | V2 | Approved | PAPER
2 | NOM |  |  |  |  | S48 | S48 | Zip5 | RT_S48_SMP_NOMINATION_REQ | V3 | Caveated Approval
2 | NOM |  |  |  |  | S68 | S68 | Zip5 | RT_S68_ENQ_SUPPLY_METER_POINT | V2 | Approved | PAPER
2 | NOM |  |  |  |  | S69 | S69 | Zip 3 | RT_S69_NOM_SUPPLY_METER_POINT |  | Approved
2 | NOM |  |  |  |  | U70 | U70 | Zip5 | RT_U70_NTS_OPTIONAL_RATE_REQ | V1 | Approved
2 | NOM |  |  |  |  | U72 | U72 | Zip 7 | RT_U72_LDZ_OPTIONAL_RATE_REQ | V1 | Approved
2 | NRF | NRF | NRF | Approved | Zip 10 | K12 | K12 | Zip 1 | RT_K12_MAM_GAO_DETAIL | V7 | Approved
2 | NRF |  |  |  |  | K14 | K14 | Zip2 | RT_K14_ADDITIONAL_METERING INFORMATION | V4 | Caveated Approval
2 | NRF |  |  |  |  | K85 | K85 | Zip2 | RT_K85_GENERIC_ORG_NOTIFICATION | V1 | Caveated Approval
2 | NRF |  |  |  |  | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS | V1 | Approved | iGT
2 | NRF |  |  |  |  | Q46 | Q46 | Zip 3 | RT_Q46_IGT_RESPONSE | V1 | Approved | iGT
2 | NRF |  |  |  |  | S21 | S21 | Zip5 | RT_S21_CUR_SP_NOM_REJ_OR_REF | V3 | Caveated Approval
2 | NRF |  |  |  |  | S64 | S64 | NA | RT_S64_OFFER_DETAILS | V6 | Caveated Approval |  | Allowable values, questions outstanding
2 | NRF |  |  |  |  | S69 | S69 | Zip 3 | RT_S69_NOM_SUPPLY_METER_POINT | V3 | Approved
2 | NRF |  |  |  |  | S70 | S70 | Zip 6 | RT_S70_ADDRESS | V2 | Approved
2 | NRF |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL |  | Not required
2 | NRF |  |  |  |  | S75 | S75 | Zip 11 | RT_S75_METER_POINT_DETAILS | V6 | Re-approved
2 | NRF |  |  |  |  | S98 | S98 | Zip 4 | RT_S98_SMART_DATA | V2 | Approved
2 | NRF |  |  |  |  | U70 | U70 | Zip5 | RT_U70_NTS_OPTIONAL_RATE_REQ |  | Approved
2 | NRF |  |  |  |  | U71 | U71 | Zip 6 | RT_U71_NTS_OPTIONAL_RATE_DET | V1 | Caveated Approval
2 | NRF |  |  |  |  | U72 | U72 | Zip 7 | RT_U72_LDZ_OPTIONAL_RATE_REQ |  | Approved
2 | NRF |  |  |  |  | U73 | U73 | Zip 7 | RT_U73_LDZ_OPTIONAL_RATE_DET | V1 | Caveated Approval
2 | NRF |  |  |  |  | U74 | U74 | Zip 6 | RT_U74_CSO_DETAILS | V1 | Caveated Approval
2 | NRF |  |  |  |  | U75 | U75 | Zip 4 | RT_U75_METER_ASSET_DETAILS | V1 | Approved
2 | NSC | NSC | NSC | Approved | Zip 10 | K57 | K57 | Zip8 | RT_K57_COMPRESSION_SUPPORTING_INFORMATION |  | Caveated Approval
2 | NSC |  |  |  |  | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
2 | NSC |  |  |  |  | Q29 | Q29 | Zip8 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Caveated Approval
2 | OSG | OSG | OSG | Approved | Zip 10 | K55 | K55 | Zip8 | RT_K55_OWN_USE_GAS_SUPPORTING_INFORMATION |  | Caveated Approval
2 | OSG |  |  |  |  | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
2 | OSG |  |  |  |  | Q29 | Q29 | Zip8 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Caveated Approval
2 | TDS | TDS | TDS | Approved | Zip 10 | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
2 | TDS |  |  |  |  | Q29 | Q29 | Zip8 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Caveated Approval
2 | TDS |  |  |  |  | T92 | T92 | Zip8 | RT_T92_SITE_VISIT_CHARGE_DETAIL |  | Caveated Approval
2 | UPI | UPI | UPI | Approved | Zip 10 | K72 | K72 | Zip8 | RT_K72_USER_PAYS_SHIPPER_AGREED_READS_CHARGE_SUMMARY |  | Caveated Approval
2 | UPI |  |  |  |  | K73 | K73 | Zip8 | RT_K73_USER_PAYS_SHIPPER_AGREED_READS_CHARGE_DETAIL |  | Approved
2 | UPI |  |  |  |  | K74 | K74 | Zip8 | RT_K74_USER_PAYS_MUST_READS_CHARGE_SUMMARY |  | Approved
2 | UPI |  |  |  |  | K75 | K75 | Zip8 | RT_K75_USER_PAYS_MUST_READS_CHARGE_DETAIL |  | Approved
2 | UPI |  |  |  |  | K76 | K76 | Zip8 | RT_K76_ONE_OFF_CHARGE_SUMMARY |  | Approved
2 | UPI |  |  |  |  | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
2 | UPI |  |  |  |  | Q29 | Q29 | Zip8 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Caveated Approval
2 | WAO | WAO | Not required | Not required | Not required | S39 | S39 | Zip 3 | RT_S39_WITHDRAW_FROM_SP_REQ | V2 | Approved
2 | WAO |  |  |  |  | S40 | S40 | Zip 3 | RT_S40_OBJ_TO_WITHDRAWAL_REQ | V3 | Approved
2 | WAO |  |  |  |  | S41 | S41 | Zip 6 | RT_S41_CANCEL_OBJECTION_REQ | V2 | Approved
2 | WAO |  |  |  |  | S54 | S54 | Zip 3 | RT_S54_REC_OBJECTION_SUPP_DETS | V2 | Approved
2 | WAO |  |  |  |  | S73 | S73 | Zip5 | RT_S73_CANCEL_OBJ_AND_WITHDRAW | V2 | Approved
2 | WAO |  |  |  |  | S74 | S74 | Zip 4 | RT_S74_SUPPLEMENTARY_DETAILS | V2 | Approved
2 | WOR | WOR | Not required | Not required | Not required | S11 | S11 | Zip 3 | RT_S11_VOLUNTARY_SP_WITHDRAWAL | V2 | Approved | PAPER
2 | WOR |  |  |  |  | S12 | S12 | Zip 3 | RT_S12_OBJECTION | V3 | Approved
2 | WOR |  |  |  |  | S13 | S13 | Zip 3 | RT_S13_OBJECTION_CANCELLATION | V2 | Approved
2 | WOR |  |  |  |  | S14 | S14 | Zip 3 | RT_S14_OBJ_CANCELLATION_NOTICE | V2 | Approved
2 | WOR |  |  |  |  | S26 | S26 | Zip 3 | RT_S26_OBJ_SUPPLMNTRY_DETS | V2 | Approved
2 | WOR |  |  |  |  | S30 | S30 | Zip5 | RT_S30_OBJ_SUPPLEMENTARY_NOTICE | V5 | Approved
2 | WOR |  |  |  |  | S65 | S65 | Zip 6 | RT_S65_OBJECTION_NOTIFICATION | V2 | Approved
2 | WOR |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL |  | Not required
2 | ZCS | ZCS | ZCS | Approved | Zip 10 | I09 | I09 | Zip8 | RT_I09_CAP_RATCHET_CHARGE_DETAIL |  | Caveated Approval
2 | ZCS |  |  |  |  | K42 | K42 | Zip8 | RT_K42_COMM_CHARGE_ITEM |  | Approved
2 | ZCS |  |  |  |  | K54 | K54 | Zip8 | RT_K54_CAP_ADMIN_CHARGE_DETAIL |  | Approved
2 | ZCS |  |  |  |  | K71 | K71 | Zip8 | RT_K71_CAP_SEASONAL_CAPACITY_FAILURE_CHARGE_DETAIL |  | Approved
2 | ZCS |  |  |  |  | K80 | K80 | Zip8 | RT_K80_CAP_INV_DETAIL_CLASS_1_AND_2 |  | Approved | PAPER
2 | ZCS |  |  |  |  | K81 | K81 | Zip8 | RT_K81_CAP_INV_AGGREGATE_DETAIL_CLASS_3_AND_4 |  | Approved | PAPER
2 | ZCS |  |  |  |  | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
3 | AML | AML | AML | Approved | Zip 9 | K43 | K43 | NA | RT_K43_STANDARD_INDIVIDUAL_SMP_FILE_DETAIL |  | Approved
3 | AML |  |  |  |  | K92 | K92 | NA | RT_K92_AMENDMENTS_SMP_DETAIL_CLASS_3_AND_4 |  | Approved |  | Domain Questions Outstanding
3 | ASP | ASP | ASP | Approved | Zip 9 | J13 | J13 | Zip8 | RT_J13_REC_INV_RBD_CHARGE |  | Approved
3 | ASP |  |  |  |  | J14 | J14 | Zip8 | RT_J14_REC_INV_RBD_LDZ_AGGREGATE |  | Approved
3 | ASP |  |  |  |  | J15 | J15 | Zip8 | RT_J15_REC_INV_RBD_SPG_DETAIL |  | Approved
3 | ASP |  |  |  |  | J42 | J42 | Zip8 | RT_J42_ DAILY_SUMMARY_NTS_OPTIONAL_TARIFF |  | Approved
3 | ASP |  |  |  |  | K42 | K42 | Zip8 | RT_K42_COMM_CHARGE_ITEM |  | Approved
3 | ASP |  |  |  |  | K84 | K84 | Zip8 | RT_K84_CAPACITY_RECONCILIATION_CHARGE |  | Approved
3 | ASP |  |  |  |  | K88 | K88 | Zip8 | RT_K88_RECONCILIATION_INVOICE_CHARGE_CLASS_4_LSP |  | Approved
3 | ASP |  |  |  |  | K89 | K89 | Zip8 | RT_K89_RECONCILIATION_INVOICE_CHARGE_CLASS_1_2_3_LSP |  | Approved
3 | ASP |  |  |  |  | K90 | K90 | Zip8 | RT_K90_RECONCILIATION_INV_AGGREGATE_DETAIL_CLASS_3_4_SSP |  | Approved
3 | ASP |  |  |  |  | K91 | K91 | Zip8 | RT_K91_RECONCILIATION_INVOICE_UG_SMEAR |  | Approved
3 | ASP |  |  |  |  | K93 | K93 | Zip8 | RT_K93_AMENDMENT_SMP_DETAIL |  | Approved
3 | ASP |  |  |  |  | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Approved
3 | CFR | CFR | CFR | Approved | Zip 9 | K12 | K12 | Zip 1 | RT_K12_MAM_GAO_DETAIL |  | Caveated Approval
3 | CFR |  |  |  |  | K14 | K14 | Zip2 | RT_K14_ADDITIONAL_METERING INFORMATION |  | Caveated Approval
3 | CFR |  |  |  |  | K85 | K85 | Zip2 | RT_K85_GENERIC_ORG_NOTIFICATION |  | Caveated Approval
3 | CFR |  |  |  |  | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS |  | Approved | IGT
3 | CFR |  |  |  |  | Q45 | Q45 | Zip 3 | RT_Q45_DNI_INFO |  | Approved
3 | CFR |  |  |  |  | S07 | S07 | Zip 11 | RT_S07_ACCEPTED_CONFIRMATION |  | Re-approved
3 | CFR |  |  |  |  | S09 | S09 | Zip 3 | RT_S09_REJECT_COMPETITIVE_CONF |  | Approved
3 | CFR |  |  |  |  | S10 | S10 | Zip 11 | RT_S10_SP_WITHDRAWAL_NOTICE |  | Re-approved
3 | CFR |  |  |  |  | S16 | S16 | Zip5 | RT_S16_REJECT_NON_COMPTITVE_CONF |  | Caveated Approval
3 | CFR |  |  |  |  | S66 | S66 | Zip5 | RT_S66_CONTACT_DETAILS |  | Approved
3 | CFR |  |  |  |  | S67 | S67 | Zip 6 | RT_S67_ELECTRONIC_DEVICE |  | Approved | SME update pending
3 | CFR |  |  |  |  | S70 | S70 | Zip 6 | RT_S70_ADDRESS |  | Approved
3 | CFR |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL |  | Not required
3 | CFR |  |  |  |  | S75 | S75 | Zip 11 | RT_S75_METER_POINT_DETAILS |  | Re-approved
3 | CFR |  |  |  |  | S77 | S77 | Zip5 | RT_S77_WITHDRAWAL_MP_DETAILS |  | Approved
3 | CFR |  |  |  |  | S83 | S83 | Not required | RT_S83_END_CONSUMER_DETAILS |  | Not required
3 | CFR |  |  |  |  | S84 | S84 | Zip 6 | RT_S84_SPECIAL_CONDITIONS |  | Approved
3 | CFR |  |  |  |  | S98 | S98 | Zip 4 | RT_S98_SMART_DATA |  | Approved
3 | CFR |  |  |  |  | T06 | T06 | Zip 4 | RT_T06_CONF_CANCELLATION_RESPONS |  | Approved
3 | CFR |  |  |  |  | T07 | T07 | Zip 11 | RT_T07_CONF_CANCELLATION_NOTICE |  | Re-approved
3 | CFR |  |  |  |  | U70 | U70 | Zip5 | RT_U70_NTS_OPTIONAL_RATE_REQ |  | Caveated Approval
3 | CFR |  |  |  |  | U71 | U71 | Zip 6 | RT_U71_NTS_OPTIONAL_RATE_DET |  | Caveated Approval
3 | CFR |  |  |  |  | U72 | U72 | Zip 7 | RT_U72_LDZ_OPTIONAL_RATE_REQ |  | Caveated Approval
3 | CFR |  |  |  |  | U73 | U73 | Zip 7 | RT_U73_LDZ_OPTIONAL_RATE_DET |  | Caveated Approval
3 | CFR |  |  |  |  | U74 | U74 | Zip 6 | RT_U74_CSO_DETAILS |  | Caveated Approval
3 | CFR |  |  |  |  | U75 | U75 | Zip 4 | RT_U75_METER_ASSET_DETAILS |  | Approved
3 | CNF | CNF | CNF | Approved | Zip 9 | S38 | S38 | Zip 7 | RT_S38_CONFIRM_COMPTVE_SUPPLY_PT |  | Approved
3 | CNF |  |  |  |  | S42 | S42 | Zip5 | RT_S42_CONFIRM_NON_COMPETVE_SP |  | Approved
3 | CNF |  |  |  |  | S66 | S66 | Zip5 | RT_S66_CONTACT_DETAILS |  | Approved
3 | CNF |  |  |  |  | S67 | S67 | Zip 6 | RT_S67_ELECTRONIC_DEVICE |  | Approved | SME update pending
3 | CNF |  |  |  |  | S83 | S83 | Not required | RT_S83_END_CONSUMER_DETAILS |  | Not required
3 | CNF |  |  |  |  | S84 | S84 | Zip 6 | RT_S84_SPECIAL_CONDITIONS |  | Approved
3 | CNF |  |  |  |  | T05 | T05 | Zip 4 | RT_T05_CONF_CANCELLATION_REQUEST |  | Approved
3 | CNF |  |  |  |  | U70 | U70 | Zip5 | RT_U70_NTS_OPTIONAL_RATE_REQ |  | Caveated Approval
3 | CNF |  |  |  |  | U72 | U72 | Zip 7 | RT_U72_LDZ_OPTIONAL_RATE_REQ |  | Caveated Approval
3 | CRF | CRF | CRF | Approved | Zip 9 | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS |  | Approved | iGT
3 | CRF |  |  |  |  | Q46 | Q46 | Zip 3 | RT_Q46_IGT_RESPONSE |  | Approved | iGT
3 | CRF |  |  |  |  | S05 | S05 | Zip5 | RT_S05_SP_CAPACITY_CHANGE |  | Approved
3 | CRF |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL |  | Not required
3 | CRF |  |  |  |  | U71 | U71 | Zip 6 | RT_U71_NTS_OPTIONAL_RATE_DET |  | Caveated Approval
3 | CRF |  |  |  |  | U73 | U73 | Zip 7 | RT_U73_LDZ_OPTIONAL_RATE_DET |  | Caveated Approval
3 | CRF |  |  |  |  | U82 | U82 | Zip 6 | RT_U82_NTS_OPT_RATE_CHAN_RESP |  | Approved
3 | DCF | DCF | Not required | Not required | Not required | S08 | S08 | Zip 6 | RT_S08_LAPSED_CONFIRMATION_DETS |  | Approved
3 | DCF |  |  |  |  | S63 | S63 | Zip 3 | RT_S63_NTFN_OF_RETAINED_RESPONS |  | Approved
3 | DCF |  |  |  |  | S70 | S70 | Zip 6 | RT_S70_ADDRESS |  | Approved
3 | DCF |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL |  | Not required
3 | DCF |  |  |  |  | S76 | S76 | Zip5 | RT_S76_LAPSED_CONF_MP_DETAILS |  | Approved
3 | DCF |  |  |  |  | S88 | S88 | Zip 4 | RT_S88_CEASED_RESPONSIBILITY |  | Approved
3 | DNE | DNE | DNE | Approved | Zip 9 | E89 | E89 | Zip 1 | RT_E89_DAILY_ENERGY |  | Approved
3 | DNE |  |  |  |  | E90 | E90 | Zip 1 | RT_E90_SHIPPER_DETAILS |  | Approved
3 | DNE |  |  |  |  | E91 | E91 | Zip 1 | RT_E91_ENERGY_REC_DATA |  | Approved
3 | DNE |  |  |  |  | E92 | E92 | Zip 1 | RT_E92_SHIPPER_ALLOCATION |  | Approved
3 | DNR | DNR | DNR | Approved | Zip 9 | E87 | E87 | Zip 1 | RT_E87_REC_ENERGY_SPLIT |  | Approved
3 | DNR |  |  |  |  | E88 | E88 | Zip 11 | RT_E88_SHIPPER_REC_ALLOCATION |  | Re-approved
3 | EXZ | EXZ | Not required | Not required | Not required | M13 | M13 | Not required | RT_M13_EXZ_LDZ_DETAILS |  | Approved
3 | EXZ |  |  |  |  | M15 | M15 | Zip2 | RT_M15_CONFIRMATION_NOTIFICATION |  | Approved | Product missed - now seeking approval
3 | EXZ |  |  |  |  | S31 | S31 | Zip 3 | RT_S31_INVALID_OFFER_DETAILS |  | Approved
3 | EXZ |  |  |  |  | S70 | S70 | Zip 6 | RT_S70_ADDRESS |  | Approved
1 &3 | MIN | MIN | MIN | Approved | Zip 9 | C73 | C73 | Zip 1 | RT_C73_CHECK_READ_DUE_NOTFN |  | Approved
1 &3 | MIN |  |  |  |  | M96 | M96 | Zip2 | RT_M96_METER_INSPECT_DUE_NOTICE |  | Approved
1 &3 | MIN |  |  |  |  | O52 | O52 | Zip 3 | RT_O52_FAULT_NOTFN |  | Approved
1 &3 | MIN |  |  |  |  | S70 | S70 | Zip 6 | RT_S70_ADDRESS |  | Approved
3 | NRL | NRL | NRL | Approved | Zip 10 | S91 | S91 | Zip5 | RT_S91_NTFN_OF_SP_REVISION |  | Approved
3 | NRL |  |  |  |  | T04 | T04 | Zip5 | RT_T04_NTFN_MP_AQ_REVISION |  | Caveated Approval
3 | NRL |  |  |  |  | T50 | T50 | Zip 11 | RT_T50_NTFN_MP_WC_REVISION |  | Re-approved
3 | NRL |  |  |  |  | T51 | T51 | Not required | RT_T51_WC_CALC_WARNINGS_REPORT |  | Approved
3 | NRL |  |  |  |  | T97 | T97 | Zip5 | RT_T97_REVISED_AQ_IMPACTS_INFO |  | Approved | SME update pending
3 | NRL |  |  |  |  | T98 | T98 | Zip5 | RT_T98_AQ_CALC_FAILURE |  | Approved
3 | PNS | PNS | PNS | Approved | Zip 10 | K86 | K86 | Zip8 | RT_K86_PRIME_AND_SUB_CHARGE_SUMMARY |  | Caveated Approval
3 | PNS |  |  |  |  | K87 | K87 | Zip8 | RT_K87_ PRIME_AND_SUB_CHARGE_DETAIL |  | Caveated Approval
3 | PNS |  |  |  |  | Q28 | Q28 | Zip8 | RT_Q28_STANDARD_INVOICE_SUMMARY |  | Caveated Approval
3 | PNS |  |  |  |  | Q29 | Q29 | Zip8 | RT_Q29_STANDARD_CHARGE_TYPE_SUMMARY |  | Caveated Approval
3 | RTO | RTO | RTO | Deferred | Zip 10 | ASSET | ASSET | REJECT | ASSET (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTO |  |  |  |  | CONVE | CONVE | REJECT | CONVE (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTO |  |  |  |  | HEADR | HEADR | REJECT | HEADR (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTO |  |  |  |  | METER | METER | REJECT | METER (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTO |  |  |  |  | MTPNT | MTPNT | REJECT | MTPNT (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTO |  |  |  |  | READG | READG | REJECT | READG (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTO |  |  |  |  | REGST | REGST | REJECT | REGST (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTO |  |  |  |  | TRAIL | TRAIL | REJECT | TRAIL (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTR | RTR | RTR | Deferred | Zip 10 | HEADR | HEADR | REJECT | HEADR (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTR |  |  |  |  | REJFL | REJFL | REJECT | REJFL (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTR |  |  |  |  | REJRS | REJRS | REJECT | REJRS (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTR |  |  |  |  | TRAIL | TRAIL | REJECT | TRAIL (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | RTR |  |  |  |  | TROUT | TROUT | REJECT | TROUT (DATASET-RGMA) |  | REJECT | Retro | Referred to UNCC.
3 | SCR | SCR | SCR | Approved | Zip 10 | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS |  | Approved | iGT
3 | SCR |  |  |  |  | S03 | S03 | Zip5 | RT_S03_SP_MRF_AND_BATCH_FREQ_CHANGE |  | Approved
3 | SCR |  |  |  |  | S04 | S04 | Zip 11 | RT_S04_SP_MRF_AND_BATCH_FREQ_CANCELLATION |  | Re-approved
3 | SCR |  |  |  |  | S05 | S05 | Zip5 | RT_S05_SP_CAPACITY_CHANGE |  | Caveated Approval
3 | SCR |  |  |  |  | S06 | S06 | Zip5 | RT_S06_SP_CAPACITY_CANCELLATION |  | Approved
3 | SCR |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL |  | Not required
3 | SCR |  |  |  |  | U71 | U71 | Zip 6 | RT_U71_NTS_OPTIONAL_RATE_DET |  | Caveated Approval
3 | SCR |  |  |  |  | U73 | U73 | Zip 7 | RT_U73_LDZ_OPTIONAL_RATE_DET |  | Caveated Approval
3 | SCR |  |  |  |  | U82 | U82 | Zip 6 | RT_U82_NTS_OPT_RATE_CHAN_RESP |  | Approved
3 | SCR |  |  |  |  | U83 | U83 | Zip 6 | RT_U83_NTS_OPT_RATE_CAN_RESP |  | Approved
3 | SCR |  |  |  |  | X09 | X09 | Zip 11 | RT_X09_SP_CLASS_CHANGE |  | Re-approved
3 | SCR |  |  |  |  | X10 | X10 | Zip 6 | RT_X10_SP_CLASS_CHANGE_CANCELLATION |  | Approved
3 | SPC | SPC | SPC | Approved | Zip 10 | C38 | C38 | Zip 1 | RT_C38_CLASS_CHANGE |  | Approved
3 | SPC |  |  |  |  | C39 | C39 | Zip 1 | RT_C39_CLASS_CHANGE_CANCELLATION |  | Approved
3 | SPC |  |  |  |  | S34 | S34 | Zip5 | RT_S34_MRF_AND_BATCH_FREQ_CHANGE_REQUEST |  | Caveated Approval
3 | SPC |  |  |  |  | S35 | S35 | Zip 11 | RT_S35_CANCEL_MRF_AND_BATCH_FREQ_CHANGE_REQ |  | Re-approved
3 | SPC |  |  |  |  | S36 | S36 | Zip 3 | RT_S36_SP_CAPACITY_CHANGE_REQ |  | Approved
3 | SPC |  |  |  |  | S37 | S37 | Zip 3 | RT_S37_CANCEL_SP_CAPACITY_CHG |  | Approved
3 | SPC |  |  |  |  | U80 | U80 | Zip 6 | RT_U80_NTS_OPT_RATE_CHANGE |  | Approved
3 | SPC |  |  |  |  | U81 | U81 | Zip 6 | RT_U81_NTS_OPT_RATE_CANCEL |  | Approved
3 | SPI | SPI | Not required | Not required | Not required | X99 | X99 | Zip 6 | RT_X99_SHIPPER_SUPPLY_PORTFOLIO_INPUT |  | Approved | SME update pending
3 | SPO | SPO | Not required | Not required | Not required | X98 | X98 | Zip 6 | RT_X98_SHIPPER_SUPPLY_PORTFOLIO_OUTPUT |  | Approved | SME update pending
3 | STN | STN | STN | Approved | Zip 10 | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS |  | Approved | iGT
3 | STN |  |  |  |  | U76 | U76 | Reject | RT_U76_NETWORK_CHANGE_DETAILS |  | REJECT | iGT | Referred to UNCC.
3 | STN |  |  |  |  | U79 | U79 | REJECT | RT_U79_SUPPLY_METER_POINT_INFO |  | REJECT | iGT | Referred to UNCC.
3 | TRF | TRF | TRF | Approved | Zip 10 | K12 | K12 | Zip 1 | RT_K12_MAM_GAO_DETAIL |  | Caveated Approval
3 | TRF |  |  |  |  | K13 | K13 | Zip 1 | RT_K13_SMP_CEASE_OWN_DETS |  | Approved
3 | TRF |  |  |  |  | K85 | K85 | Zip2 | RT_K85_GENERIC_ORG_NOTIFICATION |  | Caveated Approval
3 | TRF |  |  |  |  | Q44 | Q44 | Zip 11 | RT_Q44_CSEP_DETAILS |  | Approved | iGT
3 | TRF |  |  |  |  | Q45 | Q45 | Zip 3 | RT_Q45_DNI_INFO |  | Approved
3 | TRF |  |  |  |  | S08 | S08 | Zip 6 | RT_S08_LAPSED_CONFIRMATION_DETS |  | Approved
3 | TRF |  |  |  |  | S15 | S15 | Zip 11 | RT_S15_TRANSFER_OF_OWNERSHIP |  | Approved | SME update pending
3 | TRF |  |  |  |  | S63 | S63 | Zip 3 | RT_S63_NTFN_OF_RETAINED_RESPONS |  | Approved
3 | TRF |  |  |  |  | S66 | S66 | Zip5 | RT_S66_CONTACT_DETAILS |  | Approved
3 | TRF |  |  |  |  | S67 | S67 | Zip 6 | RT_S67_ELECTRONIC_DEVICE |  | Approved | SME update pending
3 | TRF |  |  |  |  | S70 | S70 | Zip 6 | RT_S70_ADDRESS |  | Approved
3 | TRF |  |  |  |  | S72 | S72 | Not required | RT_S72_REJECTION_DETAIL |  | Not required
3 | TRF |  |  |  |  | S75 | S75 | Zip 11 | RT_S75_METER_POINT_DETAILS |  | Approved
3 | TRF |  |  |  |  | S76 | S76 | Zip5 | RT_S76_LAPSED_CONF_MP_DETAILS |  | Approved
3 | TRF |  |  |  |  | S88 | S88 | Zip 4 | RT_S88_CEASED_RESPONSIBILITY |  | Approved
3 | TRF |  |  |  |  | S98 | S98 | Zip 4 | RT_S98_SMART_DATA |  | Approved
3 | TRF |  |  |  |  | U71 | U71 | Zip 6 | RT_U71_NTS_OPTIONAL_RATE_DET |  | Approved
3 | TRF |  |  |  |  | U73 | U73 | Zip 7 | RT_U73_LDZ_OPTIONAL_RATE_DET |  | Approved
3 | TRF |  |  |  |  | U74 | U74 | Zip 6 | RT_U74_CSO_DETAILS |  | Approved
3 | TRF |  |  |  |  | U75 | U75 | Zip 4 | RT_U75_METER_ASSET_DETAILS |  | Approved
|  |  | Key: |  |  |  | Key: |  |  |  | Key
|  |  | Approved |  |  |  | Approved |  |  |  | Approved
|  |  | For Approval |  |  |  | For Approval |  |  |  | Deferred
|  |  | Rejected |  |  |  | Rejected |  |  |  | Reject

## Internal Change
Records | Published Field Name | Proposed Update | Reason for Change
E88 | ALLOCATION_SPLIT | Field length to be changed from 2 to 3. | In the scenario where a single shipper has 100% of the allocation a field length of 2 is insufficient to contain this detail.
I57 | ADDITIONAL RECORD | The I57 record needs to be included in the new Generic Invoice File (INV) | In order to provide the same level of information that the recipient current has through the Adhoc Invoice (ADH) the I57 record must be included in the Generic Invoice File (INV). Inclusion of this additional record ensures that all relevant supporting information can be provided to Users within the INV file - rather than by separate communication routes - e.g. email.
I59 | INVOICE_ITEM_VAT_CODE | New Data Item included at bottom or Record | Code to identify which type of VAT is being used.
K29 | FSG_CODE | Replace FSG_CODE with FSG_COMPENSATION_CODE | FSG_CODE Needs to be replaced with FSG_COMPENSATION_CODE Also the Definition needs to be amended as 'DEFINITION: Compensation code for the Failure to Supply Gas Incident' VALUE: For Direct Connect: CREDITS: 1 – 52 DEBIT: 99 For CSEPS: CREDITS: C1 – C52 DEBIT: C99
K30 | FSG_CODE | Replace FSG_CODE with FSG_COMPENSATION_CODE | FSG_CODE Needs to be replaced with FSG_COMPENSATION_CODE Also the Definition needs to be amended as 'DEFINITION: Compensation code for the Failure to Supply Gas Incident' VALUE: For Direct Connect: CREDITS: 1 – 52 DEBIT: 99 For CSEPS: CREDITS: C1 – C52 DEBIT: C99
K31 | FSG_CODE | Replace FSG_CODE with FSG_COMPENSATION_CODE | FSG_CODE Needs to be replaced with FSG_COMPENSATION_CODE Also the Definition needs to be amended as 'DEFINITION: Compensation code for the Failure to Supply Gas Incident' VALUE: For Direct Connect: CREDITS: 1 – 52 DEBIT: 99 For CSEPS: CREDITS: C1 – C52 DEBIT: C99
K32 | FSG_CODE | Replace FSG_CODE with FSG_COMPENSATION_CODE | FSG_CODE Needs to be replaced with FSG_COMPENSATION_CODE Also the Definition needs to be amended as 'DEFINITION: Compensation code for the Failure to Supply Gas Incident' VALUE: For Direct Connect: CREDITS: 1 – 52 DEBIT: 99 For CSEPS: CREDITS: C1 – C52 DEBIT: C99
K43 | EUC_DESCRIPTION | EUC_DESCRIPTION to be replaced with EUC_NUMBER | This change is to ensure that the field is consistent with other invoicing formats, For current Invoicing files the EUC Number is used instead of EUC Description. User representations requested for consistent use of EUC Number across invoicing files.
K44 | CSEP_PROJECT_REFERENCE_NUMBER | CSEP_PROJECT_REFERENCE_NUMBER in the K44 record needs to be updated to be called CSEP_ID and the field length amended to 8. | This field has been amended to bring it in line with the field name and length used in the SPA process
K46 | FIXED_LIABILITY_COST | * The field name to be changed to FIXED_LIABILITY_RATE * The length to be changed to 8 and the decimal to 4 | * The field name has been changed to provide consistency in the use of rate as an attribute across all files. * Original field length defined for this attribute was incorrect and has been amended accordingly
K46 | FSG_CODE | Replace FSG_CODE with FSG_COMPENSATION_CODE | FSG_CODE Needs to be replaced with FSG_COMPENSATION_CODE Also the Definition needs to be amended as 'DEFINITION: Compensation code for the Failure to Supply Gas Incident' VALUE: For Direct Connect: CREDITS: 1 – 52 DEBIT: 99 For CSEPS: CREDITS: C1 – C52 DEBIT: C99
K69 | SHIPPER_PERFORMANCE% | * To take the '%' off from field names * To change the length from 14 to 5 | * Percentage sign has been removed from the field name as this is not a standard character to be used in a field name. * Original field length defined for this attribute was incorrect and has been amended accordingly
K69 | ALL_SHIPPER_PERFORMANCE% | * To take the '%' off from field names * To change the length from 14 to 5 | * Percentage sign has been removed from the field name as this is not a standard character to be used in a field name. * Original field length defined for this attribute was incorrect and has been amended accordingly
K69 | PPL% | * To take the '%' off from field names * To change the length from 14 to 5 | * Percentage sign has been removed from the field name as this is not a standard character to be used in a field name. * Original field length defined for this attribute was incorrect and has been amended accordingly
N90 | Metering_Set_Reference | Removal of this field. | This field has been removed from the M00 record in the MDR file and the M03 record in the MBR file. This field has been removed from this record for consistency.
Q44 | iGT_Transportation_Rate | * Amend field name to iGT_Transportation_Charge_Rate * Notation error - Amend length to 12 to be consistent with UK Link Standards (length should include decimal characters) | * Consistency with iGT Input File Name and UK Link Naming Conventions * Consistency with UK Link Standards
Q44 | iGT_Transportation_Rate_Type | Amend field name to iGT_Transportation_Charge_Rate_Type | * Consistency with iGT Input File Name and UK Link Naming Conventions
Q44 | iGT_Transportation_Rate_Effective_Date | Amend field name to iGT_Transportation_Charge_Rate_Effective_Date | * Consistency with iGT Input File Name and UK Link Naming Conventions
Q44 | iGT_Metering_Rate | * Amend field name to iGT_Metering_Charge_Rate * Notation error - Amend length to 12 to be consistent with UK Link Standards (length should include decimal characters) | * Consistency with iGT Input File Name and UK Link Naming Conventions * Consistency with UK Link Standards
Q44 | iGT_Metering_Rate_Effective_Date | Amend field name to iGT_Metering_Charge_Rate_Effective_Date | * Consistency with iGT Input File Name and UK Link Naming Conventions
Q44 | iGT_Infill_Rate | * Amend field name to iGT_Infill_Charge_Rate * Notation error - Amend length to 12 to be consistent with UK Link Standards (length should include decimal characters) | * Consistency with iGT Input File Name and UK Link Naming Conventions * Consistency with UK Link Standards
Q44 | iGT_Infill_Rate_Effective_Date | Amend field name to iGT_Infill_Charge_Rate_Effective_Date | * Consistency with iGT Input File Name and UK Link Naming Conventions
S07 | NO_OF_DRE | Field has been removed from the record. | With the implementation of Mod 428 and the introduction of Single Supply Point there is no longer a concept of an aggregated supply point.
S10 | NO_OF_DRE | Field has been removed from the record. | With the implementation of Mod 428 and the introduction of Single Supply Point there is no longer a concept of an aggregated supply point.
S04 | METER_READ_BATCH_FREQUENCY | Removal of this field. | Remove the Batch Cancellation function from the process as the change will be immediate and therefore cannot be cancelled.
S35 | METER_READ_BATCH_FREQUENCY | Removal of this field. | Remove the Batch Cancellation function from the process as the change will be immediate and therefore cannot be cancelled.
S59 | SUPPLY_METER_POINT_CLASS | Field optionality needs to be changed to Optional | In the scenario of Greenfield sites Xoserve will not hold the Supply Meter Point Class hence the change in the field optionality from Mandatory to Optional.
S59 | NO_OF_DRE | Field has been removed from the record. | With the implementation of Mod 428 and the introduction of Single Supply Point there is no longer a concept of an aggregated supply point.
S59 | WITHDRAWAL_STATUS | Field to be added into the record.to reflect S59 | Withdrawal status is included in the Nom Enquiry Response record (S59) and to meet the Nexus Business Requirement. This field must also be included in the Nom Response record (S64).
S64 | WITHDRAWAL_STATUS | Field to be added into the record.to reflect S59 | Withdrawal status is included in the Nom Enquiry Response record (S59) and to meet the Nexus Business Requirement. This field must also be included in the Nom Response record (S64).
S75 | PREVIOUS_SUPPLIER_SHORT_CODE | Field length to be reduced from 12 to 3 | File Name has been changed from Abbreviated name to Short Code and for consistency the filed length has been reduced in line with all other records where Supplier Short Code is referenced,
T07 | REGISTERED_SHIPPER_SHORT_CODE | Change Field Name and description to reflect change to SHIPPER_SHORT_CODE | Field name changed to be consistent with other field names.
T50 | WC_CORRECTION | New Data Item included | A new correction process has been implemented, therefore the files need to be amended to reflect the changes. The record needs to highlight that the winter consumption has been changed as part of the correction process.
T50 | BACKSTOP_DATE | New Data Item included | Files need to be amended to incorporate the backstop date for the consumption as new correction process will generate this. The record needs to highlight the back stop date that has been created.
T50 | EUC_EFFECTIVE_DATE | New Data Item included | Included description: Date from when the new EUC mentioned in the file is effective.
T50 | EUC_CHANGE_REASON_CODE | New Data Item included | Included Description: The reason for change in EUC, denoted as a 2 character code. Following are the allowable values and it’s definitions; Allowable values: 04 Definition: 04 - WC correction
U06 | Metering_Set_Reference | Removal of this field. | This field has been removed from the M00 record in the MDR file and the M03 record in the MBR file. This filed has been removed from this record for consistency.
S15 | NO_OF_DRE | Field has been removed from the record. | With the implementation of Mod 428 and the introduction of Single Supply Point there is no longer a concept of an aggregated supply point.

## Consolidated List
File Formats Submitted to SE
Count | Records | Files | Hierarchies | Phase | External User | Status | Location
1 |  | ASP |  | Phase 3 | Shipper | Approved | Zip8 File Formats
2 |  | EOI |  | Phase 2 | Shipper | Approved | Zip8 File Formats
3 |  | IIS |  | Phase 2 | Shipper | Approved | Zip8 File Formats
4 |  | MIF |  | Phase 2 | Shipper | Approved | Zip8 File Formats
5 |  | NSC |  | Phase 2 | Shipper | Approved | Zip8 File Formats
6 |  | OSG |  | Phase 2 | Shipper | Approved | Zip8 File Formats
7 |  | PNS |  | Phase 3 | Shipper | Approved | Zip8 File Formats
8 |  | TDS |  | Phase 2 | Shipper | Approved | Zip8 File Formats
9 |  | UPI |  | Phase 2 | Shipper | Approved | Zip8 File Formats
10 |  | ZCS |  | Phase 2 | Shipper | Approved | Zip8 File Formats
11 |  |  | AES | Phase 2 | Shipper | Approved | Zip9 Hierarchies
12 |  |  | AML | Phase 3 | Shipper | Approved | Zip9 Hierarchies
13 |  |  | AQI | Phase 1 | Shipper | Approved | Zip9 Hierarchies
14 |  |  | AQR | Phase 1 | Shipper | Approved | Zip9 Hierarchies
15 |  |  | ASP | Phase 3 | Shipper | Approved | Zip9 Hierarchies
16 |  |  | CFR | Phase 3 | Shipper | Approved | Zip9 Hierarchies
17 |  |  | CNC | Phase 1 | Shipper | Approved | Zip9 Hierarchies
18 |  |  | CNF | Phase 3 | Shipper | Approved | Zip9 Hierarchies
19 |  |  | CNR | Phase 1 | Shipper | Approved | Zip9 Hierarchies
20 |  |  | COI | Phase 2 | Shipper | Approved | Zip9 Hierarchies
21 |  |  | COM | Phase 2 | Shipper | Approved | Zip9 Hierarchies
22 |  |  | CRF | Phase 3 | Shipper | Approved | Zip9 Hierarchies
23 |  |  | CZI | Phase 2 | Shipper | Approved | Zip9 Hierarchies
24 |  |  | DES | Phase 2 | Shipper | Approved | Zip9 Hierarchies
25 |  |  | DNE | Phase 3 | Shipper | Approved | Zip9 Hierarchies
26 |  |  | DNR | Phase 3 | Shipper | Approved | Zip9 Hierarchies
27 |  |  | EOI |  | Shipper | Approved | Zip9 Hierarchies
28 |  |  | FSI | Phase 2 | Shipper | Approved | Zip9 Hierarchies
29 |  |  | IIS | Phase 2 | Shipper | Approved | Zip9 Hierarchies
30 |  |  | LIA | Phase 2 | Shipper | Approved | Zip9 Hierarchies
31 |  |  | MIF | Phase 2 | Shipper | Approved | Zip9 Hierarchies
32 |  |  | MIN | Phase 3 | Shipper | Approved | Zip9 Hierarchies
33 |  |  | NMR | Phase 2 | Shipper | Approved | Zip10 Hierarchies
34 |  |  | NMS | Phase 1 | Shipper | Approved | Zip10 Hierarchies
35 |  |  | NOM | Phase 2 | Shipper | Approved | Zip10 Hierarchies
36 |  |  | NRF | Phase 2 | Shipper | Approved | Zip10 Hierarchies
37 |  |  | NRL | Phase 3 | Shipper | Approved | Zip10 Hierarchies
38 |  |  | NSC | Phase 2 | Shipper | Approved | Zip10 Hierarchies
39 |  |  | OSG | Phase 2 | Shipper | Approved | Zip10 Hierarchies
40 |  |  | PNS | Phase 3 | Shipper | Approved | Zip10 Hierarchies
41 |  |  | RTO | Phase 3 | Shipper | Approved | Zip10 Hierarchies
42 |  |  | RTR | Phase 3 | Shipper | Approved | Zip10 Hierarchies
43 |  |  | SCR | Phase 3 | Shipper | Approved | Zip10 Hierarchies
44 |  |  | SFN | Phase 1 | Shipper | Approved | Zip10 Hierarchies
45 |  |  | SFR | Phase 1 | Shipper | Approved | Zip10 Hierarchies
46 |  |  | SPC | Phase 1 | Shipper | Approved | Zip10 Hierarchies
47 |  |  | STN | Phase 3 | Shipper | Approved | Zip10 Hierarchies
48 |  |  | SWN | Phase 1 | Shipper | Approved | Zip10 Hierarchies
49 |  |  | TDS | Phase 2 | Shipper | Approved | Zip10 Hierarchies
50 |  |  | TRF | Phase 3 | Shipper | Approved | Zip10 Hierarchies
51 |  |  | UBR | Phase 1 | Shipper | Approved | Zip10 Hierarchies
52 |  |  | UDR | Phase 1 | Shipper | Approved | Zip10 Hierarchies
53 |  |  | UPI | Phase 2 | Shipper | Approved | Zip10 Hierarchies
54 |  |  | ZCS | Phase 2 | Shipper | Approved | Zip10 Hierarchies
55 | ONJOB |  |  | Phase 1 | Shipper | Approved | Zip1_Records
56 | C37 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
57 | C38 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
58 | C39 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
59 | C41 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
60 | C42 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
61 | C43 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
62 | C45 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
63 | C50 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
64 | C70 |  |  | Phase 2 | Shipper | Approved | Zip1_Records
65 | C71 |  |  | Phase 2 | Shipper | Approved | Zip1_Records
66 | C73 |  |  | Phase 3 | Shipper | Approved | Zip1_Records
67 | E87 |  |  | Phase 3 | Shipper | Approved | Zip1_Records
68 | E89 |  |  | Phase 3 | Shipper | Approved | Zip1_Records
69 | E90 |  |  | Phase 3 | Shipper | Approved | Zip1_Records
70 | E91 |  |  | Phase 3 | Shipper | Approved | Zip1_Records
71 | E92 |  |  | Phase 3 | Shipper | Approved | Zip1_Records
72 | G40 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
73 | I68 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
74 | K08 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
75 | K09 |  |  | Phase 1 | Shipper | Approved | Zip1_Records
76 | K12 |  |  | Phase 2 | Shipper | Approved | Zip1_Records
77 | K13 |  |  | Phase 3 | Shipper | Approved | Zip1_Records
78 | K14 |  |  | Phase 2 | Shipper | Approved | Zip2_Records
79 | K15 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
80 | K85 |  |  | Phase 2 | Shipper | Approved | Zip2_Records
81 | M12 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
82 | M15 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
83 | M79 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
84 | M80 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
85 | M81 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
86 | M82 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
87 | M83 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
88 | M84 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
89 | M93 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
90 | M96 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
91 | N11 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
92 | N44 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
93 | N45 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
94 | N93 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
95 | N94 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
96 | N95 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
97 | N99 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
98 | O15 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
99 | O17 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
100 | O20 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
101 | O22 |  |  | Phase 1 | Shipper | Approved | Zip2_Records
102 | O52 |  |  | Phase 3 | Shipper | Approved | Zip3_Records
103 | P17 |  |  | Phase 1 | Shipper | Approved | Zip3_Records
104 | Q01 |  |  | Phase 1 | Shipper | Approved | Zip3_Records
105 | Q02 |  |  | Phase 1 | Shipper | Approved | Zip3_Records
106 | Q23 |  |  | Phase 1 | Shipper | Approved | Zip3_Records
107 | Q45 |  |  | Phase 3 | Shipper | Approved | Zip3_Records
108 | Q46 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
109 | Q51 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
110 | S09 |  |  | Phase 3 | Shipper | Approved | Zip3_Records
111 | S11 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
112 | S12 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
113 | S13 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
114 | S14 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
115 | S24 |  |  | Phase 1 | Shipper | Approved | Zip3_Records
116 | S26 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
117 | S31 |  |  | Phase 1 | Shipper | Approved | Zip3_Records
118 | S36 |  |  | Phase 1 | Shipper | Approved | Zip3_Records
119 | S37 |  |  | Phase 1 | Shipper | Approved | Zip3_Records
120 | S39 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
121 | S40 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
122 | S47 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
123 | S51 |  |  | Phase 1 | Shipper | Approved | Zip3_Records
124 | S54 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
125 | S63 |  |  | Phase 3 | Shipper | Approved | Zip3_Records
126 | S69 |  |  | Phase 2 | Shipper | Approved | Zip3_Records
127 | S74 |  |  | Phase 2 | Shipper | Approved | Zip4_Records
128 | S81 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
129 | S82 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
130 | S85 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
131 | S86 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
132 | S88 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
133 | S93 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
134 | S94 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
135 | S96 |  |  | Phase 2 | Shipper | Approved | Zip4_Records
136 | S98 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
137 | T05 |  |  | Phase 3 | Shipper | Approved | Zip4_Records
138 | T06 |  |  | Phase 3 | Shipper | Approved | Zip4_Records
139 | T08 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
140 | U01 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
141 | U02 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
142 | U03 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
143 | U04 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
144 | U10 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
145 | U12 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
146 | U13 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
147 | U14 |  |  | Phase 1 | Shipper | Approved | Zip4_Records
148 | U75 |  |  | Phase 2 | Shipper | Approved | Zip4_Records
149 | S03 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
150 | S05 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
151 | S06 |  |  | Phase 1 | Shipper | Approved | Zip5_Records
152 | S16 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
153 | S21 |  |  | Phase 2 | Shipper | Approved | Zip5_Records
154 | S30 |  |  | Phase 2 | Shipper | Approved | Zip5_Records
155 | S34 |  |  | Phase 1 | Shipper | Approved | Zip5_Records
156 | S42 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
157 | S48 |  |  | Phase 2 | Shipper | Approved | Zip5_Records
158 | S66 |  |  | Phase 1 | Shipper | Approved | Zip5_Records
159 | S68 |  |  | Phase 2 | Shipper | Approved | Zip5_Records
160 | S73 |  |  | Phase 2 | Shipper | Approved | Zip5_Records
161 | S76 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
162 | S77 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
163 | S90 |  |  | Phase 1 | Shipper | Approved | Zip5_Records
164 | S91 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
165 | S97 |  |  | Phase 2 | Shipper | Approved | Zip5_Records
166 | T04 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
167 | T51 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
168 | T73 |  |  | Phase 1 | Shipper | Approved | Zip5_Records
169 | T74 |  |  | Phase 1 | Shipper | Approved | Zip5_Records
170 | T97 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
171 | T98 |  |  | Phase 3 | Shipper | Approved | Zip5_Records
172 | U70 |  |  | Phase 2 | Shipper | Approved | Zip5_Records
173 | U71 |  |  | Phase 2 | Shipper | Approved | Zip6_Records
174 | U74 |  |  | Phase 2 | Shipper | Approved | Zip6_Records
175 | U80 |  |  | Phase 3 | Shipper | Approved | Zip6_Records
176 | U81 |  |  | Phase 3 | Shipper | Approved | Zip6_Records
177 | U82 |  |  | Phase 3 | Shipper | Approved | Zip6_Records
178 | U83 |  |  | Phase 3 | Shipper | Approved | Zip6_Records
179 | ONUPD |  |  | Phase 1 | Shipper | Approved | Zip6_Records
180 | X10 |  |  | Phase 3 | Shipper | Approved | Zip6_Records
181 | X98 |  |  | Phase 3 | Shipper | Approved | Zip6_Records
182 | X99 |  |  | Phase 3 | Shipper | Approved | Zip6_Records
183 | Q03 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
184 | Q04 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
185 | Q05 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
186 | Q06 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
187 | S08 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
188 | S67 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
189 | S70 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
190 | S84 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
191 | S89 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
192 | M00 |  |  | Phase 1 | Shipper | Approved | Zip6_Records
193 | M03 |  |  | Phase 2 | Shipper | Approved | Zip6_Records
194 | S41 |  |  | Phase 2 | Shipper | Approved | Zip6_Records
195 | S65 |  |  | Phase 2 | Shipper | Approved | Zip6_Records
196 | S78 |  |  | Phase 2 | Shipper | Approved | Zip7_Records
197 | S38 |  |  | Phase 3 | Shipper | Approved | Zip7_Records
198 | U76 |  |  | Phase 3 | Shipper | Approved | Zip7_Records
199 | T67 |  |  | Phase 1 | Shipper | Approved | Zip7_Records
200 | U72 |  |  | Phase 2 | Shipper | Approved | Zip7_Records
201 | U73 |  |  | Phase 2 | Shipper | Approved | Zip7_Records
202 | COI |  |  | Phase 2 | Shipper | Approved | Zip 11 Records
203 | COM |  |  | Phase 2 | Shipper | Approved | Zip 11 Records
204 | CZI |  |  | Phase 2 | Shipper | Approved | Zip 11 Records
205 | FSI |  |  | Phase 2 | Shipper | Approved | Zip 11 Records
206 |  |  | INV | Phase 2 | Shipper | Approved | Zip 11 Records
207 | LIA |  |  | Phase 2 | Shipper | Approved | Zip 11 Records
208 |  | E88 |  | Phase 3 | Shipper | Approved | Zip 11 Records
209 |  | Q44 |  | Phase 1 | Shipper | Approved | Zip 11 Records
210 |  | S04 |  | Phase 1 | Shipper | Approved | Zip 11 Records
211 |  | S07 |  | Phase 3 | Shipper | Approved | Zip 11 Records
212 |  | S10 |  | Phase 3 | Shipper | Approved | Zip 11 Records
213 |  | S15 |  | Phase 3 | Shipper | Approved | Zip 11 Records
214 |  | S35 |  | Phase 1 | Shipper | Approved | Zip 11 Records
215 |  | S75 |  | Phase 2 | Shipper | Approved | Zip 11 Records
216 |  | T07 |  | Phase 3 | Shipper | Approved | Zip 11 Records
217 |  | T50 |  | Phase 3 | Shipper | Approved | Zip 11 Records
218 |  | XO9 |  | Phase 3 | Shipper | Approved | Zip 11 Records