## Cover
Shipperless / Unregistered Sites
1.25M ACs
750K
3M
3M
3M
3M
3M
y.0M
y.0M + Tail = 2.7M

## Shipperless Graphs
Shipper activity unregistered sites
General Comments (Suzanne Powell and Julia Sherwen) (SP) We received 4,215 invoices this week and sent 3,956. The remaining 259 were not sent due to the PP fault. The main bulk of issues remain in the workflow and exception categories. We currently have 11,235 accounts within work management that are faulted. 11, 012 are mis-directed Technical errors (Idoc). The working group have now prioritised over 80% of the faults for release (Rj312.2) and the other 20% will be actioned in tomorrow's workshop. (JS) This week we have included data (CLO 13 & 14) from Meter to Cash analysis showing invoicing performance relating to two specific dates. This will be developed in coming weeks.
Comments (Gillian Taylor) The reconciliation levels have remained constant week on week (now at 79%). The rate of raising issues on financial reconciliation has slowed, but the rate of resolution of outstanding HPOVs has also been slow. The focus this week in Finance will be to test the new functionality and fixes which were implemented for Finance as part of RJ312. There is a weekly teleconference on unbilled revenue to track issues. Key outstanding issues relate to the volume of exceptions where unbilled is unable to produce an estimate; the run times of unbilled revenue; the processing of multiple gas meter reads on the same day, and the development of an exclusion / substitution process.
Comments - Acquisitions Acquisitions slowly continue to creep up. There are a number of faults/issues surrounding Acquisitions and these are being actioned by the top 20. We expect to see an increase within Acquisitions next week due to the 5,985 new sales going through on Monday as a result of RJ312. The working group are continuing to meet daily and assess the impacts.
Comments - Withdrawals Volume outstanding again has slightly increased due to the "Discuss Objection"(243) and "Objection Received" items, Further investigations are being carried out, but the exceptions have been closed within Siebel but are showing as open in SAP. There is no customer impact.
Comments - Home Move Slight increase from 92 to 102 (109) exceptions this week. 51 of the 102are WIP and 27are faults due to cancel re-bill (909515 due in RJ312.2), 24 in progress and were cleared Monday.
Overview (xoserve) Shipper Activity unregistered sites increased by 12% when compared to the previous month. However Shipper responses to the report continue to increase.
1.25M ACs
750K
3M
3M
3M
3M
3M
y.0M
y.0M + Tail = 2.7M

## USNANA Graphs
Unregistered Sites No Activity No Assets
Overview (xoserve) 5,000 MPRNs resolved during February which is 1,000 more than the monthly benchmark amount and moves towards meeting the target figure. End user letter 2's commenced in line with the plan on the 1st February. No change in original Site visit figures as these won't increase until 30 days after the second end user letter during March.

## Shipperless Data
Shipper Activity Data | 2007 |  | 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
No response from Shipper | 2007 Nov: 10546; 2007 Dec: 8269; 2008 Jan: 5601; 2008 Feb: 5408; 2008 Mar: 5444
Orphaned | 2007 Nov: 1514; 2007 Dec: 2053; 2008 Jan: 2083; 2008 Feb: 2011; 2008 Mar: 1946
Shipper intends to confirm | 2007 Nov: 1253; 2007 Dec: 1193; 2008 Jan: 1089; 2008 Feb: 896; 2008 Mar: 850
Total Shipper Activity MPRN's Including Orphaned | 2007 Nov: 13313; 2007 Dec: 11515; 2008 Jan: 8773; 2008 Feb: 8315; 2008 Mar: 8240
Target Level | 7000 | 6250 | 5500 | 4750 | 4000 | 4500 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
Cumulative - Shipper Activity Unregistered Sites Shipper Response | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
No response from Shipper | 10546 | 8269 | 5601 | 5408 | 5444 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Orphaned | 1514 | 2053 | 2083 | 2011 | 1946 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipper intends to confirm | 1253 | 1193 | 1089 | 896 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target | 6500 | 6000 | 5500 | 5000 | 4500 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
Total | 13313 | 11515 | 8773 | 8315 | 8240 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check Cell - Shipper Intent | bar: 2007 Nov to 2008 Oct
Cumulative - Shipper activity unregistered sites Age Analysis | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1 to 6 months old | 2007 Nov: 6610; 2007 Dec: 5241; 2008 Jan: 2758; 2008 Feb: 2501; 2008 Mar: 2171
7 to 12 months old | 2007 Nov: 3026; 2007 Dec: 2113; 2008 Jan: 1743; 2008 Feb: 1671; 2008 Mar: 1840
Over 12 months old | 2007 Nov: 1099; 2007 Dec: 1056; 2008 Jan: 1128; 2008 Feb: 1104; 2008 Mar: 1220
Over 24 months old | 2007 Nov: 1064; 2007 Dec: 1052; 2008 Jan: 1061; 2008 Feb: 1028; 2008 Mar: 1063
Total | 11799 | 9462 | 6690 | 6304 | 6294 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check Cell | bar: 2007 Nov to 2008 Oct
Cumulative - Unregistered 'Yes' responses age analysis | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1 to 6 months old | 2007 Nov: 3; 2007 Dec: 9; 2008 Jan: 37; 2008 Feb: 28; 2008 Mar: 16
7 to 12 months old | 2007 Nov: 546; 2007 Dec: 490; 2008 Jan: 281; 2008 Feb: 159; 2008 Mar: 28
Over 12 months old | 2007 Nov: 535; 2007 Dec: 525; 2008 Jan: 701; 2008 Feb: 539; 2008 Mar: 631
Over 24 months old | 2007 Nov: 169; 2007 Dec: 169; 2008 Jan: 70; 2008 Feb: 170; 2008 Mar: 175
Total | 1253 | 1193 | 1089 | 896 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check Cell | bar: 2007 Nov to 2008 Oct
Cumulative Orphaned End User Age Analysis | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1 to 6 months old | 2007 Nov: 0; 2007 Dec: 348; 2008 Jan: 179; 2008 Feb: 31; 2008 Mar: 9
7 to 12 months old | 2007 Nov: 76; 2007 Dec: 278; 2008 Jan: 404; 2008 Feb: 463; 2008 Mar: 420
Over 12 months old | 2007 Nov: 539; 2007 Dec: 545; 2008 Jan: 531; 2008 Feb: 498; 2008 Mar: 440
Over 24 months old | 2007 Nov: 899; 2007 Dec: 891; 2008 Jan: 969; 2008 Feb: 1019; 2008 Mar: 1077
Total | 1514 | 2062 | 2083 | 2011 | 1946 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check Cell | bar: 2007 Nov to 2008 Oct

## USNANA Data
Unregistered Data
USNANA Age Analysis | Pre 1996 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | Total
Original age analysis | 79 | 1790 | 835 | 1793 | 2269 | 4380 | 3635 | 15957 | 23439 | 11831 | 9328 | 15950 | 22838 | 114124
Current age analysis | 0 | 0 | 17 | 147 | 606 | 1771 | 1683 | 6283 | 19496 | 9466 | 7464 | 9733 | 11067 | 67733
Resolved to date | 79 | 1790 | 818 | 1646 | 1663 | 2609 | 1952 | 9674 | 3943 | 2365 | 1864 | 6217 | 11771 | 46391
Cumulative - USNANA Overall status | Pre 1996: 2007; 1997: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Outstanding target | 49470 | 42470 | 37470 | 33470 | 29470 | 24220 | 18970 | 13720 | 8470 | 4220 | 1150 | 0
Outstanding | 2007 Nov: 49470; 2007 Dec: 48105; 2008 Jan: 44361; 2008 Feb: 37967; 2008 Mar: 32543
Variance from target | 2007 Nov: 0; 2007 Dec: 5635; 2008 Jan: 6891; 2008 Feb: 4497; 2008 Mar: 3073
Under investigation | 2007 Nov: 52826; 2007 Dec: 33017; 2008 Jan: 33448; 2008 Feb: 34626; 2008 Mar: 35190
Cleared | 2007 Nov: 11828; 2007 Dec: 33002; 2008 Jan: 36315; 2008 Feb: 41531; 2008 Mar: 46391
Check Cell - Total Project Amount | 0 | 0 | 0 | 0 | 0 | -114124 | -114124 | -114124 | -114124 | -114124 | -114124 | -114124
Check cell - Cleared Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative - Desktop actions | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Total Registered | 2008 Feb: 12803; 2008 Mar: 14558
Total Set to Extinct (EX) | 2008 Feb: 24287; 2008 Mar: 27532
Total Legitimately Unregistered | 2008 Feb: 2384; 2008 Mar: 2338
Desktop Registered | 2007 Nov: 5397; 2007 Dec: 7164; 2008 Jan: 10894; 2008 Feb: 12655; 2008 Mar: 14401
Desktop Set to EX | 2007 Nov: 541; 2007 Dec: 19138; 2008 Jan: 20833; 2008 Feb: 23731; 2008 Mar: 26788
Desktop Legitimately Unregistered | 2007 Nov: 2725; 2007 Dec: 2591; 2008 Jan: 2449; 2008 Feb: 2309; 2008 Mar: 2263
Desktop Moved to Shipper Activity Pot | 2007 Nov: 3165; 2007 Dec: 4109; 2008 Jan: 2139; 2008 Feb: 2057; 2008 Mar: 1963
Desktop End user | 2007 Dec: 1369; 2008 Jan: 2377; 2008 Feb: 5034; 2008 Mar: 7372
Total | 11828 | 34371 | 38692 | 45786 | 43452 | 0 | 0 | 0 | 0 | 0 | 0 | 0
End User Actions | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Letter pending | 2007 Nov: 0; 2007 Dec: 36; 2008 Jan: 45; 2008 Feb: 181; 2008 Mar: 1724
Letter 1 Sent | 2007 Nov: 0; 2007 Dec: 1005; 2008 Jan: 1721; 2008 Feb: 2578; 2008 Mar: 2209
Letter 2 Sent | 2007 Nov: 0; 2007 Dec: 0; 2008 Jan: 0; 2008 Feb: 588; 2008 Mar: 1219
Site Visit | 2007 Nov: 0; 2007 Dec: 0; 2008 Jan: 0; 2008 Feb: 0; 2008 Mar: 0
Query | 2007 Nov: 0; 2007 Dec: 43; 2008 Jan: 39; 2008 Feb: 179; 2008 Mar: 279
PSA | 2007 Nov: 0; 2007 Dec: 132; 2008 Jan: 160; 2008 Feb: 215; 2008 Mar: 252
No Gas | 2007 Nov: 0; 2007 Dec: 101; 2008 Jan: 171; 2008 Feb: 553; 2008 Mar: 712
Vacant | 2007 Nov: 0; 2007 Dec: 47; 2008 Jan: 67; 2008 Feb: 111; 2008 Mar: 151
To be set to extinct | 2007 Nov: 0; 2007 Dec: 4; 2008 Jan: 144; 2008 Feb: 487; 2008 Mar: 675
Registered | 2007 Nov: 0; 2007 Dec: 1; 2008 Jan: 30; 2008 Feb: 142; 2008 Mar: 151
Total | 0 | 1369 | 2377 | 5034 | 7372 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check cell - end user totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Site visits | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Sent | 2007 Nov: 350; 2007 Dec: 494; 2008 Jan: 494; 2008 Feb: 494; 2008 Mar: 494
Undertaken | 2007 Nov: 150; 2007 Dec: 163; 2008 Jan: 163; 2008 Feb: 163; 2008 Mar: 163
Resolved | 2007 Nov: 0; 2007 Dec: 150; 2008 Jan: 150; 2008 Feb: 150; 2008 Mar: 150
Response outstanding | 200 | 331 | 331 | 331 | 331 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check cell - site visit total | 350 | 494 | 494 | 494 | 494 | 0 | 0 | 0 | 0 | 0 | 0 | 0
National Grid Plc | 2007 Dec: 220; 2008 Jan: 220; 2008 Feb: 220; 2008 Mar: 220
Northern Gas Networks Ltd | 2007 Dec: 31; 2008 Jan: 31; 2008 Feb: 31; 2008 Mar: 31
Scotland Gas Networks Ltd | 2007 Dec: 39; 2008 Jan: 39; 2008 Feb: 39; 2008 Mar: 39
Southern Gas Networks Ltd | 2007 Dec: 13; 2008 Jan: 13; 2008 Feb: 13; 2008 Mar: 13
Wales & the West Utilities | 2007 Dec: 28; 2008 Jan: 28; 2008 Feb: 28; 2008 Mar: 28
Check cell outstanding split | -200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Site Visit Resolution breakdown | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Registered | 2007 Dec: 6; 2008 Jan: 6; 2008 Feb: 6; 2008 Mar: 6
Set to EX | 2007 Dec: 69; 2008 Jan: 69; 2008 Feb: 69; 2008 Mar: 69
Legitimately Unregistered | 2007 Dec: 75; 2008 Jan: 75; 2008 Feb: 75; 2008 Mar: 75
Eu has contract with supplier | bar: 2007 Dec to 2008 Mar
Live supply and burning Gas | 2007 Dec: 8; 2008 Jan: 8; 2008 Feb: 8; 2008 Mar: 8
No Access | 2007 Dec: 4; 2008 Jan: 4; 2008 Feb: 4; 2008 Mar: 4
Total | 0 | 163 | 163 | 163 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A25: Adam Turbitt (AT097): Run Full Breakdown Report off EUDB. Will be sum of all values under USNANA heading.
Note on A30: Adam Turbitt (AT097): Blank cells, Letter 1 Printed
Note on A31: Adam Turbitt (AT097): Letter 1 Sent, Letter 2 Printed
Note on A32: Adam Turbitt (AT097): Letter 2 Sent
Note on A35: Adam Turbitt (AT097): PSA
Note on A33: Adam Turbitt (AT097): Site Visit
Note on A36: Adam Turbitt (AT097): No Gas
Note on A34: Adam Turbitt (AT097): Address, Query
Note on A37: Adam Turbitt (AT097): Vacant
Note on A39: Adam Turbitt (AT097): Conf
Note on A38: Adam Turbitt (AT097): DN Link