## Slide 1: 4361 UK Link Future Release 2
Release 2 Scope Business Benefit Review

## Slide 2: R2 Business Case - Scope Financial Assessment
Release 2 proposed scope was agreed by the ChMC on 11/10/17.
Since ChMC, Xoserve has received supplier costs for design and delivery
We’ve consequently undertaken a Value For Money review with our suppliers
We’ve also conducted a challenge and review of business benefits to understand the cost/benefit for each CR to determine business case viability before proceeding.
This review has identified the following:
  Assessment has identified that whilst the change cost is considered reasonable, low workaround efforts/costs for CDSP to operate result in a non-viable business case
  A large proportion of this is due to manual workarounds not being as onerous as first predicted
  Throughout the cost/benefit analysis, risk of continuing to operate manual processes has been reviewed and only those with an acceptable profile have been recommended to be descoped
Internal/External | Case For Change | No Case For Change
Internal - UK Link Deferred Change Budget | 5 | 7
External - Market DSC Change Budget | 9 | 1

## Slide 3
R2 Business Scope – Approval Scope
As a result of the business benefit review, Xoserve are recommending that 14 CRs should continue within the project delivery scope of R2.
Xoserve are reviewing whether a secondary scope could be included to utilise R2 capacity that does not pose risk to delivery. This is underway and we will return to DSC (potentially an extraordinary session) to provide a view and seek authorisation.
Xoserve require two decisions from ChMC:
Decision 1 – Confirm the scope of R2
  Continue with agreed scope for all 22 CRs – not recommended
  Reduced scope to only include the 14 CRs with a viable business case and consider if additional scope can be added – recommended
  Reduced scope to only include the 14 CRs with a viable business case – not recommended
  Do not start design and conduct analysis on additional scope to be included before commencing R2 delivery - not recommended
Decision 2 – Approve/Reject the EQR for R2 Detailed Design to commence the R2 Project (based on recommended option B above)

## Slide 4
If you have any immediate questions on this, please write to the Retail & Network Platform Project Team at
box.xoserve.uklinkfuturerelease@xoserve.com
Contacts - (Lee Chambers (lee.chambers@xoserve.com) or Christina Francis (christina.francis@xoserve.com)
or contact your relevant Customer Account Manager.
Contact Us

## Slide 5: Appendix

## Slide 6
Appendix A - Proposed Release 2 Scope
CR Ref | Change Title | Budget | Business Benefit Review (VFM)
UKLP112 | Missing Key Data Items from iGTs to Shippers (Plot Number) | Market DSC Change Budget | Yes
UKLP122 | PAF Indicator field inclusion on VAD and ACR files | UK Link Deferred Change Budget | No
UKLP140 | .DUP & .DUS file type registration in AMT | UK Link Deferred Change Budget | No
UKLP147 | DDS/DDU file amendment | Market DSC Change Budget | Yes
UKLP194 | Billing History by all NTS capacity / commodity related charges (from Nexus implementation onwards) | Market DSC Change Budget | Yes
UKLP197 | Addition of New fields from CMS being available in BW/IP reporting environment | UK Link Deferred Change Budget | No
UKLP222 | Theft Risk Assessment Service Tip-off Hotline Data Provision – Enduring Solution | Market DSC Change Budget | Yes
UKLP223 | Allow for a capacity revision on a Seasonally Large Supply Point | UK Link Deferred Change Budget | No
UKLP226 | Provide the DMSP with the AQ in the O13 record on the GCC file | Market DSC Change Budget | No
UKLP251 | Reports required under UNC TPD V16.1 in Nexus (reports required by MOD 520A) | Market DSC Change Budget | Yes
UKLP256 | NDM Twin Stream Read Validation | UK Link Deferred Change Budget | No

## Slide 7
Appendix A - Proposed Release 2 Scope
CR Ref | Change Title | Budget | Business Benefit Review (VFM)
UKLP267 | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field & remove as allowable value from AMT & ISU. | UK Link Deferred Change Budget | Yes
UKLP270 | Amend referral rules for class 2 smaller LSP’s | UK Link Deferred Change Budget | Yes
UKP273 | Vulnerable Customer Data Requirements (Special Need Codes) | Market DSC Change Budget | Yes
UKLP287 | Back billing for domestic (SSP) sites needs to be reflect the correct adjustment start date | UK Link Deferred Change Budget | Yes
UKLP292 | Changes to the upper parameter of the XDO partial refresh file | UK Link Deferred Change Budget | Yes
UKLP300 | Unique Sites – Adding profiles | UK Link Deferred Change Budget | No
XRN4248 | Quarterly smart Metering reporting for HSE and DNs | Market DSC Change Budget | Yes
UKLP315 | Meter Point Details Report & Sector Breakdown Report | UK Link Deferred Change Budget | Yes
COR3386 | New DN role for CMS | Market DSC Change Budget | Yes
UKLP325 | Annual shrinkage submission (.ORD ) | UK Link Deferred Change Budget | No
COR3283 | Recording of DN Siteworks / New Network Connection Ref No in central systems | Market DSC Change Budget | Yes