## Propose to Close
Propose to Close Change requests
Ref | UKLP | Title | Date raised | Originator | Change Description | Rejection Proposal
3661 | 65 | Correction Factor Application | 2015-01-13 | Emma Smith | This will ensure the appropriate Correction Factor is being applied and thus consumption can be calculated. | This has been discussed at SDG, it was felt the existing process to amend is right and should not be changed therefore recommended for closure.
4430 | 198 | Ability to submit a read taken at meter inspection with meter inspection update | 2016-04-29 | Dean Johnson | There was a requirement to include the submission of the read along with the inspection date following a meter inspection. | This was discussed at SDG, during prioritisation, and agreed that this CR would not be required due to complexities of providing read data on a file other than the read file.
4439 | 244 | GDE Cashout – Daily Curtailment Volume (DCV) for Daily Metered sites | 2016-08-04 | Lorraine Cave | The changes include introduction of obligations on Distribution Networks (DNs) to supply specific information to NG Transmission in the event of a Gas Deficit emergency (GDE). As part of COR3745 ‘GDE Cashout DN Obligations’ the work on Daily Curtailment Volumes (DCV) for Daily Metered (DM) sites was postponed until after Project Nexus Implementation as the cost / benefit to implement a rarely used solution in a soon to be legacy system wasn’t justifiable. | Xoserve comfortable with the manual workaround we have in place as Xoserve will be unlikely to ever have to put this workaround into place, and therefore do not believe business benefit of an automated solution would ever be realised.
4455 | 284v2 | Ability to reduce Capacity on DM Meter points outside on CRP (as per UNC G5.2) | 2017-01-04 | Linda Whitcroft | Where the existing Registered User has acted inappropriately and has not managed the Supply Point Capacity requirements and therefore the Prevailing Supply Point Capacity is substantially higher than necessary, a Proposing User should Nominate at the current BSSOQ but before confirming an Offer at this capacity, they must notify the Transporter, in which case the Transporter may allow a Supply Point Capacity reduction down (to the BSSOQ) outside the Capacity Reduction Period. | there is a manual workaround in place at present and is sustainable, this is a very rare scenario and therefore is highly doubtful that the cost of change would be beneficial.
3699 | 96 | IA for strategic solution options for the GDE Offline database | 2015-05-15 |  | This Change Request is for Wipro to provide a High Level Impact Assessment on the timescales and costs to deliver a strategic solution for the GDE Offline database as part of the UK Link Programme. | Xoserve have an establisied off line tool that can be used rather than this going into UK Link system, and therefore do not believe business benefit of an automated solution would ever be realised.
3868 | 136 | Notification of Twin streams that have calculated an AQ or W/C ( T04, S91 & T50 | 2015-09-18 | Susan Prosser | The current NRL T04,S91 & T50 files does not support the communication of twin stream: these being SMP’S that have multiple asset and reads. Design would need to be changed to accommodate and support the communication of asset data for twin stream sites via T04, S91 and the T50. | There are less than 30 twin stream sites at present, there would need to be substantial changes to the way this information is supplied in the AQ files (requiring changes to the file formats).
3869 | 137 | CUN being issued downstream | 2015-09-18 | Susan Prosser | The CUN file needs to generated to notify all of the downstream IGTs if and when there has been a change in exit zone for an upstream CSEP | there is a manual workaround in place at present that is sustainable, this is a very rare scenario and therefore is highly doubtful that the cost of change would be beneficial.
4450 | 276 | iGT IIL & IDL files splitting - manual workaround provided in Market Trials into Production post go live | 2016-11-29 | Darren Jackson | The iGTs have had the following service as part of Market Trials when their IDL files have had to be stopped/re-started as a result of a system failure: When files are ready to go again, SAP produces a single “catch up” file covering all the “down” days. However, the MT team (after a request from the iGTs) split the total file into its daily components before issuing out to the iGTS. This was a manual workaround during Market Trials, the iGTs would like this service to be replicated in production for both the IIL and the IDL files. | During Project Nexus Market Trials, several defects were encountered which lead to an inability to deliver iGT daily delta files (IDL), whilst the incident was being investigated and resolved. On these incidences, the approach deployed by Xoserve Market Trials team was to provide a full portfolio refresh (IQL file) and re-instigate the provision of iGT daily delta files. iGTs requested that an alternative approach be utilised, with daily data files being provided for each affected processing day, in order to ‘catch up’ the data position correctly. Xoserve have since confirmed that capability is already in place to request files for any days impacted by a defect period, therefore this change is not required. In addition, Xoserve have confirmed any approach utilised to catch up the data position will be tailored to the specific issue, and will be agreed bilaterally with iGTs.’
3668 | 72 | Design Gaps - Ability To Provide Missing Class 3 Reads | 2015-02-10 | Emma Smith | Following a review of the external BRD’s it has been identified the following requirements have been missed from design - - Notification to shippers of reads missing in a batch of reads for Class 3 SMP’s. This design gap has been discussed with Shippers and it has been agreed it is not required to be delivered for day 1. | Complex change to send a notification back of missing reads from a batch of reads. Unlikely that the business benefit would be realised.
4492 | 348 | Ability to replace Code cut off reads |  |  | MOD578/587 was raised to allow Xoserve to estimate readings at LIS and for re-confirmations where there was no actual reading recorded for a period of up to 3 years pre LIS. All these estimates genareated were determined to be an actual reading for all downstream processes but shown as an esitimated read as the read type. The modifications determined all these read would be replacable for the User registered at the time if didn’t agree with read and/or had better read data available. As these are all set with a read type of estimate if has become apparent in some instances, where the read is not determined to be an opening read, a User would be unable to replace as the validations require to validate to a previous actual reading and one does not exist.. | Have amended the enduring change for code cut off reads to ensure the solution allows for any generated readings to be replacable by the Registered User
4422 | CMS Billing Template Class Change Adjsutment Crossover |  | propose to close, xoserve will raise a new CP should the issue actually present itself |  | The logic in which CMS pulls the adjsutment start and adjustment end date needs to be ammended. CMS need to pull the asjustment start and end date based on the class change dates to make sure that none of the adjustmentments cross over the class change period. This will mean a change to the data the web services pull between CMS and SAP and SAP and CMS. | at present this is not causing a problem internally should it start to cause an issue in the future we will raise a new CR
4467 | Amend functionality to send GCC file to DMSP when Class 1 Confirmation Requests Lapse due to objection. | 2017-03-03 | propose to close doubtful the business benefit would stack up |  | On confirmation of a Class 1 site a GCC file is sent to the relevant DMSP informing them of changes. Should the confirmation be cancelled there is a further GCC sent informing the DMSP that the confirmation is not going ahead. It has been identified that this not being sent in the event that the confirmation request is lapsed due to objection. The functionality needs to be amended to send the GCC in this scenario. There will be no requirement for file format change as we can use the existing request type - CA - Cancelled Confirmation | the number of class 1 sites will reduce during first half of 2018 and therefore will be a significantly reduced number of MPRNs in Class 1, Xoserve recommend this change for closure as unlikely the business benefits would ever be realised. We have a workaround in place that can continue, workaround details - reqt to provide 2 reports to the DMSPs; 1) with their MPRN & AQ information on a monthly basis; 2) with their MPRN & [ratcheted] SOQ information on a weekly basis.

## Changes requiring Sponsorship
XRN Ref | Change Title | Change Description | Delivery Status | Platform | Origination Date | Change Originator | Previous UK Link CR Ref
4499 | CDN/CDR File record Occurence Change | The CDN and CDR file formats specify a record occurrence of up to 10000. Currently SAP and AMT has been set up to mirror the legacy position which limits the record count to 600. This needs to change to reflect the agreed and published file formats. | LIVE | R & N | 2017-07-11 | Emma Lyndon | UKLP IADBI365
4451 | Treatment of values in the CDR | Within the Connection and Disconnection Suite of jobs (this includes the CDN, CDR and CDJ (or CDJOB)) we do not attempt to define allowable values for the functional data items as the original regulations do not go to this level of detail. They do place an obligation on Transporters to record the information that is provided in a C&D Notification. It is for this reason that any notification that involves a connection and / or disconnection gets written to the C&D Store so that we are able to demonstrate this compliance regardless of the outcome of the transaction that writes to UK Link ‘proper’. We cannot reject a CDN if the values don’t match those that we’d expect, and it therefore follows that the CDR (and CDJOB) may include unexpected values. We try to convey this with the phrase ‘anticipated values’ so that Users are aware what we’d ideally like to receive (and in turn provide).In the case that you quote you have highlighted that there is an error in the existing Code. The instance you quote was as a result of a JOB file being processed and the CDR is the confirmation that the details have been written to the C&D Store. In the instance that we are providing the value of ‘U’ in the CDR this is being incorrectly obtained from an alternative (and incorrect) source, but investigations suggest that this error has existed since the inception of this job in July 2004! | LIVE | R & N | 2016-12-05 | David Addison | UKLP IADBI277
4345 | File format changes to the CGI file | The solution to Defect 211 has identified that we need to undertake a file format change to resolve this issue. The requested is to amendment the length of 3 fields on the CGI file because they are currently failing in AMT validation, the actual values that have being derived in some scenario are actually exceeding the current allowable field length. 1. PERCENTAGE_BREACH_CONNECTION_MAX_AQ_SMP 2. PERCENTAGE_BREACH_IGT_SYSTEM_MAX_AQ. 3. PERCENTAGE_BREACH_CONNECTION_MAX_AQ_CSEP Currently the Length of file is defined as 6. Digits before decimal point and 2 after decimal. While investigating the data we found that in some circumstance the value/ calculation exceeds the current acceptable defined length. We are proposing that the length of field is increased. The proposal is that we increase these values to 20 digits before decimal point and 2 after decimal. This is a warning notification that advises that the new calculated values are in excess of 85% of the CSEP MAQ AQ Value.When the Percentage value exceeds the current value there is no actual impact to the Xoserve system or SMP record. The impact is isolated to the outbound file flow of the CGI to IGTs and DNOs. The Transporters will not get the CGI notification file where the AQ breach is greater than the allowable file value. This tolerance breach information supports the Transporter in managing the capacity requirements of their networks. This issue is currently being supported with a manual workaround and the fix will require a file format change. The actual fix should be delivered in line with the notification period of the file format change. | LIVE | R & N | 2017-09-12 | Emma Lyndon | UKLP IADBI379
3667 | Provision of Formula Year AQ | It is not currently included within the current file formats to provide prospective Formula Year AQ. Users have indicated that the non provision of this data creates material uncertainty in pricing for prospective consumers. They are further frustrated that this value is known by Xoserve, but is not passed to Users. It is suggested that adding an optional field to the S75 (which is issued in response to a nomination enquiry, nomination, confirmation and at the transfer of ownership) would provide visibility of this data. The value would be populated where this had been derived for the forthcoming year, and had yet to become effective. | LIVE | R & N | 2015-02-06 | Emma Smith | UKLP IADBI071
3656 | Read Validation Tolerances | Change the read validation tolerance from a % based test to a kWh test for a Supply Meter Point with an AQ less than [30,000 kWh] and to split the AQ band of less than 73,200 into 2 further AQ bands | LIVE | R & N | 2014-12-24 | Michelle Downes | UKLP IADBI060