## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | Incrementing Reads on Isolation Supply Meter Points | 1839.3 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 Deferred | Rejected at ChMC on 14th February. Xoserve are awaiting further clarification from the parties who rejected the change

## IP - For Approval
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
4249 | NA | Address Maintenance Solution | 1856.2 | 2018-01-31 | 2018-02-14 | 2018-02-21 | X | X |  | X |  | 2018-03-07 | Proposed for Release 3
4453 | NA | XRN4453 – File Format Changes | 1856.3 | 2018-01-31 | 2018-02-21 | 2018-02-28 | X | X | X | X | X | 2018-03-07 | Proposed for Release 3
Documentation changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | Changes Proposed for Removal from the Change Log | 1856.1 | 2018-01-31 | 2018-02-14 | 2018-02-21 | X | X | X | X | X | 2018-03-07 | 2018-03-08
NA | NA | New User Notification Method | 1866.1 | 2018-02-09 | 2018-02-23 | 2018-03-02 | X |  |  |  |  | 2018-03-07 | 2018-05-07

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 7th February
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
4299 | 0520A | Reports required under UNC TPD V16.1 in Nexus (reports required by MOD 520A) | 1831.1 | 2018-01-03 | 2018-01-17 | 2018-01-24 | X |  |  |  |  | 2018-02-14 | 29/06/2018 (Release 2)
4304 | NA | Amend referral rules for class 2 smaller LSP’s | 1831.2 | 2018-01-03 | 2018-01-17 | 2018-01-24 |  | X |  |  |  | 2018-02-14 | 29/06/2018 (Release 2)
4248 | NA | Quarterly smart Metering reporting for HSE and DNs | 1831.4 | 2018-01-03 | 2018-01-17 | 2018-01-24 |  | X |  |  |  | 2018-02-14 | 29/06/2018 (Release 2)
4303 | NA | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | 1831.5 | 2018-01-03 | 2018-01-17 | 2018-01-24 | X |  |  |  |  | 2018-02-14 | 29/06/2018 (Release 2)
2381.5B | NA | Changes to the upper parameter of the XDO partial refresh file | 1831.6 | 2018-01-03 | 2018-01-17 | 2018-01-24 |  |  |  |  | X | 2018-02-14 | 29/06/2018 (Release 2)
3477 | NA | Missing Key Data Item from iGTs to Shippers (Plot Number) | 1831.7 | 2018-01-03 | 2018-01-17 | 2018-01-24 | X |  |  | X |  | 2018-02-14 | 29/06/2018 (Release 2)
4288 | NA | DDS/DDU file amendment | 1831.8 | 2018-01-03 | 2018-01-17 | 2018-01-24 |  | X |  |  |  | 2018-02-14 | 29/06/2018 (Release 2)
4514 | NA | MIV File changes for MUR Invoice | 1836.1 | 2018-01-10 | 2018-01-24 | 2018-01-30 |  |  |  |  | X | 2018-02-14 | 29/06/2018 (Release 2)
3386 | NA | New DN role for CMS | 1836.2 | 2018-01-10 | 2018-01-24 | 2018-01-30 |  | X |  |  |  | 2018-02-14 | 29/06/2018 (Release 2)
4513 | NA | Validate all address fields - CMS | 1836.3 | 2018-01-10 | 2018-01-24 | 2018-01-30 | X |  |  |  |  | 2018-02-14 | 29/06/2018 (Release 2)
4309 | NA | Back billing for domestic (SSP) sites needs to be reflect the correct adjustment start date | 1839.2 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 2018-02-14 | 29/06/2018 (Release 2)
4449 | NA | Vulnerable Customer Data - One off Shipper report | 1839.4 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 2018-02-14 | 29/06/2018 (Release 2)
3283 | NA | Recording of DN Siteworks / New Network Connection Reference in Central System | 1845.1 | 2018-01-17 | 2018-01-29 | 2018-01-31 |  | X |  | X |  | 2018-02-14 | 29/06/2018 (Release 2)
4316 | NA | Meter Point Details Report & Sector Breakdown Report | 1845.2 | 2018-01-17 | 2018-01-29 | 2018-01-31 |  |  |  |  | X | 2018-02-14 | 29/06/2018 (Release 2)
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | Changes Proposed for Removal from the Change Log | 1824.1 | 2017-12-15 | 2018-01-12 | NA | X | X | X | X | X | 2018-02-07 | 2018-02-08
NA | NA | Schedule for the Issuing of the Supporting Invoicing Information Files (AML, COI, CZI) January – March 2018 | 1831.3 | 2018-01-03 | 2018-01-17 | 2018-01-24 | X |  |  |  |  | 2018-02-07 | 2018-02-08

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
7th March - no outages to notify