## R&N_2yr_view
Change Allocation | Count of XRNs
Solution Manager Update (Feb'18) | 1
ROM (Not yet landed as a CP) | 3
R4.0 (Jun'19) | 5
R3.0 (Nov'18) | 18
R2.0 (Jun'18) | 17
R1.1 (Dec'17) | 5
R1.0 (Nexus) | 1
R&N New Environment (Apr'18) | 1
R&N Minor Release/Impact Assessment (Mar'18) | 1
Out for industry sponsorship/approval to reject | 7
MOD (Not yet landed as a CP) | 4
Minor Enhancement Delivered Change | 16
Defect R1.16 (Feb'18) | 1
Defect R1.15 (Feb'18) | 1
CSS | 1
Candidate for Minor Release | 5
Grand Total | 87
Please filter in column C within the 'R&N_Live_Changes' tab to view specific XRNs

## R&N_Live_Changes
XRN Ref | High-Level Status | R&N Release Allocation | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Xoserve Proposed Indicative Prioritsation Score | July'17 Change Demand Backlog ChMC Priority | July'17 Change Demand Backlog SDG Priority | Xoserve Platform Owner | Origination Date | Change Originator | Xoserve Project Manager | R&N Release Number | Previous UK Link CR Ref | Delivery Team | ClearQuest Ticket (Minor Enhancement Delivery) | Current Delivery Implementation Forecast Date | Actual Delivery Implenmentation Date | Customer Requested Implementation Date | Primary Application Impacted | Business Process Impact | Flash IA: Percieved Delivery Effort | Workaround Available? | Workaround Accountability | Workaround Frequency | No. of Xoserve FTEs required to service the workaround | Workaround Complexity? | Workaround Lifespan | Change Driver | Change Beneficiary | Shipper Impact | Network Impact | iGT Impact | Primary Impacted DSC Service Area | Number of DSC Service Areas impacted | Change Improvement Scale (Size of proposed change) | Customer System Changes Required? | Customer Testing Likely Required? | Customer Training Required? | Safety of Supply at risk? | Financial Loss Incurred to Customer? | Customer Switching at risk? | ChMC CP Approval date | ChMC EQR Approval date | ChMC BER Approval date | ChMC CCR Approval date
4601 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | US01 Exception Remove Dummy Meter Occurrences | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 60.66% |  |  | R & N | 2018-01-30 | Jo Duncan/Dean Johnson | Donna Johnson | 50 |  | ME | XO3650 | No Date | No Date | 2018-03-31 | ISU | Invoicing | 30-60 days | TRUE | Xoserve | Daily | Five to Ten | Medium | 2018-03-31 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
1154 | 2. Change sanction/approved and in project delivery | R1.0 (Nexus) | UK Link Programme | CP | LIVE | 11. Change In Delivery | 22.22% |  |  | R & N | 2008-03-03 | Chris Smith | Paul Toolan | 1 |  | Project Delivery |  | 2017-06-01 | 2017-06-01 | 2017-06-01 | Other | Other | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 23: Internal | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4528 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | The word ‘PLOT’ as a prefix | CR | LIVE | 11. Change In Delivery | 27.03% |  |  | R & N | 2017-11-07 | Mike Orsler/Emma Smith | Donna Johnson | 50 |  | ME | XO3592 | 2018-03-30 | No Date | 2018-03-23 | Other | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4597 | 1. Start-Up (Progressing through change governance) | ROM (Not yet landed as a CP) | Changes to settlement regime to address Unidentified Gas issues (MOD642) | CP | LIVE | 0. ROM In-Progress | 21.02% |  |  | R & N | 2018-01-25 | Justine Price (Corona Energy) | Steve Ganney | 0 |  | BICC |  | 2018-02-07 | No Date | 2018-02-07 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4452 | 3. Change delivered, awaiting closure approval/sign-off | R1.1 (Dec'17) | Pending capacity amendment with Ratchet | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% | Medium | Medium | R & N | 2016-12-06 | Dean Johnson | Matt Rider | 1.1 | UKLP IADBI279 | Project Delivery |  | 2017-12-08 | 2017-12-08 | 2017-12-08 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-09-13 | No Date | 2017-09-13 | No Date
3747 | 3. Change delivered, awaiting closure approval/sign-off | R1.1 (Dec'17) | Notification of Formula Year AQ & SOQ | CP | LIVE | 12. CCR/Closedown document in progress | 15.02% | High | High | R & N | 2015-07-07 | Emma Smith / Susan Prosser | Matt Rider | 1.1 | UKLP IADBI113 | Project Delivery |  | 2017-12-08 | 2017-12-08 | 2018-05-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-09-13 | No Date | 2017-09-13 | No Date
4598 | 1. Start-Up (Progressing through change governance) | ROM (Not yet landed as a CP) | Changes to settlement regime to address Unidentified Gas issues issues including retrospective correction(MOD 643) | CP | LIVE | 0. ROM In-Progress | 21.02% |  |  | R & N | 2018-01-25 | Lorna Lewin (Orsted) Lorna Lewin (Orsted) Lorna Lewin ( Orsted ) | Steve Ganney | 0 |  | BICC |  | 2018-02-07 | No Date | 2018-02-07 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4448 | 3. Change delivered, awaiting closure approval/sign-off | R1.1 (Dec'17) | Capacity referral raised in error following Nomination | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% | High | High | R & N | 2016-11-09 | Dean Johnson | Matt Rider | 1.1 | UKLP IADBI272 | Project Delivery |  | 2017-12-08 | 2017-12-08 | 2017-12-08 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-09-13 | No Date | 2017-09-13 | No Date
4466 | 3. Change delivered, awaiting closure approval/sign-off | R1.1 (Dec'17) | Mod431 – Validations against file header and data within records | CP | LIVE | 12. CCR/Closedown document in progress | 21.02% | High | High | R & N | 2017-02-27 | Steve Nunnington | Matt Rider | 1.1 | UKLP IADBI305 | Project Delivery |  | 2017-12-08 | 2017-12-08 | 2017-12-08 | AMT | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-09-13 | No Date | 2017-09-13 | No Date
4599 | 1. Start-Up (Progressing through change governance) | ROM (Not yet landed as a CP) | Changes to settlement regime to address Unidentified Gas issues (642A) | CP | LIVE | 0. ROM In-Progress | 21.02% |  |  | R & N | 2018-01-25 | Kirsty Dudley (Eon) | Steve Ganney | 0 |  | BICC |  | 2018-02-07 | No Date | 2018-02-07 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4510 | 3. Change delivered, awaiting closure approval/sign-off | R1.1 (Dec'17) | Negative Consumption Period For Rolling AQ20171023 | CP | LIVE | 13.1. CCR Awaiting ChMC Approval | 21.02% |  |  | R & N | 2017-10-25 | Linda Whitcroft | Debi ¦Jones | 1.1 |  | Project Delivery |  | 2017-12-08 | 2017-12-08 | 2017-12-01 | Other | Other | 0-30days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-11-08 | No Date | 2017-11-08 | No Date
4463 | 2. Change sanction/approved and in project delivery | Defect R1.15 (Feb'18) | CSEP MAX AQ SOQ Rate Application | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | R & N | 2017-02-20 | Emma Smith | Padmini Duvvuri | 1.15 | UKLP IADBI298 | Project Delivery |  | 2018-02-02 | No Date | 2018-04-03 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4468 | 2. Change sanction/approved and in project delivery | Defect R1.16 (Feb'18) | Proposal for the process improvement for SI files | CR | LIVE | 11. Change In Delivery | 21.02% | TBP | Medium | R & N | 2017-03-14 | Linda Whitcroft | Padmini Duvvuri | 1.16 | UKLP IADBI307 | Project Delivery |  | 2018-02-19 | No Date | 2017-12-01 | ISU | Invoicing | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4484 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release | Remove restriction on nominated SOQ (as per MOD 445 | CR | LIVE | 2.1. Start-Up Approach In Progress | 36.64% |  |  | R & N | 2017-06-06 | Bhupinder Basra | Matt Rider | 75 | UKLP IADBI336 | Project Delivery |  | No Date | No Date | 2018-10-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4513 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Change to validation of address fields | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI359 | Project Delivery |  | 2018-06-29 | No Date | 2017-11-01 | CMS | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4529 | 1. Start-Up (Progressing through change governance) | MOD (Not yet landed as a CP) | UNC Modification 0619A Protection from ratchet charges for daily read customers with AQ of 73,200kWh and below MOD0619A | CP | LIVE | 0.5 Change Proposal awaiting MOD approval (ROM complete) | 42.64% |  |  | R & N | 2017-11-09 | Steve Ganney | Padmini Duvvuri | 0 |  | Project Delivery | 3595 | 2017-12-13 | 2017-12-13 | 2018-10-01 | ISU | Invoicing | 0-30days | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-12-13 | No Date | No Date | No Date
4554 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Amendment Invoice validation Reports | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 28.83% |  |  | R & N | 2017-12-05 | Vicky Spiller | Donna Johnson | 50 |  | ME | XO3613 | 2018-06-30 | No Date | 2018-02-28 | ISU | Invoicing | 0-30days | TRUE | Xoserve | Monthly | One | High | 2019-12-01 | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4561 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | US01 Exception Automation | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 66.07% |  |  | R & N | 2017-12-18 | Jo Duncan | Donna Johnson | 50 |  | ME | XO3618 | 2018-06-22 | No Date | 2018-03-31 | ISU | Invoicing | 30-60 days | TRUE | Xoserve | Daily | Five to Ten | Medium | 2018-03-31 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | No Number of impacted DSC Service Areas | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
4543 | 1. Start-Up (Progressing through change governance) | MOD (Not yet landed as a CP) | UNC Modification 0636 - - Updating the parameters for the NTS Optional Commodity Charge | CP | LIVE | 0.5 Change Proposal awaiting MOD approval (ROM complete) | 44.44% |  |  | R & N | 2017-11-28 | Debra Hawkin | Padmini Duvvuri | 50 |  | Project Delivery |  | 2017-12-11 | 2017-12-13 | 2018-06-01 | ISU | Reads | 0-30days | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4514 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | MIV File Changes for MUR Invoice - CMS | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI367 | Project Delivery |  | 2018-06-29 | No Date | 2017-12-01 | CMS | Invoicing | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4347 | 1. Start-Up (Progressing through change governance) | MOD (Not yet landed as a CP) | UNC Modification 0619 - Application of proportionate ratchet charges to daily read sites | CP | LIVE | 0.5 Change Proposal awaiting MOD approval (ROM complete) | 42.64% |  |  | R & N | 2017-08-17 | Murray Thomson on behalf of JO | Murray Thomson | 0 |  | Project Delivery |  | 2017-09-07 | 2017-09-07 | 2018-10-01 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4316 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Meter Point Details Report & Sector Breakdown Report | CR | LIVE | 11. Change In Delivery | 15.02% | TBP | Low | R & N | 2017-04-07 | Mark Cockayne | Christina Francis | 2 | UKLP315 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | BW | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4449 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | PSR requirements – Vulnerable Customer data requirements | CP | LIVE | 11. Change In Delivery | 24.02% | High | High | R & N | 2016-11-11 | Steve Nunnington | Christina Francis | 2 | UKLP273 | Project Delivery |  | 2018-06-29 | No Date | 2017-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | Multiple Market Participants | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
3995a | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Energy Theft Tip-off Service Data Provision | CP | LIVE | 11. Change In Delivery | 21.02% | TBP | High | R & N | 2016-03-15 | Alex Ross-Shaw | Christina Francis | 2 | UKLP222 | Project Delivery |  | 2018-06-29 | No Date | 2016-08-01 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4249 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Address Maintenance Solution | CR | LIVE | 11. Change In Delivery | 21.02% |  |  | R & N | 2017-03-22 | Steve Ganney | Christina Francis | 2 |  | Project Delivery |  | 2018-06-29 | No Date | 2017-11-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4299 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Reports required under UNC TPD V16.1 in Nexus (reports required by Mod 520A) | CP | LIVE | 11. Change In Delivery | 15.02% | High | High | R & N | 2016-08-12 |  | Christina Francis | 2 | UKLP251 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | BW | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4303 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | CR | LIVE | 11. Change In Delivery | 15.02% | TBP | Low | R & N | 2016-10-18 | Dean Johnson | Christina Francis | 2 | UKLP267 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4304 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Amend referral rules for class 2 smaller LSP’s | CR | LIVE | 11. Change In Delivery | 15.02% | TBP | Medium | R & N | 2016-11-03 | Dean Johnson | Christina Francis | 2 | UKLP270 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4545 | 1. Start-Up (Progressing through change governance) | MOD (Not yet landed as a CP) | UNC Modification 0619B - Application of proportionate ratchet charges to daily read sites | CP | LIVE | 0.5 Change Proposal awaiting MOD approval (ROM complete) | 42.64% |  |  | R & N | 2017-11-29 |  | Murray Thomson | 50 |  | Project Delivery |  | 2017-12-13 | 2017-12-13 | 2018-10-01 | ISU | No Process | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-12-13 | No Date | No Date | No Date
4309 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Back billing for domestic (SSP) sites needs to be reflect thecorrect adjustment start date | CR | LIVE | 11. Change In Delivery | 15.02% | TBP | Low | R & N | 2016-01-19 | Dean Johnson | Christina Francis | 2 | UKLP287 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | CMS | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
2831.5b | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Changes to the upper parameter of the XDO partial refresh file. Post Nexus (R2) | CR | LIVE | 11. Change In Delivery | 21.02% | TBP | High | R & N | 2017-02-07 | Jon Follows | Christina Francis | 2 | UKLP292 | Project Delivery |  | 2018-06-29 | No Date | 2017-04-07 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4526 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | MOD432 incorrectly removed M3.7.3 & M3.7.4 revised Meter Read to be re-instated in UNC and the associated process | CR | LIVE | 97. Xoserve require ChMC sponsorship | 9.009% | TBP | Medium | R & N | 2016-02-10 | Emma Smith | No Project Manager | 0 | UKLP IADBI174 | No Delivery Team |  | No Date | No Date | No Date | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3477 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Missing Key Data Item from iGT’s to Shippers (Plot Number) | CP | LIVE | 11. Change In Delivery | 21.02% | High | High | R & N | 2015-07-07 | Lee Chambers | Christina Francis | 2 | UKLP IADBI112 | Project Delivery |  | 2018-06-29 | No Date | 2000-02-02 | BW | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-10 | 2018-01-10 | No Date
4556 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Process to provide a report when Gas Safety Regulations requests return no MPRN’s | CP | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 28.23% |  |  | R & N | 2017-12-06 | Andy Clasper | Matt Rider | 50 |  | ME | XO3614 | No Date | No Date | 2018-02-23 | ISU | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-01-10 | No Date | No Date | No Date
4288 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | DDS/DDU file amendment | CP | LIVE | 11. Change In Delivery | 21.02% | Low | High pending discussions with all Networks | R & N | 2015-10-14 |  | Christina Francis | 2 | UKLP IADBI147 | Project Delivery |  | 2018-06-29 | No Date | 2017-11-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4381 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | The updating of the ZDT_AQ_OPER table | CR | LIVE | 11. Change In Delivery | 56.76% |  |  | R & N | 2017-10-06 | Sue Prosser/Emma Lyndon | Donna Johnson | 50 |  | ME |  | 2018-03-16 | No Date | 2018-02-19 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
3283 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Recording of DN Siteworks’ / New Network Connection Reference in Central systems (ON HOLD PENDING NEW CO) | CP | LIVE | 11. Change In Delivery | 21.02% | Low | Low | R & N | 2013-12-16 | Joel Martin | Christina Francis | 2 | n/a | Project Delivery |  | 2018-06-29 | No Date | 2000-02-02 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
3386 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Create new “role” for CMS to cover all activities undertaken within a Distribution Network (ON HOLD PENDING NEW CO) | CP | LIVE | 11. Change In Delivery | 21.02% | Low | Low | R & N | 2014-05-08 | Jo Ferguson | Christina Francis | 2 | n/a | Project Delivery |  | 2018-06-29 | No Date | 2000-02-02 | CMS | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4248 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Quarterly smart metering reporting for HS&E and GDNs (post Nexus R2) | CP | LIVE | 11. Change In Delivery | 21.02% | High | High | R & N | 2017-03-22 | Joanna Ferguson | Christina Francis | 2 | n/a | Project Delivery |  | 2018-06-29 | No Date | 2017-06-29 | BW | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4361 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Release 2 Delivery | CP | LIVE | 11. Change In Delivery | 15.02% |  |  | R & N | 2017-10-11 | Christina Francis | Christina Francis | 2 |  | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | ISU | Other | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4534 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Amendment to RGMA Validation Rules for Meter Asset Installation Date | CP | LIVE | 7. BER/Business Case In Progress | 52.85% |  |  | R & N | 2017-11-20 | Andrew Margan | Padmini Duvvuri | 3 |  | Project Delivery |  | No Date | No Date | 2018-06-01 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | ChMC endorsed Change Proposal | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | One | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | 2018-01-10 | 2018-02-07 | No Date | No Date
4345 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | File format changes to the CGI file | CR | LIVE | 97. Xoserve require ChMC sponsorship | 21.02% |  |  | R & N | 2017-09-12 | Emma Lyndon | Padmini Duvvuri | 99 | UKLP IADBI379 | Project Delivery |  | No Date | No Date | 2017-12-31 | AMT | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3667 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Provision of Formula Year AQ | CR | LIVE | 7. BER/Business Case In Progress | 10.21% | High | High | R & N | 2015-02-06 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI071 | Project Delivery |  | No Date | No Date | 2018-12-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4538 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Insertion of Maximum Number of Occurrences in Meter Inspection Date Notice (MID) File. | CR | LIVE | 7. BER/Business Case In Progress | 21.02% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | Project Delivery |  | 2000-02-02 | No Date | 2017-09-01 | ISU | No Process | 0-30days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4539 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | New File Level Rejection | CR | LIVE | 7. BER/Business Case In Progress | 27.63% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | Project Delivery |  | 2000-02-02 | No Date | 2018-11-01 | ISU | Invoicing | 0-30days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4453 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | File Format Should Have Changes | CR | LIVE | 7. BER/Business Case In Progress | 33.63% | TBP | Low | R & N | 2016-12-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI280v3 | Project Delivery |  | No Date | No Date | 2018-06-01 | ISU | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4454 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Cadent Billing - DN Sales (Outbound Services) | CP | LIVE | 7. BER/Business Case In Progress | 51.95% | TBP | High | R & N | 2016-12-16 | Linda Whitcroft | Padmini Duvvuri | 3 | UKLP IADBI281 | Project Delivery |  | 2018-06-29 | No Date | 2018-06-01 | ISU | Invoicing | 31-100days | TRUE | Both Xoserve & Customer | Daily | 2-5 | High | 2018-06-01 | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | High | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | 2017-12-13 | 2018-02-07 | No Date | No Date
4273 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Introducing IHD (In-Home Display) Installed Status of Failed MOD614 | CP | LIVE | 7. BER/Business Case In Progress | 25.23% |  |  | R & N | 2017-05-10 | Alex Cebo | Padmini Duvvuri | 3 |  | Project Delivery |  | No Date | No Date | 2018-06-01 | ISU | Other | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-11-08 | 2018-02-07 | No Date | No Date
4432 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Amendment to U82 record to include the revised NTS optional tariff rate | CR | LIVE | 7. BER/Business Case In Progress | 21.62% | TBP | Low | R & N | 2016-05-04 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI203 | Project Delivery |  | No Date | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4451 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | Treatment of values in the CDR | CR | LIVE | 97. Xoserve require ChMC sponsorship | 11.41% | TBP | Low | R & N | 2016-12-05 | David Addison | Padmini Duvvuri | 99 | UKLP IADBI277 | Project Delivery |  | No Date | No Date | 2018-10-01 | ISU | RGMA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4436 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Change number of occurances for K13 record for SSMP’s | CR | LIVE | 7. BER/Business Case In Progress | 22.82% | TBP | Low | R & N | 2016-06-21 | Dean Johnson | Padmini Duvvuri | 3 | UKLP IADBI225 | Project Delivery |  | No Date | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4465 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Annual Production and notification of LIS-3years read | CR | LIVE | 11. Change In Delivery | 50.75% | TBP | Low | R & N | 2017-02-21 | Emma Smith | Donna Johnson | 50 | UKLP IADBI301 | ME | XO3624 | 2018-03-31 | No Date | 2018-03-01 | ISU | Reads | 30-60 days | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | LOW | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4337 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | To change the optionality of the Supply Point confirmation reference for the T51 file | CR | LIVE | 7. BER/Business Case In Progress | 30.63% |  |  | R & N | 2017-07-24 | Sue prosse/Emma Lyndon | Padmini Duvvuri | 3 |  | Project Delivery |  | 2017-07-31 | No Date | 2018-04-01 | AMT | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | One | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4495 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Energy Tolerance Rejection code | CR | LIVE | 7. BER/Business Case In Progress | 27.63% |  |  | R & N | 2017-06-28 | Nick Timm | Padmini Duvvuri | 3 | UKLP IADBI356 | Project Delivery | 3627 | No Date | No Date | 2018-11-01 | ISU | Reads | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4469 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release | UMR Hierarchy Amendment in AMT | CR | LIVE | 2.1. Start-Up Approach In Progress | 27.63% | TBP | Low | R & N | 2017-03-27 | Karen Marklew | Matt Rider | 75 | UKLP IADBI309 | Project Delivery | 3628 | No Date | No Date | 2018-10-01 | AMT | Reads | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3656 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Read Validation Tolerances | CR | LIVE | 7. BER/Business Case In Progress | 15.02% | TBP | Low | R & N | 2014-12-24 | Michelle Downes | Padmini Duvvuri | 3 | UKLP IADBI060 | Project Delivery |  | No Date | No Date | 2018-05-01 | ISU | RGMA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4431 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | CR | LIVE | 7. BER/Business Case In Progress | 33.03% | TBP | High | R & N | 2016-05-04 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI202 | Project Delivery |  | No Date | No Date | 2018-10-01 | ISU | Reads | 31-100days | TRUE | External Customer | Daily | No Xoserve FTEs | Low | 2018-12-31 | MOD/Ofgem | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4443 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | File Format Changes Aug 16 Unique Sites (deferred items from CR252) | CR | LIVE | 7. BER/Business Case In Progress | 24.62% | TBP | Low | R & N | 2016-09-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI258 | Project Delivery |  | No Date | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4458 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Class 4 CSEPS Reconciliation Variance Identification | CR | LIVE | 7. BER/Business Case In Progress | 22.22% | TBP | Medium | R & N | 2017-01-26 | Karen Marklew | Padmini Duvvuri | 3 | UKLP IADBI289 | Project Delivery |  | No Date | No Date | 2018-12-31 | ISU | Reads | 31-100days | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | LOW | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4421 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | Addition of Daily LDZ Unidentified Gas (UG) to National Grid Operational Data Services | CR | LIVE | 97. Xoserve require ChMC sponsorship | 36.04% | TBP | Medium | R & N | 2015-12-17 | Fiona Cottam | Matt Rider | 99 | UKLP IADBI162 | Project Delivery |  | No Date | No Date | 2017-06-01 | ISU | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | FALSE | TRUE | FALSE | Service Area 15: Demand Estimation | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4480 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release | Capacity reconciliation charge (MOD445) calculation functionality | CR | LIVE | 2.1. Start-Up Approach In Progress | 48.65% |  |  | R & N | 2017-05-30 | Kiran Kumar | Matt Rider | 75 | UKLP IADBI331 | Project Delivery |  | No Date | No Date | 2018-10-01 | ISU | Other | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4486 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Meter Type O = Oriffice to be an acceptable value in file formats and reports | CR | LIVE | 7. BER/Business Case In Progress | 21.62% |  |  | R & N | 2017-06-05 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI338 | Project Delivery |  | No Date | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4482 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | SAP Meter Read Entry Screen | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 24.62% |  |  | R & N | 2017-05-30 | Emma Smith | Donna Johnson | 99 | UKLP IADBI333 | ME | XO3629 | No Date | No Date | 2018-03-01 | ISU | Reads | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4496 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release | iGT Address Amendments - SAP | CR | LIVE | 2.1. Start-Up Approach In Progress | 34.83% |  |  | R & N | 2017-06-30 | Richard Cresswell | Matt Rider | 75 | UKLP IADBI358 | Project Delivery |  | No Date | No Date | 2018-12-31 | ISU | SPA | 31-100days | TRUE | Xoserve | Daily | No Xoserve FTEs | High | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4499 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release | CDN/CDR File record Occurence Change | CR | LIVE | 2.1. Start-Up Approach In Progress | 25.23% |  |  | R & N | 2017-07-11 | Emma Lyndon | Matt Rider | 75 | UKLP IADBI365 | Project Delivery |  | No Date | No Date | 2018-05-31 | ISU | RGMA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4612 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | RGMA Activity on Transfer Date | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 63.96% |  |  | R & N | 2018-02-20 | John Harris | Donna Johnson | 0 |  | ME | XO3659 | No Date | No Date | 2018-04-01 | ISU | Reads | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | FALSE | FALSE | Service Area 23: Internal | Two to Five | High | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
4521 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | NTS Datalogged Site not being loaded into Gemini | CR | LIVE | 11. Change In Delivery | 33.63% |  |  | R & N | 2017-10-31 | Liz Ryan/Emma Lyndon | Donna Johnson | 50 |  | ME | XOS3587 | 2018-04-29 | No Date | 2018-04-30 | Gemini | Other | 0-30days | TRUE | Both Xoserve & Customer | Daily | One | Medium | 2019-12-01 | License Condition | One Market Participant | FALSE | TRUE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4358 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Offline Systems Database D096 Phase 2 | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | R & N | 2017-09-04 | Dan Donovan | Donna Johnson | 50 |  | ME | XO3559 | 2018-02-28 | No Date | 2018-10-31 | Other | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4044 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Extension of ‘Must Read’ process to include Annual Read sites | CP | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 27.03% |  |  | R & N | 2017-12-05 | Andy Clasper | Matt Rider | 50 |  | ME | XO3610 | No Date | No Date | 2018-09-01 | ISU | RGMA | 0-30days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | FALSE | No DSC Service Area | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-01-10 | No Date | No Date | No Date
4574 | 2. Change sanction/approved and in project delivery | R&N New Environment (Apr'18) | Provision of a New Project Track UK Link Environment | CR | LIVE | 11. Change In Delivery | 13.21% |  |  | R & N | 2018-01-08 | Lee Chambers | Lee Chambers | 0 |  | Project Delivery |  | 2018-03-31 | No Date | 2018-06-15 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4573 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | AQ Market Breaker Tolerance validation values Error | CR | LIVE | 11. Change In Delivery | 31.53% |  |  | R & N | 2018-01-03 | Sue Pross | Donna Johnson | 50 |  | ME | XO3623 | 2018-02-22 | No Date | 2018-02-16 | ISU | Reads | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4575 | 2. Change sanction/approved and in project delivery | R&N Minor Release/Impact Assessment (Mar'18) | Introduction of a R&N Minor Release Delivery Mechanism | CR | LIVE | 11. Change In Delivery | 15.02% |  |  | R & N | 2018-01-09 | Lee Chambers | Lee Chambers | 0 |  | Project Delivery |  | 2018-05-15 | No Date | 2018-05-15 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4481 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Resolution of penny mismatches within invoice supporting information for Core invoices. | CR | LIVE | 7. BER/Business Case In Progress | 31.83% |  |  | R & N | 2017-05-30 | Kiran Kumar | Padmini Duvvuri | 3 | UKLP IADBI332 | Project Delivery |  | 2018-03-01 | No Date | 2018-06-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4584 | 1. Start-Up (Progressing through change governance) | CSS | Central Switching Services | CR | LIVE | 2.1. Start-Up Approach In Progress | 9.009% |  |  | R & N | 2018-01-17 | Andy Earnshaw | Smitha Pichrikat | 0 |  | Project Delivery |  | No Date | No Date | 2020-12-01 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4587 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Test of the Bulk upload facility | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 63.96% |  |  | R & N | 2018-01-22 | Dawn Gallacher | Donna Johnson | 50 |  | ME | XO3648 | No Date | No Date | 2018-05-04 | ISU | SPA | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | Two to Five | High | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
4591 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | FOF environment for GDE Lookup tables in SAP BW | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 31.53% |  |  | R & N | 2018-01-23 | Julie Bretherton | Donna Johnson | 50 |  | ME | XOS3658 | No Date | No Date | 2018-03-06 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4593 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Removal of Backbiling Exceptions (BB02, BB04, BB05) | CR | LIVE | 2.2. Awaiting ME/BICC HLE Quote | 22.22% |  |  | R & N | 2018-01-23 | Jo Duncan | Donna Johnson | 50 |  | ME | XO3645 | No Date | No Date | 2018-06-30 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 2018-06-30 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3699 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | IA for strategic solution options for the GDE Offline database | CR | LIVE | 98. Xoserve Propose Change Not Required | 21.02% | Low | Low | R & N | 2015-05-15 |  | Padmini Duvvuri | 99 | UKLP IADBI096 | Project Delivery |  | No Date | No Date | 2000-02-02 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4439 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | GDE Cashout – Daily Curtailment Volume (DCV) for Daily Metered sites | CR | LIVE | 98. Xoserve Propose Change Not Required | 21.02% | Low | Low | R & N | 2016-08-04 | Lorraine Cave | Padmini Duvvuri | 99 | UKLP IADBI244 | Project Delivery |  | No Date | No Date | 2000-02-02 | Gemini | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4461 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | Splitting of the DXI inbound and DXR outbound file from the DCC. | CR | LIVE | 98. Xoserve Propose Change Not Required | 20.42% | TBP | Consensus is Medium, One DN had a recommendation of high | R & N | 2017-02-07 | Jon Follows | Paul Orsler | 99 | UKLP IADBI293 | Project Delivery |  | No Date | No Date | 2018-12-31 | ISU | SPA | 31-100days | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | LOW | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4572 | 1. Start-Up (Progressing through change governance) | R3.0 (Nov'18) | Retail & Network Release 3 | CP | LIVE | 7. BER/Business Case In Progress | 11.41% |  |  | R & N | 2018-01-03 | Padmini Duvvuri | Padmini Duvvuri | 3 |  | Project Delivery |  | No Date | No Date | 2018-10-31 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | No Date | No Date
4541 | 1. Start-Up (Progressing through change governance) | R4.0 (Jun'19) | Read Design Gaps - Missing Overide Flags In RGMA and Retro Files Linked to Retro (4474) | CR | LIVE | 2.1. Start-Up Approach In Progress | 29.43% | Low | Low - to be reviewed in 3 months time | R & N | 2015-02-10 | Emma Smith | Matt Rider | 4 | UKLP IADBI073 | Project Delivery |  | No Date | No Date | 2018-11-01 | ISU | RGMA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4609 | 1. Start-Up (Progressing through change governance) | R4.0 (Jun'19) | Change to CSEP Creation Effective From Date | CR | LIVE | 2.1. Start-Up Approach In Progress | 27.63% |  |  | R & N | 2018-02-20 | Emma Lyndon | Lee Chambers | 4 |  | Project Delivery |  | No Date | No Date | 2018-05-31 | ISU | Invoicing | 30-60 days | TRUE | Xoserve | Monthly | One | Medium | 2018-05-31 | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4474 | 1. Start-Up (Progressing through change governance) | R4.0 (Jun'19) | Delivery of Retro | CR | LIVE | 2.1. Start-Up Approach In Progress | 37.24% | TBP | High | R & N | 2017-04-21 | Lee Chambers | Matt Rider | 4 | UKLP IADBI319 | Project Delivery |  | No Date | No Date | 2019-02-01 | ISU | Other | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Five to Twenty | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3732 | 1. Start-Up (Progressing through change governance) | R4.0 (Jun'19) | Capability to replace a sequence of readings | CR | LIVE | 2.1. Start-Up Approach In Progress | 44.44% | High | Medium | R & N | 2015-06-17 | Emma Smith | Matt Rider | 4 | UKLP IADBI109 | Project Delivery |  | No Date | No Date | 2018-11-01 | ISU | Other | 100+days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4576 | 1. Start-Up (Progressing through change governance) | R4.0 (Jun'19) | Class 4 Transfer Reads not visible to shippers in DES | CP | LIVE | 2.1. Start-Up Approach In Progress | 21.02% |  |  | R & N | 2018-01-09 | Alison Cross | Lee Chambers | 4 |  | Project Delivery | XO3630 | No Date | No Date | No Date | BW | Portal | 30-60 days | TRUE | External Customer | Monthly | One | Low | 2018-03-30 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4378 | 2. Change sanction/approved and in project delivery | Solution Manager Update (Feb'18) | Solution Manager Upgrade | CR | LIVE | 11. Change In Delivery | 18.02% |  |  | R & N | 2017-10-02 | Smitha Pichrikat | Smitha Pichrikat | 0 |  | Project Delivery |  | 2018-03-23 | No Date | 2018-04-03 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date

## Sheet4 (hidden)
Row Labels | Count of XRN Ref
(blank)
Solution Manager Update (Feb'18) | 1
ROM (Not yet landed as a CP) | 3 | y
R4.0 (Jun'19) | 5 | y
R3.0 (Nov'18) | 18 | y
R2.0 (Jun'18) | 17 | y
R1.1 (Dec'17) | 5 | y
R1.0 (Nexus) | 1 | y
R&N New Environment (Apr'18) | 1 | y
R&N Minor Release/Impact Assessment (Mar'18) | 1 | y
Out for industry sponsorship/approval to reject | 7 | y
MOD (Not yet landed as a CP) | 4 | y
Minor Enhancement Delivered Change | 16 | y
Defect R1.16 (Feb'18) | 1 | y
Defect R1.15 (Feb'18) | 1 | y
CSS | 1 | y
Candidate for Minor Release | 5 | y
Grand Total | 87