## Version Control
VERSION CONTROL/GUIDANCE
Version | COR | Issue Date | Summary of Change
1 | 4186 | 2017-05-03 | Original Change Demand Register for discussion at the 10th May DSC ChC
2 | 4186 | 2017-05-23 | Updates from DSC Change Committee held on the 10th May to include a number of COR's not on the V1 Change Demand Register and proposed prioritisation of those change completed at the ChC
3 | 4186 | 2017-06-16 | 1. Updated the Existing Change Proposal Number column 2. Date of DSC Proposed Priority Coulmn added 3. Added a new column 'Date of ChMC Proposed Priority' and 'ChMC Proposed Priority' 3. Column Names renamed: a. Requirement(s) of Change Request/Proposal to Requirement Description b. High level view of impact to market participants to Potential Impacted Market Participants c. Service Area to Service Area Details 4.New column added to capture the 'Justification of Change' 5. SDG Comments and SDG Priority columns added
4 | 4186 | 2017-07-05 | 1. Added coulmns to capture SDG Meeting details - SDG Priority - SDG Comments - Actions from SDG - Status = Open/Closed - CDB Audit History 2. Serial number 69 and 70 have been newly added to the list as 'Proposed for Bubbling Under' changes to consider for prioritisation

## ChMC Change Demand Backlog
Serial No | Existing Change Proposal Number | Xoserve Change Request Number | Change Request Title | CDB Audit History | Drivers of Change | Benefit/Case for Change | Requirement Description | Breach of Code | Related to MOD Ref | MOD Implementation Date | Comments | Potential Impacted Market Participants | Service Area Details | Source | Justification of Change | Change Status | Proposed Status | Dependency to any other Change/Defect | ChMC Proposed Priority | Date of ChMC Proposed Priority | SDG Priority | SDG Comments | Actions from SDG | Next review |  |  |  | Direct Services - Code Services | Direct Services - Non-Code Services | Agency Services GT - Code Services | Agency Services GT - Non-Code Services | Specific Services | Specific Services Terms
1 |  | UKLP060 | Read Validation Tolerances | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement to change the Read validation tolerance from a % based test to a kWh test for a Supply Meter Point with an AQ less than [30,000 kWh] and to split the AQ band of less than 73,200 into 2 further AQ bands. | No |  |  |  | Shippers | Service Area 5: Metered Volume and Metered Quantity | PNUNC | The analysis proved that the change would result in significantly less rejections for Meter Points with an AQ less than 30,000 kWh (domestic sites) | Open | Proposed for Bubbling Under | NA | TBP |  | Low | There remains Read validation concerns; some Users would like to review the whole process. However, further time is needed for UKLP to embed. | ChMC to recommend a review group or technical sub committee to consider in more detail | ChMC - For consideration on 12th July. SDG review in 3 months - 18th September 2017
2 |  | UKLP065 | Correction Factor Application | 03/05/2017 - Change added to CDB | Business Excellence | New Requirement | A requirement to ensure a facilitation is available to censor check the appropriate Correction Factor is being applied and thus consumption can be calculated. In addition, the Energy Thermal Regulations document state the requirements for what Correction Factor that must be applied. | No |  |  |  | Shippers | Service Area 15: Demand Estimation | PNUNC | This will ensure the appropriate Correction Factor is being applied and thus consumption can be calculated. In addition, the Energy Thermal Regulations document state the requirements for what Correction Factor that must be applied. | Open | Proposed for Bubbling Under | NA | Medium | 2017-06-07 | Low | This change relates to threshold crossers and there being no trigger to show the Correction Factor should be amended. This is a Shipper obligation. The obligation is reviewed by the Performance Assurance Committee (PAC). It is reported through PAC and the shipper performance packs therefore Shippers have visibility. There is an AQ notification to show when a site moves across the threshold. Currently this is within Shipper control to amend. SDG recommended a low priority. | ACTION 28/06/17: ChMC to consider the recommendation from SDG that is different to the previous prioritisation made at ChMC | ChMC to review and agree prioritisation proposed by SDG on 12th July | System/Process | Business Excellence | Internal
3 |  | UKLP071 | Provision of Formula Year AQ | 03/05/2017 - Change added to CDB | Business Excellence | New Requirement | A requirement to add an optional field to the S75 which would provide visibility of provision year AQ data. The value would be populated where this had been derived for the forthcoming year, and had yet to become effective. | No |  |  | Not in UNC, users require this for quotes and transportation charges | Shippers | To Be Determined | PNUNC | Provision of this data in response to a nomination enquiry, nomination, confirmation and at the transfer of ownership where it is derived and held in UK Link will mean that all Users have the same information available with which to engage the consumer. | Open | Proposed for Bubbling Under | NA | High | 2017-06-07 | High | This change would require a file format change to add in the prospective AQ value. Currently there is no workaround. SDG confirmed to prioritise as high | ACTION 28/06/17: Xoserve to investigate a workaround, could the service desk be called as a commercial service? Is this feasible in terms of rules and competition? | SDG 10th July | Report | Market Driven | External
4 |  | UKLP072 | Design Gaps - Ability To Provide Missing Class 3 Reads | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to create notification to Shippers of any Reads missing in a batch of Reads for Class 3 SMP’s | No |  |  |  | Shippers | Service Area 5: Metered Volume and Metered Quantity | PNUNC | These requirements have been captured in the external BRD’s but have not been captured in design. | Open | Proposed for Bubbling Under | NA | Low | 2017-05-10 | Low | SDG concluded there is only a small window of value in this report as AQ finishes at M+10. SDG confirmed low priority | To be reviewed in 6 months time | SDG review in 6 months - 18th December |  | Service Introduction
5 | XRN4281 | UKLP073 | Read Design Gaps - Missing Override Flags In RGMA and RETRO Files | 03/05/2017 - Change added to CDB | Business Excellence | Design Gap | A requirement to include Read validation to the Reads supplied by the Registered User in the RGMA and RETRO update file flows. A Read tolerance override flag will be required to be added to the relevant file formats and validation to consider when the tolerance override flag has been set the by User. | No |  |  | Discussed in DSC meeting 10/05/2017 The validation rules are contained in a supplementary guidance and not in UNC. Inner tolerance validation not applied. There should be 2 Change Proposals submitted for this change to cover RGMA and RETRO. | DNs Shippers | Service Area 5: Metered Volume and Metered Quantity | PNUNC | There was a requirement which has not been fulfilled. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low - to be reviewed in 3 months time | Outer tolerance is still rejecting, therefore this change only impacts on inner tolerance. RGMA governance will also need to followed which could delay or amend the change. Shipper Users feel that it is too early following implementation to assess, further analysis over a few months needs to be completed. There is no business case to progress at present. Change may be required to be split into 2 changes - one to cover RETRO (RTO file) and one for RGMA | To be reviewed in 3 months time | SDG review in 3 months - 18th September 2017 |  | Service Sustaining
6 |  | UKLP096 | IA for strategic solution options for the GDE Offline database | 03/05/2017 - Change added to CDB | Business Excellence | Continuous Improvement | A requirement for solution options for a GDE solution to remove the offline solution. | No |  |  |  | DNs Shippers |  | DN | It is the enduring solution for the SCR MOD driven change. A workaround currently exists, this change is to look at an enduring online solution. | Open | Proposed for Bubbling Under | NA | Low | 2017-05-10 | Low | Assessed as low priority due to offline solution. SDG confirmed low priority | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
7 | XRN4282 | UKLP109 | Capability to replace a sequence of Readings | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A Requirement to replace multiple Readings in one file. A user can replace a sequence of Readings but only 1 at a time and the chances of failure are high. | No |  |  |  | Shippers | Service Area 5: Metered Volume and Metered Quantity | PNUNC | There was a requirement which has not been fulfilled. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Medium | The requirement for this change was captured however the design was built differently. This was discussed through RETRO workshops and agreed to be discussed post go-live. Some Shipper Users expressed that this is already causing concerns, creating work. There is potential for the priority to decrease over time however high at present on sites with poor Read history. May be impacting on the current AQ issue. Shipper Users felt it is high priority, causing system effort and User intervention - creating rework and additional effort - resource and manpower. However categorised as medium whilst the solution needs developing. | ChMC to recommend a review group or technical sub committee to consider in more detail | ChMC - For consideration on 12th July.
8 |  | UKLP112 | Missing Key Data Item from iGTs to Shippers (Plot Number) | 03/05/2017 - Change added to CDB | Service Sustaining | New Requirement | A requirement to include the Plot number within current Shippers File Formats. | No |  |  |  | iGTs Shippers |  | PNUNC | This is a missed file format requirement from the initial file format baseline and is a requirement for NGD to receive from Xoserve to support their business processes. The file format will require some amended to be consistent with the new EWS (Emergency) file and to work in the new SAP ISU system. The file format needs to be documented with its hierarchy. | Open | Proposed for Bubbling Under | NA | High | 2017-06-07 | High | Currently the plot number is in the Delivery Point Alias field which is not within the AES. Shipper Users view it as high priority for ease of process and to help with new connections. Viewed as an improvement that will help the process. | ChMC to recommend a review group or technical sub committee to consider in more detail | ChMC - For consideration on 12th July.
9 | XRN3747 | UKLP113 | Notification of Formula Year AQ & SOQ | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to notify Users at Month -5 of changes to the Rolling and/or Formula year AQ/SOQ following the monthly calculation/update process. | Yes | 432 | 1st June 17 | MOD432 text - G1.6.6Code implies we will notify the user 'New formula year AQ & SOQ First notification due to be issued March 18 | Shippers | Service Area 6: Annual Quantity, DM Supply Point and Offtake Rate Reviews | PNUNC | The Formula Year AQ/SOQ is used to derive transportation rates and capacity charging for Class 3 & 4 SMP’s therefore Shippers must have this information sent to them as and when it changes. The change in the formula year AQ value must trigger the offer addendum process (the S91). The AQ correction process has accommodated this requirement. However, the Annual update for the Formula year AQ value is missing this trigger for the offer addendum process. | Open | CP Available (CDSP Proposed R1.1) | NA | High | 2017-06-07 | High | Users requested confirmation that there are no change to file formats - Xoserve confirmed this to be correct. Confirmed high priority as set at ChMC | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
10 | XRN4284 | UKLP122 | PAF Indicator field inclusion on VAD and ACR files | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | A requirement to include the PAF Indicator field on VAD and ACR file formats. | No |  |  |  | DNs Shippers | Service Area 1: Manage Supply Point Registration | UKLP | Xoserve reports to the industry on the accuracy of the address data that we hold. This is reflected by using the ‘PAF Indicator’ information that is currently held within UK Link. Therefore, if we are not able to report this information correctly Xoserve is failing in one of the services we provide and also will be reflecting an untrue and less positive position on the quality of our data. This would see a reduction in the trust our stakeholders will have in the service we provide and the data we hold. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Users questioned the proposal and its intention Xoserve confirmed the impact is around data quality and ensuring it is the best; This is to ensure the address is PAF valid. Users felt that the change is relevant to Xoserve but has minimal impacts on Users. As address quality is high for now it feels as though it is a low priority | ACTION 28/06/17: Xoserve to provide additional details about the change | SDG 10th July
11 | XRN4286 | UKLP136 | Notification of Twin streams that have calculated an AQ or W/C ( T04, S91 & T50) | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to support twin streams. The current NRL T04,S91 & T50 files does not support the communication of twin stream: these being SMP’S that have multiple Asset and Reads. | No |  |  |  | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | UKLP | The current design does not accommodate the communication of the Asset and Read information for Twins Stream SMP’S once either the AQ or the W/C has been calculated. The NRL T04, S91 and the T50 only communicate a single set of Meter Reads and Asset details. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | The files are providing data on the first Asset but not giving Reads on other Meters on twin stream sites. There are 21 twin streams. Users asked if there is a workaround Xoserve informed Users the first line of data is provided, the lower level of data is not included. The AQ is provided which was viewed as important. Concern that any errors on these sites can be large as the sites have large AQs. Low impact based on an additional workaround, whereby portal is not giving the information, Users are calling in. In terms of the volumes it was deemed low. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
12 | XRN4287 | UKLP140 | .DUP & .DUS file type registration in AMT | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to support the duplicate invoice & supporting information from the new UK Link application | No |  |  |  | Shippers | 18 Provision of user reports and information | UKLP | If a new solution is not implemented then CDSP would not be able to fulfil any external Stakeholder request to issue out duplicate invoice and supporting information from the new UKLink solution. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low - to be reviewed in 3 months time | Clarification was provided on this change - this is for a duplicate copy of a file. Users found it difficult to prioritise as invoices are yet to be issued | To be reviewed in 3 months time | SDG review in 3 months - 18th September 2017
13 | XRN3830 | UKLP142 | Change to DN files .DDU .DDS & .CPM | 03/05/2017 - Change added to CDB | Business Excellence | New Requirement | A requirement for additional data items on Demand Derivation System to realise the benefits of the systems improvements. | No |  |  | CDSP has submitted a Change Order for this requirement in September 2015 which has the XRN 3830. | DNs | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | DN | National Grid is replacing its Demand Derivation System and this necessitates the provision of additional data fields in the files sent by Xoserve for use with their demand system. | Open | CP Available (CDSP Proposed R1.1) | NA | TBP |  | High pending discussions with all Networks | This change has 5 fields that have been requested for changes- this was after close out of design. There is no impact to Gemini. National Grid are currently completing a manual workaround to resolve. Action was taken at ChMC for DNs to further discuss this change. | ACTION 28/06/17: Awaiting an outcome from the DN discussions | ChMC to review and agree prioritisation proposed by SDG on 12th July
14 | XRN4288 | UKLP147 | DDS/DDU file amendment | 03/05/2017 - Change added to CDB | Service Sustaining | New Requirement | A requirement for the following changes to the DN DDS and DDU files: 1. Twin stream Meters - For DDS and DDU files to only contain the first Asset for a twin stream Meter i.e. suppress any instances where there is a second record for an MPRN. 2. Rolling AQ updates – For the DDU file to not include any records relating to rolling AQ updates. | No |  |  |  | DNs | 21 Data flows and services to Network Operators 14 Provision of reporting services to Gas Transporters | DN | 1. Twin Stream Meters - Current DDS/DDU files have a MPRN as a unique identifier, Twin Stream Meter changes introduce the possibility of multiple records for the same MPRN, which DN systems cannot deal with. 2. Rolling AQ updates – The DDU file will contain any change in AQ due to the ‘rolling AQ’ process, these will all become effective on the 1st of the month which will result in an exceptionally large DDU file on that day. DN systems would struggle to process these files in a timely manner. | Open | CP Available (CDSP Proposed R1.1) | NA | TBP |  | High pending discussions with all Networks | Similar to serial number 13 | ACTION 28/06/17: Awaiting an outcome from the DN discussions | ChMC to review and agree prioritisation proposed by SDG on 12th July
15 |  | UKLP152 | Change to processing ONJOB/ONUPD where existence of a Read marked Suspect as one of the latest activities | 03/05/2017 - Change added to CDB | Market Driven | RETRO | A requirement to amend the validation check framework (VCF) logic in current RGMA functionality in SAP-ISU to include an additional Read Type (suspect Reads) validation for checking suitability to process ONJOB/ONUPD across sites of all class types. Currently plot address is captured inappropriately in building name. | No |  |  |  | Shippers | 1 Manage supply point registration 5 Metered volume and quantity 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence | PNUNC | The change is required to support the full functionality of RETRO. | Open | Proposed for Bubbling Under | RETRO | TBP |  | High | Defer awaiting ongoing RAASP discussions. These are requirements added on since RETRO was deferred so will need assessing at a later date. | NA | NA
16 |  | UKLP154 | RETRO Updates - Suspecting Reads following Asset Attribute Update | 03/05/2017 - Change added to CDB | Market Driven | RETRO | A requirement to have a consistent approach to the treatment of Reads, being all Reads recorded are marked ‘suspect’ and it will be Shippers responsibility to either replace Reads or submit a latest Reading to trigger reconciliation and generate the adjustment to charges. | No |  |  |  | Shippers | 1 Manage supply point registration 5 Metered volume and quantity 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence | PNUNC | This change is required as it is simpler for SAP following a RETRO update for a billable Meter Asset attribute. This will produce more accurate and robust Read data. | Open | Proposed for Bubbling Under | RETRO | TBP |  | High | Defer awaiting ongoing RAASP discussions. These are requirements added on since RETRO was deferred so will need assessing at a later date. | NA | NA
17 |  | UKLP155 | RETRO Updates - Notifying of Suspect Reads | 03/05/2017 - Change added to CDB | Market Driven | RETRO | A requirement to issue notification of all Reads (the Registered User only) marked ‘Suspect’ | No |  |  |  | Shippers | 5 Metered volume and quantity 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence | PNUNC | In order the Shipper can establish the Reads that are now suspect and can re-assess the Reads and replace where necessary. | Open | Proposed for Bubbling Under | RETRO | TBP |  | High | Defer awaiting ongoing RAASP discussions. These are requirements added on since RETRO was deferred so will need assessing at a later date. | NA | NA
18 | XRN4289 | UKLP159 | Document Archival in ILM | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | A requirement to archive historical transactional (invoicing and supporting) files, dating back up to 7 years prior to Go-Live date. | No |  |  | CR prioritised at DSC Meeting 10/05/17 Score given = High | Xoserve | To Be Determined | UKLP | This information may be required by Shippers and Xoserve has a legal obligation to provide this info upon request. The files will be captured from tapes by for offline archival into the ILM Informatica system that is part of the UK Link Solution Design being implemented on the 01st June 2017. | Open | Proposed for Bubbling Under | NA | High | 2017-05-10 | High | Archiving for Xoserve, ChMC set the priority as high however there is internal discussions at Xoserve about this change and amending the 'base solution' Historical data has been bought out of legacy UK Link. Users feel archiving is important. A concern was raised about storage of UK Link and how long the archiving can be delayed without UK Link system running out of space and performance being impacted | ACTION 28/06/17: Xoserve to provide additional information for example how long can the system cope without archiving | SDG 10th July
19 |  | UKLP162 | Addition of Daily LDZ Unidentified Gas (UG) to National Grid Operational Data Services | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement to make daily Unidentified Gas (UG) as calculated during daily Nominations and Allocations at LDZ level available to Shippers on National Grid’s Operational Data service. | No |  |  |  | NTS | 18 Provision of user reports and information | UKLP | Publication of this information has been requested repeatedly in the UNC Demand Estimation Sub-Committee meetings. | Open | Proposed for Bubbling Under | NA | TBP |  | Medium | Was raised a considerable period of time ago. One User expressed that people in their organisation were keen for this to progress | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
20 |  | UKLP189 | Transfer Reading following a RETRO update | 03/05/2017 - Change added to CDB | Market Driven | RETRO | A requirement to review the current process as it has a huge customer satisfaction impact for end consumers as their ending with old and starting with new Supplier Readings could be different. | No |  |  |  | Shippers | 5 Metered volume and quantity | PNUNC | The SSP Shippers in PNUNC did not agree with the UKLP design, this has a huge customer satisfaction impact for end consumers as their ending with old and starting with new Supplier Readings could be different. | Open | Proposed for Bubbling Under | RETRO | TBP |  | High | Defer awaiting ongoing RAASP discussions. These are requirements added on since RETRO was deferred so will need assessing at a later date. | NA | NA
21 |  | UKLP192 | Impact Assessment on changes to Market Intelligence report and Change of Supplier reporting suite ahead of OFGEM RFI | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement for changes to the Market Intelligence report and Change of Supplier reporting suite. No requirement to provide these reports. Central switching service will provide these reports into the future. | No |  |  | OFGEM need to instruct the Networks to update a suite of reports after Xoserve provide the delivery timescales. | Xoserve |  | OFGEM | A formal Request for Information (RFI) will be issued to the Gas Transporters by OFGEM - tying into Gas Transporter license condition 34A – Provision of Data to the Regulator. OFGEMs driver is to have these reports delivered as soon as possible, however they are aware of our UKLP commitments and understand that a realistic date of delivery will need to be specified by Xoserve. The purpose of conducting the feasibility assessment is to manage OFGEMs expectations on that front and to determine whether any short term measures can be delivered ahead of changes being implemented to the full reporting suite. | Open | Proposed for Bubbling Under | NA | TBP |  | High | License driven and OFGEM driven | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
22 | XRN4290 | UKLP194 | Billing History by all NTS capacity / commodity related charges (from Nexus implementation onwards) | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement to create an enduring solution for National Grid to receive the billing history data to feed into the analysis, that will be conducted as part of the Phase 4 and Charging Review (Gas).The data is required from Nexus Implementation date on an enduring basis (annual and monthly basis which is dependant on that particular report) via report/s which should have the flexibility to be run by a number of users (within Market Change Gas). | No |  |  | New CO to support enduring solution is required | DNs | 7 NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoices 21 Data flows and services to Network Operators | DN | Analysis of all charges is required to understand bookings and flows of all Shippers at all ASEPs and Exit Points. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Further information is required for this change. | ACTION 28/06/17: National Grid to take away to understand the requirements | SDG review in 3 months - 18th September 2017
23 | XRN4291 | UKLP197 | Addition of New fields from CMS being available in BW/IP reporting environment | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | Addition of new fields from CMS to Xoserve's SAP Business Warehouse to enable use in future reporting services. | No |  |  |  | Xoserve | 18 Provision of user reports and information 21 Data flows and services to Network Operators | UKLP | This change will allow the business to be able to deliver reporting requirements from the SAP Business Warehouse where there is a requirement identified to do so. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Part of CMS Consequential Change - data items to be available in BW to ensure reporting can be completed. Initially impacts Xoserve. External reports that may be requested will be incomplete until the data items are added. | ACTION 28/06/17: Xoserve and users to explore what the data items are and what they may feed - any commercial reports | SDG 10th July
24 | XRN4292 | UKLP198 | Ability to submit a Read taken at Meter inspection with Meter inspection update | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to include the submission of the Read along with the inspection date following a Meter inspection. | No |  |  |  | Shippers | 5 Metered volume and quantity | PNUNC | This change provides another route to supply a Read and ensure maximum Reads are recorded on the UK Link system. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Users felt that this was an unnecessary change to provide the Read on the Meter inspection date. The change is linking two processes which should not be linked. Xoserve suggested the original requirement was to increase the Reads onto the system. Users stated the inspection date should stand even whereby a Read is not submitted. This change creates complexities where a Read is rejected, and other complexities with Class 1 Reads. Users concerned about whether there is any benefit. Would also impact the file format. | ChMC to consider the proposal to close the change with no benefit and complexities. | ChMC to review and agree proposal to close the change by SDG on 12th July
25 | XRN4293 | UKLP202 | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to have maximum Reads loaded on the system, which results in more accurate AQ’s. | Yes | 432 | 1st June 17 | MOD 432 text - UNC G1.6.26 - No workaround this has been discussed with PNUNC and agreed can be resolved at a later date | Shippers | 5 Metered volume and quantity 6 Annual quantity, DM Supply Point and Offtake Rate Reviews | PNUNC | Following a Read being rejected as it failed the market breaker tolerance check, the User may raise an AQ correction, once the AQ has been updated. The Shippers have requested the ability to re-submit the Read that failed the market breaker tolerance for the correct date (original Read date) but validate the Read against the newly corrected AQ rather than the AQ that was Live as at the Read date. | Open | CP Available (CDSP Proposed) | NA | TBP |  | High | This is based on a rule that the Read submitted for an earlier date should validate against the AQ at that time. Presently validates on current AQ. The Read should be reflected on the AQ at the time. Users feel this should be about replacing a Read after an AQ correction and is not currently sufficient. Requires further work and development with regards to how to solution. Likely to cause file format changes. Is currently creating some impacts for Shipper Users but would like to develop the solution rather than implement as is. Can also impact on a CoS event as can impact opening Read scenarios. | ChMC to recommend a review group or technical sub committee to consider in more detail | ChMC - For consideration on 12th July.
26 | XRN4294 | UKLP203 | Amendment to U82 record to include the revised NTS optional tariff rate | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement file format change required to add the NTS Optional Tariff Rate. | No |  |  | A current workaround exists | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | PNUNC | The User will not have the new rate applicable when an optional tariff is switched on. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | There is a workaround in place whereby these values can be provided over the phone. Small numbers are impacted. May change over time if it becomes a bigger issue. | To be reviewed in 3 months time | SDG review in 3 months - 18th September 2017
27 | COR3995 | UKLP222 | Theft Risk Assessment Service Tip-off Hotline Data Provision – Enduring Solution | 03/05/2017 - Change added to CDB | Business Excellence | New Requirement | A requirement for an enduring solution for the Energy Theft Tip-Off Services provider to identify an MPRN for an address where they receive a tip-off/notification of a suspected theft of gas situation. Xoserve would provide a monthly report to the Energy Theft Tip-Off Services provider via a .csv file. | No |  |  | COR 3995 was submitted to deliver the report. However, as part of this change order they have developed an interim solution to support the change till the enduring solution is delivered. | DNs | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | UKLP | OFGEM have mandated Suppliers to develop a Theft Risk Assessment Service (TRAS), which includes Energy Theft Tip-Off Service (ETTOS). The requirements of the ETTOS stipulate access to data that will allow the ETTOS provider to correctly direct the information they receive to the relevant Supplier, and in cases where a correct address has been identified with no Supplier attached, the Transporter as a last resort. | Open | CP Available (CDSP Proposed) | NA | TBP |  | High | Question around the date of the service provision. The service has been offered, now there is a break in service until the enduring solution is provided. This is part of a license condition, the service may be impacted whilst this is not provided therefore this impacts all Users. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
28 | XRN4295 | UKLP223 | Allow for a capacity revision on a Seasonally Large Supply Point | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to support UNC code B4.9.2 - The current design does not allow for a capacity revision for a Seasonal Supply Point. | Yes | 432 | 1st June 17 | B4.9.5 (d) states a User can amend capacity at certain times via capacity revision. A User can submit a re-confirmation to revise capacity to fulfil the requirement. Extremely low volumes of MPRN's impacted. | Shippers | 6 Annual quantity, DM Supply Point and Offtake Rate Reviews | PNUNC | To ensure that the UK Link solution meets the obligations of UNC Modification 432. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Users can do a reconfirmation or capacity amendment at the start of a contract to workaround this. There are very small numbers however it is a breach in code. Any sites now cannot be amended until April 2018. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
29 | XRN4296 | UKLP225 | Change number of occurrences in the K13 record for SSMP’s | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to update Supplier Code to contain prospective Supplier and Shipper values(SUPPLIER SHORT CODE and SHIPPER SHORT CODE in K13 record (TRS/TRF file)). | No |  |  |  | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | UKLP | Upon a Shipper transfer if the incoming or outgoing registration is for a Shared Supply Meter Point(s) there is a requirement to send multiple K13 records to the User for each Sharing User. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Low numbers impacted. There is currently a manual workaround in place. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
30 | XRN4297 | UKLP226 | Provide the DMSP with the AQ in the O13 record on the GCC file | 03/05/2017 - Change added to CDB | Business Excellence | New Requirement | Requirements: 1. Provide the DMSP with the site AQ value in order they can accurately validate class 1 Readings prior to submission to Xoserve. 2. Trigger the GCC file following a ‘finalised ratchet’ to the DMSP. 3. Supply the MNEPOR value for any NTS data logged SMP’s | No |  |  |  | DMSP | 21 Data flows and services to Network Operators | UKLP | 1. In order for the DMSP to accurately validate a daily Reading they need to know the AQ of the SMP as the AQ bandings dictate the % tolerance amount to be applied for Read validation. The current GCC file does not contain any AQ information. 2. Provide the updated SOQ value in order the DMSP can carry out accurate Read validation. 3. To enable the DMSP to accurately validate the Read prior to submission to Xoserve. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Medium | Various elements to the change in terms of different trigger points. Users asked about the impacts, there is limited view of scale of the problem. May significantly reduce when DMs are moved from Class 1 if they do not hit the requirement to stay in Class 1. There was a question regarding whether DMSPs receive the calorific value. The DMSPs are going to be asked. Impact could be that more estimates are being created. | ACTION 28/06/17: Networks to enquire with DMPSs. DMSPs - to be consulted do they receive the CV? | SDG 10th July
31 |  | UKLP233 | Functional change to reflect data that has been nulled in output files provided to Shippers | 03/05/2017 - Change added to CDB | Business Excellence | New Requirement | A requirement to support nullified data. Shippers will not know of contact titles that are nulled by Xoserve as the return file provided to Shippers will contain the original information supplied by Shippers. | No |  |  |  | Shippers | 1 Manage supply point registration | UKLP | Shippers will not know of contact titles that are nulled by Xoserve as the return file provided to Shippers will contain the original information supplied by Shippers. It has been expressed by Shippers at UKLC that as the change has implications to Shippers (and consumers can be very insistent about how they wish to be addressed), that they would like to bridge the gap of any discrepancies. Furthermore approval of the current contact title list was conditional on the basis Shippers would be provided with a list of contact titles that have been nullified by UKLink systems | Open | Proposed for Bubbling Under | NA | TBP |  | Low | Shipper has the correct title within their systems, UK Link will hold a null value. Deemed low priority. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
32 | XRN4057 | UKLP244 | GDE Cashout – Daily Curtailment Volume (DCV) for Daily Metered sites | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | The changes include introduction of obligations on Distribution Networks (DNs) to supply specific information to NG Transmission in the event of a Gas Deficit Emergency (GDE). | No |  |  |  | DNs iGTs Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | DN | This change meets the obligations for DN's to provide NGGT with Supply specific information in the event of a GDE. | Open | CP Available (DSC Prioritised) | NA | Low | 2017-05-10 | Low | SDG confirmed low priority as prioritised by ChMC. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
33 | COR4097 | UKLP249 | Addition of new Vulnerable Customer Needs codes | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | An OFGEM lead requirement, their final consultation requires the new needs codes to be in use from 1st June 2017, this will be reiterated through license condition changes to Gas Transporter licences. | No |  |  | CR prioritised at DSC Meeting 10/05/17 Score given = High | DNs iGTs Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | OFGEM | To establish better sharing mechanisms for vulnerable customer data in order to align processes across both Gas and Electricity. | Open | CP Available (CDSP Proposed R1.1) | UKLP273 | High | 2017-05-10 | High | Still 3 choices on the table, the option that is selected may impact on the release. Both sending and receiving systems will have to be able to process new needs codes. SDG confirmed High priority as prioritised by ChMC. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
34 | XRN4299 | UKLP251 | Reports required under UNC TPD V16.1 in Nexus (reports required by MOD 520A) | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement for a number of reports. DNs are to provide a number of reports both to the industry in general and also to Performance Assurance Committee members. | No |  |  |  | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | BAU Change | Change Order has been raised to meet the reporting requirements as defined in MOD0520A | Open | CP Available (DSC Prioritised) | NA | High | 2017-05-10 | High | SDG confirmed High priority as prioritised by ChMC. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
35 | XRN4300 | UKLP256 | NDM Twin Stream Read Validation | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to support NDM twin stream and automated Read input validation process. | No |  |  | This is not breaching the code because we have a workaround in place, Xoserve will input the Meter Reads supplied by the registered User until such time as a fix is implemented. We are expecting extremely low volumes on this. | Shippers | 5 Metered volume and quantity | UKLP | This was a requirement with supporting rule that has not been implemented. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | There is a workaround in place. There are 20 twin streams. Most twin streams are currently in Class 1. The impacts for this are larger if the twin streams move into Class 4. To be reviewed following the movement from Class 1. | Review in 8-9 months | SDG review in 9 months - 19th March 2019
36 | XRN4301 | UKLP257 | Class 1 validation errors (NTS/teleMetered/CSO sites) | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | A requirement to support G1.5.2(a) that states what qualifies to be class 1. | No |  |  | This is not breaching the code because there is a workaround in place to ensure those impacted sites. | Shippers | 1 Manage supply point registration | UKLP | Nominations/Confirmations will incorrectly reject when sites are transferring ownership. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | All NTS sites reside in Class 1. The validation is looking for sites above 58.6million kWh. The rule needs to be added so the sites reside in Class 1 regardless of AQ. Expiry of 9 months, they could go through an AQ calculation and fall out of Class 1, the manual workaround will need to be completed again. | Review in 8-9 months | SDG review in 9 months - 19th March 2019
37 | XRN4302 | UKLP258 | Various File Format Changes identified in August 2016 | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | A requirement to change the structure and composition of the Unique Sites file format (e.g. additional field, optionality/allowable values etc.) to enable files to be issued and received. | No |  |  |  | DNs iGTs Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | UKLP | During testing of Unique Sites in Market Trials there were a number of functional differences highlighted between the file records and templates. In Market Trials several users have identified allowable values which they are using that were not in legacy files. These functional changes are identified as ‘Must Have’ changes and are required to enable files to be issued and received (without these changes files will fail). | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Workarounds are currently in place. 7 changes to the file formats, appear to be allowable values. 5 changes to the S75, 1 to the U80 and 1 change to the U82. There are not a high number of Unique Sites however the sites have large AQ. Users enquired whether the changes will result in testing being required across the industry. | ACTION 28/06/17: Xoserve to confirm the workaround | SDG 10th July
38 |  | UKLP262 | Change to RGMA validations for LI confirmations | 03/05/2017 - Change added to CDB | Business Excellence | New Requirement | A requirement to change Existing RGMA validation rules in legacy and new UK Link. | No |  |  |  | Shippers | 1 Manage supply point registration | UKLP | The amendment to the rules will allow for Asset updates to be recorded with the correct effective date in the register and allow for Xoserve to correctly bill Capacity and Commodity as set out in the UNC. | Open | Proposed for Bubbling Under | NA | TBP |  | High | Asset updates can be done at the status of CO at the earliest. This was trying to amend RGMA validations on a Greenfield site to install the Asset on the correct effective date to allow billing correctly as per UNC. This relates to first registration. This is different to RETRO. Users viewed it as high priority. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
39 | XRN4303 | UKLP267 | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | A requirement to adjust file format that allows the User to set ‘n’ when providing site visit Reads via the SFN file, this indicates that, following site visit, the Reads taken have not fixed the fault. | No |  |  |  | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | UKLP | Ensures that Shippers can set a value of N when providing Site Visit details within the SFN file that meets the requirement specified. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | File format change to remove the value of 'n' as an allowable value. Users will not be submitting a Read if the fault has not been fixed - it is illogical. Question whether it is causing an issue. Question whether the field is valid as currently the allowable values are Y, N or blank. | ACTION 28/06/17: Xoserve to review the file to see if there are any conditional mandatory conditions in the file for the impacts of removing N | SDG review in 3 months - 18th September 2017
40 | XRN4304 | UKLP270 | Amend referral rules for class 2 smaller LSP’s | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to accept Class 2 Meter Points and to be a configurable upper value with the ability to increase/decrease if required. There could be a significant number of Class 2 Meter Points, some of which will have lower AQ/SOQ value (LSP’s that still require nomination). | No |  |  |  | DNs | 1 Manage supply point registration | UKLP | There could be a significant number of Class 2 Meter Points, some of which will have lower AQ/SOQ value (LSP’s that still require nomination), however the DN’s had confirmed they did not wish these MPRN’s to be referred as the loads were not significant and would not pose any safety issues on the network so were not required to approve requested loads. If all were to refer this could create a large volume of work clearing referrals | Open | CP Available (CDSP Proposed) | UKLP272 | TBP |  | Medium | Impacts both DNs and Shippers as adds 10 days to the nomination process. Impacts on consumers also. Impact is limited to Class 2, currently low movement but going forward movement is likely to increase. The current threshold is 73,200kWh. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
41 | XRN4305 | UKLP271 | Work Items unique Task ID request | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | A requirement in SAP to generate unique Task ID. There are several types of Work Items have the same Task ID which makes it difficult to predict volumetric and ensure that they are completed in a timely and correct manner. | No |  |  |  | Xoserve | To Be Determined | UKLP | During Market Trials we have identified that there are several different types of Work Items that have the same Task ID which makes it difficult to predict volumetrics and ensure that they are completed in a timely and correct manner. Having a unique identifier for the Work Items types will also assist with the design documentations and ensuring that the relevant detail is added to the centralised information repository. | Open | CP Available (CDSP Proposed) | NA | TBP |  | low | Exceptions are categorised as one at present, we would like to separate them between technical exceptions and business process exceptions. Xoserve to revisit to see whether it is required as exceptions have been lower than anticipated. | ACTION 28/06/17: Xoserve to review the change to determine if it is still required | SDG 10th July
42 | XRN4306 | UKLP272 | Capacity referral raised in error following Nomination | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to amend rules so NOT to issue a referral in the below scenario. SAP is referring a nomination to DN’s when the User has requested prevailing SOQ/SHQ values but the SOQ/SHQ is >16 /<24. In this scenario no referral is required and an offer should be issued to User (providing all other validations are passed). | No |  |  |  | DNs Shippers | 1 Manage supply point registration | UKLP | There will be increase in the number of referrals to DN’s, this will increase workload to the DN’s (may have to consider a workaround in the interim) and will also slow the response time for providing an Offer to the Shipper. | Open | CP Available (CDSP Proposed R1.1) | UKLP270 | High | 2017-06-07 | High | Legacy system did not refer whereas this is occurring in UKLP. SDG confirmed as high priority as confirmed by ChMC. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
43 |  | UKLP273 | PSR requirements – Vulnerable Customer data requirements | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirements to be in place to assist customers in vulnerable situations; - Aligned vulnerable customer needs codes between Gas and electricity - Mapping of existing vulnerable customer needs code to new vulnerable customer needs code | No |  |  |  | DNs iGTs Shippers | 9 User admission and termination | OFGEM | OFGEM are driving an initiative that is looking at improvements to the Priority Services Register (PSR) and part of this relates to Vulnerable customers. The industry already communicates data around the vulnerability of end consumers via the CNF and CNC files to Shippers and EDL / EQL to Transporters and the EWS file to EMWS. Suppliers and Transporters license conditions ensure that vulnerable customer data is recorded. The OFGEM Solution implementation is currently under review at 1st June 2017 or 3 months after PNID. To advise OFGEM accordingly it is critical this change request is prioritised and requirements are understood and communicated to the Industry. | Open | Proposed for Bubbling Under | UKLP249 | High | 2017-06-07 | High | One CR will be raised once the final solution is confirmed. SDG confirmed as high priority as confirmed by ChMC. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
44 |  | UKLP276 | iGT IIL & IDL files splitting - manual workaround provided in Market Trials into Production post go live | 03/05/2017 - Change added to CDB | Service Introduction | New Requirement | A requirement iGTs would like IIL & IDL files to split, the total file into its daily components. SAP produces a single “catch up” file covering all the “down” days. | No |  |  |  | iGTs | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | UKLP | Xoserve had to carry out the process of splitting the files in Market Trials as IDL files got stuck a number of times. We had to have a catch up process to ensure there data was aligned to ours. As no process had been defined we discussed with IGTs the best way to complete this catch up. The main concerns from the IGTs is that if this happens again in Production no formal catch up process has been agreed. They want assurance prior to Go Live that if this issue is to occur there is an agreed process in place to rectify the situation, whether it is part manual work or fully automated. | Open | Proposed for Bubbling Under | NA | TBP |  | Remove | IIL was fixed and implemented as a one off on go-live. There are a few issues with IDL as on some occasions several files are issued due to a batch timing issue. | ACTION 28/06/17: Agree to remove with the iGTs | ChMC to review and agree proposal to close the change by SDG on 12th July
45 |  | UKLP277 | Treatment of values in the CDR | 03/05/2017 - Change added to CDB | Service Sustaining | New Requirement | A requirement to define allowable values for the functional data items (lower level of detail) within the Connection and Disconnection Suite of jobs (this includes the CDN, CDR and CDJ (or CDJOB). | No |  |  |  | Shippers | 1 Manage supply point registration | PNUNC | Understanding is that the majority of Users don’t use the CDR within their processing as it merely indicates that the Transporter has discharged the obligation to store the data. I suspect that this is why this error has laid undetected for as long as it has. Once we identify an error in the Code we would normally resolve this, but given the level of utilisation of this file, and the level of activity that we have at this point in time in the Legacy system was to support Nexus Go Live. | Open | Proposed for Bubbling Under | NA | TBP |  | Low | To do with anticipated values. A 'U' is being provided in a field it is not meant to be. | ACTION 28/06/17: Users to see if there are any system impacts. | SDG 10th July
46 | XRN4307 | UKLP279 | Pending capacity amendment with Ratchet | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to for current functionality to take into consideration a pending capacity amendment when a ratchet occurs. The incorrect (lower value) could go live resulting in further ratchets that should not be applied. | Yes |  |  | The code reference is B4.7G5. There is no workaround in place therefore it is required to be implemented in release 1.1 as ratchets run from 1st October each year. | Shippers | 1 Manage supply point registration | UKLP | The incorrect (lower value) could go live resulting in further ratchets that should not be applied. | Open | CP Available (CDSP Proposed R1.1) | NA | Medium | 2017-06-07 | Medium | SDG confirmed as medium priority as confirmed by ChMC | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
47 | XRN4308 | UKLP280 | Various File Format changes identified in December 2016 | 03/05/2017 - Change added to CDB | Service Sustaining | New Requirement | A requirement for File Format description and system changes that have been identified and recorded to be reviewed post Go Live. | No |  |  |  | DNs iGTs Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | UKLP | There are a number of Should Have/Could Have File Format description and system changes that have been identified and recorded to be reviewed post Go Live. These changes have been considered as not critical for Go Live (Must Have) although there are a few Must Have changes that were discussed and deferred to PGL through the SDG. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Will be changes to file formats, considered to be 'nice to haves' - identified as 'should have' and 'could have' changes through the programme. Suggestion to check the list of changes against the defects. | ACTION 28/06/17: Xoserve to check the list of defects against changes with file formats | SDG review in 3 months - 18th September 2017
48 |  | UKLP281 | DN Sales (Outbound Services) Requirements for UKLP enduring solution | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement for an enduring solution to split invoicing automated without manual intervention is required by 1 year after UKLP Go Live. | No |  |  | There was a project COR4043 that delivered the interim solution however it was agreed that Beverly Viney will be raising a separate Change Proposal for the enduring solution. | DNs Shippers NTS | 7 NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoices | DN | Xoserve will have implemented an interim solution in new UK Link and will be providing the invoicing service to both NGGT and Cadent Gas. It is not feasible to continue with manual intervention on an enduring basis and therefore an enduring solution is required | Open | Proposed for Bubbling Under | NA | TBP |  | High | Currently a manually intensive workaround for Xoserve. Impacts all Users | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
49 | XRN4309 | UKLP287 | Back billing for domestic (SSP) sites needs to be reflect the correct adjustment start date | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to ensure correct adjustment period is billed for SSP sites as part of the back billing (GSR site visit) process. | No |  |  |  | Shippers | 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-Hoc Adjustment and Energy Balancing Invoices | UKLP | Change required to ensure correct adjustment period is billed for SSP sites as part of the Back Billing (GSR site visit) process. | Open | CP Available (CDSP Proposed) | UKLP289 | TBP |  | Low | Adjustment period to be aligned to when we originally ceased billing. Relevant to SSP. Billing from the stop commodity date not the Asset removal date. Ensures billing correctly. Question whether there is currently a workaround. Small amount of pots currently impacted. | ACTION 28/06/17: additional clarity to be provided on the CR, potentially a diagram. ACTION 28/06/17: is there a workaround after the event | SDG 10th July
50 | XRN4310 | UKLP289 | Class 4 CSEPS Reconciliation Variance Identification | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to ensure correct reconciliation billing following a CSEPs Project change. | Yes |  |  | Breach of UNC section S. this was deemed to be a low priority change as the likelihood of only a CSEPs grid change is low. | iGTs Shippers | To Be Determined | UKLP | The change is required to ensure correct reconciliation billing following a CSEPs Project change | Open | CP Available (CDSP Proposed) | UKLP287 | TBP |  | Medium | As it is a breach of code within the prioritisation approach it is a medium priority | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
51 | COR2831.5 | UKLP292 | Changes to the upper parameter of the XDO partial refresh file | 03/05/2017 - Change added to CDB | Business Excellence | New Requirement | A requirement to ensure that the obligations in the Smart Energy Code are fully met. At present a request greater than 30k MPRNs can not be met. The SEC does not stipulate a size restriction and therefore the DCC / DSP can submit a partial request of any size up to a full portfolio. | No |  |  | As part of COR2831.5 this requirement was supposed to be delivered but it was deferred and it needs to be considered for the DSC prioritisation. | DCC | To Be Determined | Smart | To meet the requirements outlined in Smart Energy Code and the subsidiary testing documents. | Open | CP Available (CDSP Proposed) | NA | TBP |  | High | Ability for Xoserve to refresh the data for the DCC. The DCC can request to refresh any data subset. Creates a breach for Networks, there is an efficient workaround in place. Will become higher due to smart Meter roll out. A refresh is going to occur to include the iGT data set following Nexus go-live to align to what iGTs have previously sent to DCC. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
52 | XRN4319 | UKLP293 | Splitting of the DXI inbound and DXR outbound file from the DCC. | 03/05/2017 - Change added to CDB | Business Excellence | New Requirement | A requirement to ensure that the treatment of the DXI and DXR files meets the obligations in the Smart Energy Code. The SEC does not stipulate a size restriction and therefore the DCC / DSP can submit a file of any size. | No |  |  | As part of COR2831.5 this requirement was supposed to be delivered but it was deferred and it needs to be considered for the DSC prioritisation. | DCC | To Be Determined | Smart | The change is required to ensure that the treatment of the DXI and DXR files meets the obligations in the Smart Energy Code. The SEC does not stipulate a size restriction and therefore the DCC / DSP can submit a file of any size | Open | CP Available (CDSP Proposed) | NA | TBP |  | Consensus is Medium, One DN had a recommendation of high | Cap on size of files into Xoserve. It is a daily file received by Xoserve with data on 250,000-300,000 MPRNs. Multiple files may need to be received by Xoserve. The DCC are being constrained by the SAP limits. Concern that the DCC could deprioritise the activity and not complete the workaround. Viewed as a compliance issue but not urgent due to low Smart Meter numbers. | ACTION 1 28/06/17: Xoserve to establish how hard it is to fix, to help establish when it will become an issue. ACTION 2 28/06/17: Review as Smart Meters increase. | ACTION 1: SDG 10th July. ACTION 2: SDG review in 3 months - 18th September 2017
53 | XRN4311 | UKLP300 | Unique Sites – Adding profiles | 03/05/2017 - Change added to CDB | Business Excellence | Continuous Improvement | A requirement to enable the correct profiles to be added automatically and not manually. | No |  |  |  | Xoserve | To Be Determined | UKLP | During Unique Sites Testing in Market Trials it was identified that the setting up of profiles was not automated and required a User to manually update each type before the energies could be loaded on a daily bases. The activities are complex and can only be carried out on Move in Date due to SAP ISU functionality not setting up the installations for the set up before this date. This activity is required to be completed on D Move in Date. As we do not operate a 365 day working week, those transactions with a Move in Date on a non-working day will require the re-run of the Read allocation process to update the energies and sent the relevant details to Gemini once the profiles have been added on the next working Day. These functional changes are identified as ‘Must Have’ changes and are required to enable the correct profiles to be added automatically and not manually. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Internal to Xoserve, no external impacts. Oversight in design, creates a manual workaround. Occurs with Unique Sites, Class 1 and Class 2 sites. Numbers are currently low and not occurring on a daily basis. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
54 | XRN4312 | UKLP301 | Annual Production and notification of LIS 3 years Read | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | A Read requirement to be generated each year for any Meter Point that do not have a Read recorded post LIS -3 years to be loaded by 1st April each year. This Read is required to be issued to, and identifiable by, the registered User as it will be used for Reconciliation purposes. | No |  |  |  | Shippers Xoserve | To Be Determined | UKLP | A Read is required to be generated each year for any Meter Point that do not have a Read recorded post LIS -3 years to be loaded by 1st April each year. This Read is required to be issued to, and identifiable by, the registered User as it will be used for Reconciliation purposes. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Linked to modification 0576, this is the enduring solution on how we communicate the Reads. Currently there is a workaround whereby the Reads can be communicated via email. This is not ideal however is workable. | ACTION 28/06/17: Xoserve to establish how difficult the workaround is, the resource internally | SDG 10th July
55 | XRN4313 | UKLP305 | MOD 431 – Validations against file header and data within records | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to validate that; the recipient within the file header is the same as the Shipper short code within records, where any discrepancies are found – these should be rejected. | Yes | 431 |  | We would be in breach of code until this is fixed. No identified workaround, required to issue out Nov 17 | Shippers | To Be Determined | UKLP | The change is required to remove the possibility of Xoserve: 1. Providing information to a Shipper (as within the record) which actually has not provided the data, which could be a data control issue. 2. Providing information to a Shipper (as within the file header) which has provided the data, but this would not align with the monitoring undertaken as part of the process and could lead to force confirmations being undertaken against a Shipper who has not been notified as per UNC requirements. | Open | CP Available (CDSP Proposed R1.1) | NA | High | 2017-06-07 | High | Breach and no workaround in place. Users requested confirmation that this issue is limited to the SPI and SPO files. This was confirmed. SDG confirmed as high priority as prioritised by ChMC | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
56 | XRN4314 | UKLP306 | Amend functionality to send GCC file to DMSP when Class 1 Confirmation Requests Lapse due to objection. | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A Requirement for DMSP to be informed via GCC when the Class 1 confirmation request is cancelled | No |  |  |  | DMSP | To Be Determined | UKLP | A DMSP is informed via GCC when the Class 1 confirmation request is cancelled so we also need to include the scenario when the site is lapsed due to objection. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | GCC flows to the DMSP at confirmation stage, this confirmation could be cancelled for up to 2 days following this point. There is no way for the DMSP to be informed that the confirmation is cancelled or lapses. The time is to be changed to confirmation acceptance. There is a workaround with a monthly report provided to the DMSP's. Low volumes. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
57 |  | UKLP307 | Proposal for process improvements for Supporting Information files (AML,COI and CZI) | 03/05/2017 - Change added to CDB | Business Excellence | Continuous Improvement | A requirement to the supporting information program to enable the simulation of the supporting information files before the actual generation and submission of these supporting information files for delivery. | No |  |  |  | Shippers | To Be Determined | UKLP | A requirement to the supporting information program to enable the simulation of the supporting information files before the actual generation and submission of these supporting information files for delivery. | Open | Proposed for Bubbling Under | NA | TBP |  | Medium | Users would like the secondary supporting invoicing information files to be issued sooner. If this enables this to happen, it is supported | ACTION 28/06/17: Xoserve to provide further information on this Change | SDG 10th July
58 | XRN4315 | UKLP309 | UMR Hierarchy Amendment in AMT | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | A requirement to change file format hierarchy. The UMR file U01 record is currently registered in AMT as having unlimited occurrences – this need to be changed to 300,000 occurrences as per the approved file format hierarchy. | No |  |  |  | Shippers | To Be Determined | UKLP | If a Shipper submits 300,001 records in UMR record will not be rejected for not following hierarchy record limit, instead the file will be accepted and processed – this will have direct performance impacts on both MF and SAP PO. Considering the number of files (~ 250 files) submitted every day, the number of occurrences have to be changed to protect system performance and also align to the approved file format. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Agreed 300,000 occurrence limits on these files. Files above 300,000 records can have impacts on system performance. Impacts to Xoserve systems also impact User systems. | ACTION 28/06/17: Xoserve to publish UMR hierarchy with occurrences, current version is legacy without occurrences ACTION: Xoserve to check how many files are coming in above this threshold | SDG review in 3 months - 18th September 2017
59 | XRN4252 |  | DES Access Restriction and Audit | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement to support the Competition and Markets Authority (CMA) order to provide data to Price comparison Websites (PCWs) to facilitate faster switching. | No |  |  |  | Shippers | To Be Determined | BAU Change | A requirement to support the Competition and Markets Authority (CMA) order to provide data to Price comparison Websites (PCWs) to facilitate faster switching. | Closed | CP Available (DSC Prioritised) | NA | High | 2017-05-10 | Remove | Consideration to remove the change with ChMC approval as the solution is no longer valid. | NA | ChMC to review and agree proposal to close the change by SDG on 12th July
60 | XRN4248 |  | Quarterly smart Metering reporting for HSE and DNs | 03/05/2017 - Change added to CDB | Business Excellence | Continuous Improvement | A requirement to produce a quarterly report to be provided as a national report to the HS&E and as a DN level report to each network summarising Meter exchanges and installations. | No |  |  |  | DNs | To Be Determined | BAU Change | The HS&E has requested reporting to enable better monitoring of the smart Meter roll-out, in particular to enable them to monitor for geographic hot-spots that they can match to RIDDOR reports associated with Meter installations. | Open | CP Available (DSC Prioritised) | NA | High | 2017-05-10 | High | SDG confirmed as high priority as confirmed by ChMC. | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
61 | XRN4317 | UKLP317 | Sybase NLS Solution Design Gap | 03/05/2017 - Change added to CDB | Service Sustaining | Service Sustaining | A requirement to support the Sybase solution and NLS data. The design of the Sybase solution based on the business requirements and the BW capability delivered, a solution design gap has been identified where the use of reports through the Universe reporting layer capability are unable to Read NLS data. | No |  |  |  | Xoserve | To Be Determined | UKLP | This is solution design gap and the change is required to remove the issue with reports accessing the NLS Sybase data. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Additional information is required | ACTION 28/06/17: Xoserve to provide additional information | SDG 10th July
62 | XRN4285 | UKLP132A | Delivery via Automated Integration Solution for all IP reports from SAP BW | 03/05/2017 - Change added to CDB | Business Excellence | Continuous Improvement | A requirement that all external reports produced from the SAP BW solution would be submitted to Users via an automated delivery mechanism. | No |  |  |  | Xoserve | To Be Determined | UKLP | The Xoserve Information Security Forum (ISF) have an action on the UKLP to deliver this requirement to reduce or remove the risk of data compliance breaches where information is at risk of being submitted incorrectly to external market participants. By delivering the automated delivery of reports to external market participants it will remove efforts required by Xoserve resources to have to manually apply processes and procedures (on a daily, weekly, monthly, quarterly, yearly basis) of which provides financial benefits in not having to do so. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | Additional information is required, Users would like further information - are they over the I'X are they still emails, how is security realised? | ACTION 28/06/17: Xoserve to provide additional information | SDG 10th July
63 | XRN4316 | UKLP315 | Meter Point Details Report & Sector Breakdown Report | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to develop two reports to validate the amendment invoices. 1. Meter Point Details Report 2. Sector Breakdown Report | No |  |  |  | Xoserve | To Be Determined | UKLP | This is a design gap identified as currently under the new design there is no process to validate the amendment invoice. | Open | CP Available (CDSP Proposed) | NA | TBP |  | Low | 2 reports to aid validation, further information is required. | ACTION 28/06/17: Xoserve to confirm how much impact does this have? Does this impact the second level supporting information files? | SDG 10th July
64 |  | UKLP319 | Delivery of RETRO | 03/05/2017 - Change added to CDB | Market Driven | RETRO | A requirement to support the delivery of MOD 434 into the UK Link Solution Design. | No |  |  | MOD 573 - Sets implementation date 1st October 2017 | All | To Be Determined | UKLP | The change is required to support the full functionality of RETRO. | Open | Proposed for Bubbling Under | RETRO | TBP |  | High | Defer awaiting ongoing RAASP discussions. These are requirements added on since RETRO was deferred so will need assessing | NA | NA
65 | COR3283 |  | Recording DN Siteworks | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement to receive Network connection(s) reference numbers and the ability to store these reference numbers in a central system. | No |  |  |  | DNs | To Be Determined | BAU Change | Improving transparency of MPRN creation history and also improving efficiency of capacity referral requests. | Open | CP Available (DSC Prioritised) | NA | Low | 2017-05-10 | Low | SDG confirmed low priority as prioritised by ChMC | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
66 | COR3386 |  | New DN role for CMS | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement to create a new role that includes all activities that can be undertaken within DNs to facilitate more efficient working practices. | No |  |  |  | DNs | To Be Determined | BAU Change | At present Network role does not include all activities that are carried out within the DNs requiring some individuals needing multiple accounts to access CMS for different work streams. This CR is to facilitate more efficient working practices. | Open | CP Available (DSC Prioritised) | NA | Low | 2017-05-10 | Low | SDG confirmed low priority as prioritised by ChMC | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
67 | COR3287 |  | MOD 455s - updating of Meter Asset information by the transporter | 03/05/2017 - Change added to CDB | Market Driven | New Requirement | A requirement to develop a proposal to update Sites and Meters with Meter Asset details as per MOD455S. | No |  |  |  | DNs | To Be Determined | BAU Change | To meet the requirements specified in UNC Modification Proposal 0455S. | Open | CP Available (DSC Prioritised) | NA | Medium | 2017-05-10 | Medium | SDG confirmed medium priority as prioritised by ChMC | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
68 | XRN4318 | UKLP325 | Annual shrinkage submission (.ORD ) received from Networks is not getting apportioned correctly when the adjustment period is spanning across Nexus Go live date (01-June-2017) | 03/05/2017 - Change added to CDB | Service Sustaining | Design Gap | A requirement to correct the smearing process for Annual shrinkage in SAP because the current design is considering the variance period as 6 months and this will not work as expected with the new Go live date as 01-June-2017. If the error persists it will result in incorrect charges present in the amendment invoice (AMS) and will have financial impacts to Networks revenue. | No |  |  |  | DNs | To Be Determined | UKLP | Currently the smearing process for Annual shrinkage process in SAP is designed to consider the variance period as 6 months and will not work as expected from the UKLP Go Live date (01-June-17). This will result in incorrect charges present in the amendment invoice (AMS) and will have financial impacts to Networks revenue. | Open | CP Available (CDSP Proposed) | NA | TBP |  | High | Users feel that impacted parties should be extended as it is likely to impact more than DNs. Concern re financial implications. | ACTION 28/06/17: Xoserve to provide further information is required on this change | SDG 10th July
69 |  | UKLP294 | BEIS_Consumption Data | 28/06/2017 - Change added to CDB | Service Sustaining | New Requirement | A requirement to provide a report to the BEIS – Department of Business, Energy & Industrial Strategy (formerly DECC). They need to receive a full portfolio report of all Meter Points present on Xoserve systems following completion of AQ Review each year via Report DTIRP10Ss. This fulfils an annual requirement of the Networks under the Statistics of Trade Act 1947. The date for delivery of the full report details to BEIS is approximately Friday 20th October 2017 | No |  |  | This change may be potentially required for R1.1 but it needs to be agreed by ChMC. Marking this change as 'Proposed for Bubbling Under' until it is agreed by ChMC. |  |  |  | This report is produced in Legacy as part of the AQ Review Process, and will still be required post UK Link Go Live. There have been no transition arrangements to migrate this report into the UKLR Project. | Open | NA | TBP |  | High |  |  | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July
70 |  | UKLP174 | MOD432 incorrectly removed M3.7.3 & M3.7.4 revised Meter Read to be re-instated in UNC and the associated process | 28/06/2017 - Change added to CDB | Service Sustaining | New Requirement | A requirement to reinstate the process defined in the legal text that was removed in error. It refers to M3.7.3 & M3.7.4 revised Meter Read to be re-instated in UNC and the associated process | No |  |  | Based on a discussion in SDG it was recommended that this change be added into the Change Demand Backlog. Marking this change as 'Proposed for Bubbling Under' until it is agreed by ChMC. |  |  |  | This was removed in error and Shippers have confirmed they still require this functionality | Open | NA | TBP |  | Medium |  |  | NA | ChMC to review and agree prioritisation proposed by SDG on 12th July

## Sheet1 (hidden)
Count of Change Request Title | Column Labels
CDSP Proposed | High | Low | Medium | TBP | Grand Total
No | 6 | 5 | 2 | 14 | 27
Yes |  |  |  | 33 | 33
Yes - 1.1 | 5 |  | 1 | 2 | 8
Grand Total | 11 | 5 | 3 | 49 | 68