## PAC Issue Register
Performance Assurance Committee (PAC): Issue Register (as at 06 August 2018)
Issue Ref. | Issue | Background | Issue Originator | Date Created | Status | Priority for Discussion (H/M/L) | Status Date | Status Summary/Action taken | Next Review
PAC 009 | Data quality and issues with the submission of readings result in higher levels and fluctuations in unidentified gas | The UIG process has changed since Project Nexus was delivered. In this time there have been fluctuations in the UIG values see across LDZs. In addition the levels of UIG are higher than anticipated | PAC | 2017-10-10 | Live | High | 2018-08-06 | PAC notes the IA has closed for Urgent Modification 0642, 0642A and 0643 PAC also notes that the Authority expects the AUGE, DESC and PAC to play a role in resolving the ongoing UIG issues. PAC notes that Urgent Modification 0658 has been implemented and that establishment of the task force should allow for the development of options and solutions. | 2018-10-09
PAC 010 | Product Class 2 and 3 faiure to submit meter readings | A number if sites have been transferred into Product Classes 2 and 3 from other Product Classes and have failed to either provide or provide frequent meter reads. This is creating an issues in terms of short term UIG allocation. | PAC | 2018-03-05 | Live | High | 2018-08-06 | A draft Modification sponsored by PAC is in development with an aim of submitting the proposals to the July/August Panel. PAC to follow progress of the modification and consider the issue at a later date. | 2018-10-09

## Closed Issues
Performance Assurance Committee (PAC): Closed Issues
Issue Ref. | Issue | Background | Issue Originator | Date Created | Status | Priority for Discussion (H/M/L) | Status Date | Status Summary/Action taken | Next Review
PAC001 | Performance Assurance Framework Document: Document 5 - Provision and Signing of Letters of Agreement and/or Confidentiality for Members and Alternates | Initial letters are more about compliance with Code and not about maintaining confidentiality of data. | PAC | 2016-06-29 | Closed | Low | 2016-10-10 | DNOs were requested to develop a Confidentiality Agreement for incorporation into Document 5 and review the existing content of Document 5 and the definition (page 5, Section 1). In particular to consider whether an indemnity of some form is required for PAC Members and/or PAFA Drafting included in v1.5, to be agreed in Jan 17 | Completed at Jan 17 meeting
PAC002 | Performance Assurance Framework (PAF) Document: Document 4 (Page 28) - Performance Assurance Administrator Scope: Part 1 General; paragraph 5 - Agreeing the PAFA Scope, cost estimates and cost reporting - timecales/percentages at paragraph 5 are currently in square brackets and need to be agreed | Agreeing such matters ahead of a forthcoming gas year will become more relevant for year 2 onwards, since year 1 is more about engaging a PAFA, gathering data and initial risk identification. | PAC | 2016-06-29 | Closed | Low | 2018-02-05 | Review against proposed workplan and and industry consultation document. | Closed
PAC003 | Engagement of Specialist Experts - Future requirement to procure ad hoc independent expertise to support areas of a specialist nature | It is recognised that expert input and/or analysis will be required and PAC needs to decide if it wants a direct engagement relationship or via PAFA. Initial thoughts are that PAC needs to be the effective 'client'. | Ofgem (JD) | 2016-06-29 | Closed | Medium | 2016-10-10 | To be considered - possible creation of a standing Register of Independent Experts (similar to OC ITE?). Confidentiality? Nomination? Areas of expertise? Skillsets? Funding? Wording agreed at Oct 16 PAC | Completed at Oct meeting
PAC004 | Annual Industry Workplan and Budget Statement | An annual statement from PAC to the industry about the work areas and likely budget would be a positive move - would allow some consultation/feedback and understanding of the costs to be incurred (and budgeted for). | Chairperson (LJ) | 2016-06-29 | Closed | Low | 2016-10-10 | Noted that a similar arrangement existed in the equivalernt electricity industry arrangements. To be included in the next iteration of the Framework Document - action PAC1003. | Completed at Jan 17 meeting
PAC005 | User Representative appointment rules | The Framework document needs to be amended to accommodate differing situations of nominees; directly employed or otherwise. This is not needed until the 2017/18 gas year User Representation process - however UNCC (Aug 16) have requested progression. | Chairperson (LJ) | 2016-07-27 | Closed | High | 2016-08-31 | To be included in the next iteration of the Framework Document - action PAC0804d. Drafting included in the v1.2 ToR and the appropriate Assurance letter in the Framework Document v1.6 | Completed at Jan 17 meeting
PAC006 | PAC Membership - to consider whether Ofgem should be included explicitly (non-voting) | Ofgem have obligations under the CMA report to ensure that a PAF is implemented by June 17 - also means that Ofgem would have sight of attributable information. | Chairperson (LJ) | 2016-08-31 | Closed | Low | 2016-10-10 | Is a confidentiality agreement required? Action PAC0809 Ofgem should be able to attend meetings but not qualify as a Member. To be included as a line in the PAF document as "Ofgem Representative" - link to Action 0804d | Completed at Nov meeting
PAC007 | Transporter Standards of Service and Liabilities | TSLs driven by sections of the UNC removed by the Nexus and FGO modifications are not necessarily 'not required' going forwards. (i) It it expected that CMSG (a DSC committee) will establish suitable CDSP measures and this needs to be monitored. (ii) Transporter standards removed by thee mods should be considered and if necessary defined | Chairperson (LJ) | 2017-01-10 | Closed | Low | 2017-02-14 | New at Jan 17 meeting (after SoS review). RP is looking at the code requirements that drive the TSLs to see whether a mod is required to remove the reporting obligation. As part of this he will consider alternative routes to consider the transporter standards. Contract Managers group is already looking at this. PAC agreed to defer to them to avoid duplication. | Completed at Feb 2017 Meeting
PAC007 | There might be a need for PAF-specific contacts to be established; need to understand the purposes (such as operational process, commercial etc). | After considering the Electricity Incentive scheme it could be necessary to be able to quickly reach a variety of contacts throughout the industry to understand/address areas of poor performance | PAC | 2017-03-14 | Closed | Medium | 2017-10-10 | Ongoing, DSC Contract managers to be requested to nominate PAC specific contacts or to be the contact. List to be considered at August 2017 PAC | Completed at Oct 2017 Meeting
PAC008 | There might be benefits in providing some 'preventative services’ (such as systems/process verification, formal training etc) to parties. | After considering the Electricity Incentive scheme it could be necessary to be able to quickly reach a variety of contacts throughout the industry to understand/address areas of poor performance | PAC | 2017-03-14 | Closed | Low | 2017-10-10 | New issue - suggested completion December 2017. Update 10 Oct - review of training requirments started/review. | Completed at Oct 2017 Meeting