## Slide 1: XRN5682 – February 24 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER approved at ChMC on 11/10. Currently in System integration testing phase with Build completed on 24/11. Progress update: Build for all XRNs completed on - 24/11 System integration testing is in progress and on track to complete – 29/12 User acceptance testing and regression testing prep in progress with test cases for both phases in review. Approval of test cases is due on – 08/12 Implementation Approach document draft to be presented at December ChMC Decision in December ChMC: None |  | ​ Implementation date of 24th February, the contingency date is 02nd March | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5604 - UNC Modification 0811S Shipper Agreed Read (SAR) Exceptions Process XRN5605 - IGT Modification 159 – Amendments to the must-read process​ XRN5607 - Update to AQ Correction Processes (Modification 0816S) |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 29th November 2023