## Slide 1: XRN5629 – November 23 Major Release- Status Update
Slide updated on 29th November 2023
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER was approved in ChMC on 10/05. Currently in post implementation support (PIS) phase following successful implementation on 04/11, PIS on track to complete 01/12. Progress update: User acceptance testing completed on 13/10 Regression testing completed on 13/10 Performance testing completed on 27/10 Implementation Go Live successfully completed 04/11 Post implementation support (PIS) for XRN5186 and XRN5482 in progress, to be completed on 01/12 Decision in December ChMC: None |  | Implementation date of 4th November, the contingency date is 11th November | 
Risks and Issues | N/A |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs XRN5482 - Replacement of reads associated to a meter asset technical details change or update (RGMA) |  |  | 
Complete
On Track
At Risk
Overdue