## 0639R Issues
Modification 0639R: Issue Register (as at 27 February 2018)
Issue Ref. | Issue | Source | Background/Description | Issue Originator | Date Created | Status | Priority for Discussion (H/M/L) | Status Date | Status Summary/Action taken | Next Review
0639R01 | Scope – what is included/not included. | AUGE Year Review Report for 2016/17 - Section 4.1 The AUG Framework | 1. Clarity of scope - what is included that AUGE can directly/indirectly influence 2. Should scope be limited to downstream activities? 3.Should scope be purely a formulaic approach or more holistic to include detail on the issues that influence the value | Workgroup | 2018-01-31 | Live | H | 2018-02-27 | 27/2/18 - section 5 of the AUG Framework reviewed and the following options were identified as a way forward: • Continue with the current arrangements as is; • Build on the current arrangements with additional guidance/clarification/lists as to what was in scope; • Review current arrangements to ensure the AUGE has full flexibility to investigate an issue; • Provide separate/limited guidance on how the AUGE will deal with any known and/or new issues that already has an agreed industry governance approach. There was consensus not to have an overly-prescriptive list. Options to be discussed further at the next meeting, especially in the light of other developments. | 2018-03-27
0639R02 | How interaction with third parties should work and how to deal with conflict of interest issues. | AUGE Year Review Report for 2016/17 - Section 4.1 The AUG Framework | Conflict of interest - how to define third party does it include AUGE own organisation? | Workgroup | 2018-01-31 | Live | M | 2018-02-27 | 27/2/18 - section 5 of the AUG Framework was reviewed and it was identified that amendments to the wording in paragraph 5.1.7 could be considered to remove any potential for bias from the process. To be discussed further at the next meeting. Illustrative text: Where multiple data sources exist the AUG Expert will consider any potential conflicts of interest when deciding to evaluate the chosen data to obtain the most statistically sound solution, will document the alternative options and provide an explanation for its decision, including how any bias was avoided. | 2018-03-27
0639R03 | How feedback is treated throughout the AUG process (including the formal consultation period). Linked to issue R063905 (overall process improvements). | AUGE Year Review Report for 2016/17 - Section 4.1 The AUG Framework | 1. Guidance on how the AUGE should handle new issues that arise during the process or take into consideration issues being managed through other forums (for example LDZ shrinkage). 2. The framework document does not define the consultation period. Need clarification of when consultation starts and ends. | Workgroup | 2018-01-31 | Live | H | 2018-02-27 | 27/2/18 - paragraphs 6.3 and 6.4 of the AUG Framework document were reviewed, confirming that there was no specific reference to the 42-consultation period. Paragraph 7.1.3 defines the consultation period as 42 calendar days. The workgroup considered the merits of 42 days and whether it would be beneficial to move to a shorter 21-day consultation period. The general consensus was that 42 days is too long and a shorter timeframe was supported. At the next meeting it will need to be decided whether it is 21 (working assumption) or 28 calendar days. A draft future AUG timeline/process had been put forward by the Proposer and this was reviewed. See issue 0639R05 for the proposal for this and the other process improvements. | 2018-03-27
0639R04 | Review/clarification of UNC, UNCC process and AUG Framework documents in relation to voting requirements. Should the voting be related to the methodology, the weightings table or both? | AUGE Year Review Report for 2016/17 - Section 4.1 The AUG Framework |  | Workgroup | 2018-01-31 | Live | H | 2018-02-27 | 27/2/18 - UNC Section E 9.4.3 - sub paragraph (h) and other clauses were reviewed but as some of the rules are contained in the AUG Framework document as well, it was difficult to assess what needs to be changed. The AUG Framework 7.1.8 (Voting section) and Voting for the Statement were not specifically reviewed. A draft future AUG timeline/process had been put forward by the Proposer and this was reviewed. It was proposed that the UNCC meeting in May will consider both the final AUGS and Table. This means that only one UNCC voting meeting is required and as a result the process time is reduced as the July UNCC meeting is not required. See issue 0639R05 for the proposal for this and other process improvements. | 2018-03-27
0639R05 | The AUG process needs to have sufficient rigor, transparency, feedback opportunities and checkpoints. In particular, the AUGE statement and AUGE table need to be reviewed to decide what needs to be done to align them and clarification on when the tables should be published and whether they can be changed or not. | Section 4.2 The AUGE for areas such as: communication, industry engagement, query responses etc. | An issue was raised where the AUGE statement and AUGE table did not align and suggested that this could be an area of the process where clarity would be beneficial. When the tables should be published and whether they can be changed or not, also needs clarification. Note: There are no timescales specified in UNC. | Workgroup | 2018-01-31 | Live | H | 2018-02-27 | A draft future AUG timeline/process had been put forward by the Proposer and this was reviewed. There was general support for the following AUG process improvements: • an earlier initial industry meeting in October/December. • reduce the consultation period (see issue 0639R03) • incorporation of additional stakeholder engagement from the end of March (Publish Revised AUGS + Table) to May (UNCC Meeting to consider final AUGS and Table). • change the rules to clarify that the UNCC meeting in May will consider final AUGS and Table (see issue 0639R04) This means that only one UNCC voting meeting is required and as a result the process time is reduced at the July UNCC meeting is not required. See separate document for an illustration of all the proposed AUG timeline/process changes. New Action 0202: Xoserve (FC), to review the AUG timeline proposal and voting checkpoints and provide a track changed version (illustration) of the rule changes (UNC and/or Framework Document) to bring it into effect. | 2018-03-27
0639R06 | Role of Joint Office to support the AUG Process in terms of providing secretariat for the AUG meetings and providing a transparent communication vehicle for all AUG documents. | Section 4.3 The industry, e.g. for support for the process and timeliness/relevance of responses to consultation. | Concerns had been raised about the role of the Joint Office (JO) in the AUG process and feedback from industry had suggested that the Joint Office should undertake a role in the future instead of Xoserve. | Workgroup | 2018-01-31 | Closed | L | 2018-02-27 | Xoserve had approached Penny Garner the Chief Executive of the Joint Office to discuss support for the next round of meetings to take place in February, March and April 2018. The Joint Office are considering how these meetings could be supported. A new sub-committee might need to be set up through UNCC to facilitate the requested support from the JO. 27/2/18 - it was confirmed that the role of the Joint Office to support the AUG process had been discussed at the 15 February UNCC meeting. It was agreed that Joint Office would provide the secretariat for the AUG meetings and the Joint Office website would provide information on the meeting dates and papers. It was agreed that this issue can be closed. | 2018-03-27
0639R07 | Confusion of terminology - UIG and UG. | Feedback from DNV-GL. UNC Section H TPD 2.6.1 defines unidentified gas. | Current AUGE assesses final unidentified gas as line in the sand but their weighting factors are used to share out UIG at D+5 allocation. | Workgroup | 2018-01-31 | Live | M | 2018-02-27 | 27/2/18 - the proposal that unidentified gas at initial allocation (D+5) should be referred to as initial UIG and unidentified gas 'line in the sand' (Code cut-off date) should be referred to as 'final UIG', was reviewed by looking at the definitions in UNC Section H 2.6. There was ‘in-principle’ support for 2 separate definitions (initial and final UIG) but more discussion was needed to decide if a further definition was needed or if clarification of the existing definition was a better option. In addition, consideration of the knock-on implications of the new definitions would need some thought; what else would need to change and how would the definitions be applied in practice. To be discussed further at the next meeting. | 2018-03-27