## ME2 Monitor
2018 Site | Due date | Date started | Date complete | Complete within tolerance | Duration (days) | Report received | Report delay (days) | Checked by | Sent to UKT | 2018-06-11
Wytch Farm (Feb) | 2012-02-15 | 2018-04-18 | 2018-04-23 | Y | 5 | 2018-04-27 | 4
Hume | 2012-03-15 | 2018-03-07 | 2018-03-16 | Y | 9 | 2018-04-04 | 19 | SS | 2018-04-04
Soutra | 2012-03-15 | 2018-03-19 | 2018-03-21 | Y | 2 | 2018-04-04 | 14 | SS | 2018-04-04
Mitcham | 2017-03-15 |  |  |  | 0 |  | 0
Oak Avenue (Inter LDZ) | 2012-03-15
Blackmore Cres (Inter LDZ) | 2012-03-15
Dryburgh Road (Inter LDZ) | 2012-03-15
Balgray | 2012-04-15 | 2018-04-23 | 2018-04-24 | Y | 1 | 2018-04-25 | 1
Glenmavis (Winter) | 2012-04-15 | 2018-03-29 | 2018-03-29 | Y | 0 | 2018-04-04 | 6 | SS | 2018-04-04
Drum | 2012-04-15 |  |  |  | 0 |  | 0
Tatsfield (OP removal) | 2012-04-15
Winkfield SE | 2012-05-15 | 2018-05-30 | 2018-06-08 |  | 9 |  | -43259 | SS
Mappowder | 2012-05-15 | 2018-05-29 | 2018-05-31 |  | 2 | 2018-06-06 | 6 | SS | 2018-06-11
Careston | 2012-05-15 | 2018-05-22 | 2018-05-23 | Y | 1 | 2018-05-25 | 2 | SS | 2018-06-11
Winkfield SO | 2012-05-15 | 2018-05-01 | 2018-05-08 | Y | 7 | 2018-06-11 | 34 | SS | 2018-06-11
Bathgate | 2012-05-15 | 2018-05-22 | 2018-05-23 | Y | 1 | 2018-05-25 | 2 | SS | 2018-06-11
Ipsden C/D | 2012-05-15 |  |  |  | 0 |  | 0
Ipsden A | 2012-05-15 |  |  |  | 0 |  | 0
Kinknockie | 2012-05-15 | 2018-05-29 | 2018-05-30 | Y | 1 | 2018-05-31 | 1 | SS | 2018-06-11
Mitcham | 2016-05-15 | 2018-04-10 | 2018-04-12 | Y | 2 | 2018-04-13 | 1 | SS | N/A
Farningham A | 2012-06-15 |  |  |  | 0 |  | 0
Farningham B | 2012-06-15 |  |  |  | 0 |  | 0
Braishfield B | 2012-06-15 |  |  |  | 0 |  | 0
Lockerbie | 2012-06-15 |  |  |  | 0 |  | 0
Braishfield A | 2012-06-15 |  |  |  | 0 |  | 0
Pitcairngreen | 2012-04-15 | 2018-05-03 | 2018-05-04 | Y | 1 | 2018-05-17 | 13 | SS | 2018-06-11
Hardwick | 2012-06-15 |  |  |  | 0 |  | 0
Grain 2B | 2012-07-15
Armadale | 2012-07-15 |  |  |  | 0 |  | 0
Aberdeen | 2012-07-15 |  |  |  | 0 |  | 0
Shorne | 2012-07-15 |  |  |  | 0 |  | 0
Drum | 2012-07-15
Broxburn | 2012-08-15 |  |  |  | 0 |  | 0
Tatsfield (USM ME2) | 2012-08-15 |  |  |  | 0 |  | 0
Lamberton Toll (Inter LDZ) | 2016-08-15
Portsdown Hill Str 2
Portsdown Hill Str 3
St Fergus | 2012-09-15 |  |  |  | 0 |  | 0
Nether Howcleugh | 2012-09-15 |  |  |  | 0 |  | 0
Glenmavis (Summer) | 2012-09-15 |  |  |  | 0 |  | 0
Wytch Farm (Sep) | 2012-09-15 |  |  |  | 0 |  | 0
Grain 38B | 2012-09-15
Banbury | 2017-09-15
Newton Longville | 2017-09-15
Poundbury | 2013-10-15 |  |  |  | 0 |  | 0
Stranraer | 2012-10-15 |  |  |  | 0 |  | 0
Burnhervie | 2012-11-15 |  |  |  | 0 |  | 0
Didcot Bio | 2012-11-15
Langholm | 2012-11-15 |  |  |  | 0 |  | 0
Apsley (Bio) | 2015-11-15 |  |  |  | 0 |  | 0
Grants A &B | 2017-12-15 |  |  |  | 0 |  | 0
St Nicholas (Bio) | 2012-12-15 |  |  |  | 0 |  | 0
Ebbsfleet (Bio) | 2015-12-15 |  |  |  | 0 |  | 0
Coupar Angus (Bio) | 2015-12-15 |  |  |  | 0 |  | 0
Note on A11: SGN: ME2 brought forward from July to April as per C.Moffatt
Note on A12: SGN: Due to USM project, ME2 brought forward from August to April
Note on B20: am55611: Was due 15/06/15…. Change requested by BR to 15/05/15
Note on B27: am55611: Was due 15/06/15…. Change requested by BR to 15/04/15
Note on A33: SGN: ME2 brought forward to April as per C.Moffatt
Note on A35: SGN: Due to USM project.. ME2 brought forward to April