## Intro Page
Xoserve Change Delivery Plan on a Page |  | Legend
|  | XXX | Completed Task
| The attached plans give a view of the all change currently being managed by Xoserve via mutiple delivery platforms, UK link, Gemini, and Data. |  | Forcast Activity
| Tab 1 - provides all UK Link impacting change, release 2 has now been delivered & release 3 is currently in delivery, releases June-19 and Nov-19 have not yet had the scope for inclusion in the release agreed, therefore any change detailed in these releases are placeholders only. Also sets out potential delivery timelines for CSS (Central Switching Services) and UIG (unidentified Gas). At present RAASP is considered for inclusion in November 2019 release. |  | Baseline Activity
| Tab 2 - lists all current live change that feeds into the plans in this publication |  | Potential Actibity
| Tab 3 - Provides a 'look ahead' 2 year view of change for UK Link | RAG | Activity at risk
|  | RAG | Activity with potential risk
|  | RAG | Activity on Track
|  | RAG | Activity under replan/Review

## UK Link POAP
* Excludes Gemini changes
* This is a view of change taken form a point in time and it subject to change

## UK Link_Live_Changes
XRN Ref | High-Level Status | R&N Release Allocation | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Xoserve Proposed Indicative Prioritisation Score | July'17 Change Demand Backlog ChMC Priority | July'17 Change Demand Backlog SDG Priority | Xoserve Platform Owner | Origination Date | Change Originator | Xoserve Project Manager | R&N Release Number | Previous UK Link CR Ref | Delivery Team | ClearQuest Ticket (Minor Enhancement Delivery) | Current Delivery Implementation Forecast Date | Actual Delivery Implementation Date | Customer Requested Implementation Date | Primary Application Impacted | Business Process Impact | Flash IA: Perceived Delivery Effort | Workaround Available? | Workaround Accountability | Workaround Frequency | No. of Xoserve FTEs required to service the workaround | Workaround Complexity? | Workaround Lifespan | Change Driver | Change Beneficiary | Shipper Impact | Network Impact | iGT Impact | Primary Impacted DSC Service Area | Number of DSC Service Areas impacted | Change Improvement Scale (Size of proposed change) | Customer System Changes Required? | Customer Testing Likely Required? | Customer Training Required? | Safety of Supply at risk? | Financial Loss Incurred to Customer? | Customer Switching at risk? | ChMC CP Approval date | ChMC EQR Approval date | ChMC BER Approval date | ChMC CCR Approval date
4708 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Ability to assess change impact on individual customers | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 28.23% |  |  | R & N | 2018-06-26 | Linda Whitcroft | Linda Whitcroft |  |  | Xoserve Resource |  | No Date | No Date | 2019-06-01 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4711 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Feasibility Study to Analyse Alignment of Release Dates for Electricity and Gas | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 39.34% |  |  | R & N | 2018-07-02 | Padmini Duvvuri | Catrin Morgan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-07-31 | ISU | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | No Number of impacted DSC Service Areas | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
1154 | 2. Change sanction/approved and in project delivery | R1.0 (Nexus) | UK Link Programme (Archiving) | CP | LIVE | D1 - Change in delivery | 50.75% |  |  | R & N | 2008-03-03 | Chris Smith | Neil Morgan | 1 |  | Third Party SI / Service Provider |  | 2018-09-16 | No Date | 2017-06-01 | Other | Other | 100+days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4669 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Class 1 & 2 Energy Comparison Report | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 62.76% |  |  | R & N | 2018-05-14 | Carole Elwell | Donna Johnson |  |  | Minor Enhancements Team | XO3680 | No Date | No Date | 2018-06-01 | ISU | Invoicing | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
2831.5b | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Changes to the upper parameter of the XDO partial refresh file. Post Nexus (R2) | CR (Internal) | LIVE | D1 - Change in delivery | 31.83% | TBP | High | R & N | 2017-02-07 | Jon Follows | Christina Francis | 2 | UKLP292 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | FALSE | FALSE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4671 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Class 2 Energy Updates from UKL to Gemini via CON file | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 62.76% |  |  | R & N | 2018-05-14 | Jo Tedd | Donna Johnson |  |  | Minor Enhancements Team | XO3681 | No Date | No Date | 2018-07-01 | ISU | Invoicing | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
3995a | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Energy Theft Tip-off Service Data Provision | CP | LIVE | D1 - Change in delivery | 50.75% | TBP | High | R & N | 2016-03-15 | Alex Ross-Shaw | Christina Francis | 2 | UKLP222 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4513 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Change to validation of address fields | CR (Internal) | LIVE | D1 - Change in delivery | 31.23% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI359 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | CMS | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | FALSE | FALSE | TRUE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4514 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | MIV File Changes for MUR Invoice - CMS | CR (Internal) | LIVE | D1 - Change in delivery | 50.75% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI367 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | CMS | Invoicing | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4528 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | The word ‘PLOT’ as a prefix | CR (Internal) | LIVE | D1 - Change in delivery | 33.03% |  |  | R & N | 2017-11-07 | Mike Orsler/Emma Smith | Donna Johnson | 50 |  | Minor Enhancements Team | XO3592 | 2018-07-13 | No Date | 2018-03-23 | Other | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4316 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Meter Point Details Report & Sector Breakdown Report | CR (Internal) | LIVE | D1 - Change in delivery | 39.04% | TBP | Low | R & N | 2017-04-07 | Mark Cockayne | Christina Francis | 2 | UKLP315 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-05-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4449 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | PSR requirements – Vulnerable Customer data requirements | CP | LIVE | D1 - Change in delivery | 39.34% | High | High | R & N | 2016-11-11 | Steve Nunnington | Christina Francis | 2 | UKLP273 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | Service Area 22: Specific Services | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4554 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Amendment Invoice validation Reports | CR (Internal) | LIVE | D1 - Change in delivery | 28.83% |  |  | R & N | 2017-12-05 | Vicky Spiller | Donna Johnson | 50 |  | Minor Enhancements Team | XO3613 | 2018-07-30 | No Date | 2018-06-30 | ISU | Invoicing | 0-30days | TRUE | Xoserve | Monthly | One | High | 2019-12-01 | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4465 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Annual Production and notification of LIS-3years read | CR (Internal) | LIVE | D1 - Change in delivery | 54.35% | TBP | Low | R & N | 2017-02-21 | Emma Smith | Donna Johnson | 50 | UKLP IADBI301 | Minor Enhancements Team | XO3624 | 2018-06-30 | No Date | 2018-05-15 | ISU | Reads | 30-60 days | TRUE | Xoserve | Annually | One | LOW | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4249 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Address Maintenance Solution | CR (Internal) | LIVE | D1 - Change in delivery | 50.75% |  |  | R & N | 2017-03-22 | Steve Ganney | Christina Francis | 2 |  | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4299 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Reports required under UNC TPD V16.1 in Nexus (reports required by Mod 520A) | CP | LIVE | D1 - Change in delivery | 50.75% | High | High | R & N | 2016-08-12 | Steve Nunnington | Christina Francis | 2 | UKLP251 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-05-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4563 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Assurance of the Annual AQ activities | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 50.75% |  |  | R & N | 2017-12-18 | Sue Prosser | Donna Johnson | 50 |  | Minor Enhancements Team | 3632 | 2018-09-29 | No Date | 2018-09-29 | ISU | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4303 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | CR (Internal) | LIVE | D1 - Change in delivery | 50.75% | TBP | Low | R & N | 2016-10-18 | Dean Johnson | Christina Francis | 2 | UKLP267 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-05-01 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4524 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Change to generation logic of RDP data flows to include all recorded iGT Supply Points within UK Link systems | CR (Internal) | LIVE | D1 - Change in delivery | 42.64% |  |  | R & N | 2017-10-31 | Paul Orsler | Donna Johnson | 50 |  | Minor Enhancements Team | XOS3657 | 2018-09-20 | No Date | 2018-11-09 | ISU | Other | 30-60 days | FALSE | [5 empty] | License Condition | Multiple Market Participants | TRUE | TRUE | TRUE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Two to Five | Low | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | No Date | No Date | No Date | No Date
4304 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Amend referral rules for class 2 smaller LSP’s | CR (Internal) | LIVE | D1 - Change in delivery | 50.75% | TBP | Medium | R & N | 2016-11-03 | Dean Johnson | Christina Francis | 2 | UKLP270 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-05-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4482 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | SAP Meter Read Entry Screen | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 21.62% |  |  | R & N | 2017-05-30 | Emma Smith | Donna Johnson | 50 | UKLP IADBI333 | Minor Enhancements Team | XO3629 | No Date | No Date | 2018-07-27 | ISU | Reads | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4309 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Back billing for domestic (SSP) sites needs to be reflect thecorrect adjustment start date | CR (Internal) | LIVE | D1 - Change in delivery | 50.75% | TBP | Low | R & N | 2016-01-19 | Dean Johnson | Christina Francis | 2 | UKLP287 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-05-01 | CMS | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
3477 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Missing Key Data Item from iGT’s to Shippers (Plot Number) | CP | LIVE | D1 - Change in delivery | 36.94% | High | High | R & N | 2015-07-07 | Lee Chambers | Christina Francis | 2 | UKLP IADBI112 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | BW | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | FALSE | TRUE | Service Area 23: Internal | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-10 | 2018-01-10 | No Date
4288 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | DDS/DDU file amendment | CP | LIVE | D1 - Change in delivery | 31.23% | Low | High pending discussions with all Networks | R & N | 2015-10-14 | Matt Smith | Christina Francis | 2 | UKLP IADBI147 | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | FALSE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
3283 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Recording of DN Siteworks’ / New Network Connection Reference in Central systems (ON HOLD PENDING NEW CO) | CP | LIVE | D1 - Change in delivery | 34.83% | Low | Low | R & N | 2013-12-16 | Joel Martin | Christina Francis | 2 | n/a | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 21: Data Flows and Services to Network Operators | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
3386 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Create new “role” for CMS to cover all activities undertaken within a Distribution Network (ON HOLD PENDING NEW CO) | CP | LIVE | D1 - Change in delivery | 40.24% | Low | Low | R & N | 2014-05-08 | Jo Ferguson | Christina Francis | 2 | n/a | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | CMS | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | FALSE | TRUE | FALSE | Service Area 22: Specific Services | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4248 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Quarterly smart metering reporting for HS&E and GDNs (post Nexus R2) | CP | LIVE | D1 - Change in delivery | 45.35% | High | High | R & N | 2017-03-22 | Joanna Ferguson | Christina Francis | 2 | n/a | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-29 | BW | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4361 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Release 2 Delivery | CP | LIVE | D1 - Change in delivery | 35.14% |  |  | R & N | 2017-10-11 | Christina Francis | Christina Francis | 2 |  | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-05-01 | ISU | Other | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 17: UK Link Services | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4534 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Amendment to RGMA Validation Rules for Meter Asset Installation Date | CP | LIVE | D1 - Change in delivery | 60.66% |  |  | R & N | 2017-11-20 | Andrew Margan | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-06-01 | ISU | No Process | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | One | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | 2018-01-10 | 2018-02-07 | 2018-04-11 | No Date
4538 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Insertion of Maximum Number of Occurrences in Meter Inspection Date Notice (MID) File. | CR (Internal) | LIVE | D1 - Change in delivery | 19.82% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-11-09 | ISU | No Process | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4539 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | New File Level Rejection | CR (Internal) | LIVE | D1 - Change in delivery | 29.43% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-11-01 | ISU | Invoicing | 0-30days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
3699 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | IA for strategic solution options for the GDE Offline database | CR (Internal) | LIVE | X1 - Xoserve propose change not required | 27.63% | Low | Low | R & N | 2015-05-15 |  | Padmini Duvvuri | 99 | UKLP IADBI096 | Third Party SI / Service Provider |  | No Date | No Date | 2000-02-02 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4453 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | File Format Should Have Changes | CR (Internal) | LIVE | D1 - Change in delivery | 41.44% | TBP | Low | R & N | 2016-12-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI280v3 | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-06-01 | ISU | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
3656 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Read Validation Tolerances | CP | LIVE | D1 - Change in delivery | 36.64% | TBP | Low | R & N | 2014-12-24 | Michelle Downes | Padmini Duvvuri | 3 | UKLP IADBI060 | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-05-01 | ISU | RGMA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-02-07 | 2018-02-07 | 2018-04-11 | No Date
4454 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Cadent Billing - DN Sales (Outbound Services) | CP | LIVE | D1 - Change in delivery | 60.96% | TBP | High | R & N | 2016-12-16 | Linda Whitcroft | Padmini Duvvuri | 3 | UKLP IADBI281 | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-06-01 | ISU | Invoicing | 31-100days | TRUE | Both Xoserve & Customer | Daily | Two to Five | High | 2018-06-01 | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | High | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | 2017-12-13 | 2018-02-07 | 2018-04-11 | No Date
4556 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Process to provide a report when Gas Safety Regulations requests return no MPRN’s | CP | LIVE | D1 - Change in delivery | 34.83% |  |  | R & N | 2017-12-06 | Andy Clasper | Matt Rider | 50 |  | Minor Enhancements Team | XO3614 | 2018-10-10 | No Date | 2018-02-23 | ISU | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | Service Area 22: Specific Services | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-01-10 | No Date | 2018-05-09 | No Date
4687 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | PSR updates for large domestic sites | CP | LIVE | A5 - CP in capture with DSG | 34.83% |  |  | R & N | 2018-06-04 | Ellie Rogers | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2019-02-01 | ISU | SPA | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4688 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Brownfield AQ Corrections | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 34.83% |  |  | R & N | 2018-06-04 | Lee Jackson | Donna Johnson |  |  | Minor Enhancements Team | XO3687 | No Date | No Date | 2018-07-01 | ISU | AQ | 30-60 days | TRUE | Xoserve | Daily | One | High | 2019-01-31 | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4690 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Actual read following estimated transfer read calculating AQ of 1 | CP | LIVE | A6 - CP in solution consultation | 37.24% |  |  | R & N | 2018-06-04 | James Rigby (Npower) | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-08-01 | ISU | AQ | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4521 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | NTS Datalogged Site not being loaded into Gemini | CR (Internal) | LIVE | D1 - Change in delivery | 39.64% |  |  | R & N | 2017-10-31 | Liz Ryan/Emma Lyndon | Donna Johnson | 50 |  | Minor Enhancements Team | XOS3587 | 2018-07-08 | No Date | 2018-06-10 | Gemini | Other | 0-30days | TRUE | Both Xoserve & Customer | Daily | One | Medium | 2019-12-01 | License Condition | One Market Participant | FALSE | TRUE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4186 | 3. Change delivered, awaiting closure approval/sign-off | Out for industry sponsorship/approval to reject | UK Link Future Release Analysis | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 15.62% |  |  | R & N | 2017-01-30 | Jane Rocky | Lee Chambers |  |  | Third Party SI / Service Provider |  | 2017-10-11 | 2017-11-16 | No Date | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4273 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Introducing IHD (In-Home Display) Installed Status of Failed MOD614 | CP | LIVE | D1 - Change in delivery | 33.03% |  |  | R & N | 2017-05-10 | Alex Cebo | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-06-01 | ISU | Other | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-11-08 | 2018-02-07 | 2018-04-11 | No Date
4337 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | To change the optionality of the Supply Point confirmation reference for the T51 file | CR (Internal) | LIVE | D1 - Change in delivery | 40.24% |  |  | R & N | 2017-07-24 | Sue prosse/Emma Lyndon | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-04-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4495 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Energy Tolerance Rejection code | CR (Internal) | LIVE | D1 - Change in delivery | 29.43% |  |  | R & N | 2017-06-28 | Nick Timm | Padmini Duvvuri | 3 | UKLP IADBI356 | Third Party SI / Service Provider | 3627 | 2018-11-09 | No Date | 2018-11-01 | ISU | Reads | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4431 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | CR (Internal) | LIVE | D1 - Change in delivery | 37.84% | TBP | High | R & N | 2016-05-04 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI202 | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-10-01 | ISU | Reads | 31-100days | TRUE | External Customer | Daily | No Xoserve FTEs | Low | 2018-12-31 | MOD/Ofgem | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4443 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | File Format Changes Aug 16 Unique Sites (deferred items from CR252) | CR (Internal) | LIVE | D1 - Change in delivery | 33.63% | TBP | Low | R & N | 2016-09-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI258 | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4458 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Class 4 CSEPS Reconciliation Variance Identification | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% | TBP | Medium | R & N | 2017-01-26 | Karen Marklew | Padmini Duvvuri | 3 | UKLP IADBI289 | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-12-31 | ISU | Reads | 31-100days | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | LOW | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4486 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Meter Type O = Oriffice to be an acceptable value in file formats and reports | CR (Internal) | LIVE | D1 - Change in delivery | 30.63% |  |  | R & N | 2017-06-05 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI338 | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | Low | 2018-12-31 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4481 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Resolution of penny mismatches within invoice supporting information for Core invoices. | CR (Internal) | LIVE | D1 - Change in delivery | 39.64% |  |  | R & N | 2017-05-30 | Kiran Kumar | Padmini Duvvuri | 3 | UKLP IADBI332 | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-06-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4691 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | CSEPs: IGT and GT File Formats (CGI Files) | CP | LIVE | A3 - CP within initial consultation | 32.43% |  |  | R & N | 2018-06-05 | Richard Pomroy (Wales & West Utilities) | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | ISU | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | FALSE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4692 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | CSEPs: IGT and GT File Formats (CIN Files) | CP | LIVE | A3 - CP within initial consultation | 32.43% |  |  | R & N | 2018-06-05 | Richard Pomroy (Wales & West Utilities) | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | ISU | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | FALSE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4693 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | CP | LIVE | A3 - CP within initial consultation | 32.43% |  |  | R & N | 2018-06-05 | Richad Pomroy (Wales & West Utilities) | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | ISU | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | FALSE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4694 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | CSEPs: IGT and GT File Formats (Create new data validations ) | CP | LIVE | A3 - CP within initial consultation | 32.43% |  |  | R & N | 2018-06-05 | Richard Pomroy (Wales & West Utilities) | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | ISU | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | FALSE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4572 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Retail & Network Release 3 | CP | LIVE | D1 - Change in delivery | 33.33% |  |  | R & N | 2018-01-03 | Padmini Duvvuri | Padmini Duvvuri | 3 |  | Third Party SI / Service Provider |  | 2018-11-09 | No Date | 2018-10-31 | ISU | No Process | 100+ days | FALSE | [5 empty] | ChMC endorsed Change Proposal | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 17: UK Link Services | Five to Twenty | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4484 | 2. Change sanction/approved and in project delivery | MR Drop 1 | Remove restriction on nominated SOQ (as per MOD 445 | CR (Internal) | LIVE | D1 - Change in delivery | 40.24% |  |  | R & N | 2017-06-06 | Bhupinder Basra | Matt Rider | Jul2018 | UKLP IADBI336 | Third Party SI / Service Provider |  | 2018-07-14 | No Date | 2018-10-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4496 | 2. Change sanction/approved and in project delivery | MR Drop 1 | iGT Address Amendments - SAP | CR (Internal) | LIVE | D1 - Change in delivery | 38.44% |  |  | R & N | 2017-06-30 | Richard Cresswell | Matt Rider | Jul2018 | UKLP IADBI358 | Third Party SI / Service Provider |  | 2018-07-14 | No Date | 2018-12-31 | ISU | SPA | 31-100days | TRUE | Xoserve | Daily | One | High | 2018-12-31 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4469 | 2. Change sanction/approved and in project delivery | MR Drop 1 | UMR Hierarchy Amendment in AMT | CR (Internal) | LIVE | D1 - Change in delivery | 31.23% | TBP | Low | R & N | 2017-03-27 | Karen Marklew | Matt Rider | Jul2018 | UKLP IADBI309 | Third Party SI / Service Provider | 3628 | 2018-07-14 | No Date | 2018-10-01 | AMT | Reads | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4480 | 2. Change sanction/approved and in project delivery | MR Drop 1 | Capacity reconciliation charge (MOD445) calculation functionality | CR (Internal) | LIVE | D1 - Change in delivery | 52.25% |  |  | R & N | 2017-05-30 | Kiran Kumar | Matt Rider | Jul2018 | UKLP IADBI331 | Third Party SI / Service Provider |  | 2018-07-14 | No Date | 2018-10-01 | ISU | Other | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4685 | 2. Change sanction/approved and in project delivery | MR Drop 1 | Retail & Network Minor Release – Drop 1 – July-18 | CR (Internal) | LIVE | D1 - Change in delivery | 21.02% |  |  | R & N | 2018-05-29 | Matt Rider | Matt Rider | Jul2018 |  | Third Party SI / Service Provider |  | 2018-07-14 | No Date | 2018-07-14 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4621 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Suspension of the Validation between Meter Index and Uncoverted Converter Index | CP | LIVE | A5 - CP in capture with DSG | 25.83% | 0% | 0% | R & N | 2018-02-27 | Rachel Hinsley | Dave Addison | Jun2019 | 176 & 182 | Third Party SI / Service Provider |  | No Date | No Date | 2019-02-01 | ISU | Reads | 100+ days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4587 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Test of the Bulk upload facility | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 69.97% |  |  | R & N | 2018-01-22 | Dawn Gallacher | Donna Johnson | 50 |  | Minor Enhancements Team | XO3648 | No Date | No Date | 2018-04-30 | ISU | SPA | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | Two to Five | High | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
4591 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | FOF environment for GDE Lookup tables in SAP BW | CR (Internal) | LIVE | X1 - Xoserve propose change not required | 31.53% |  |  | R & N | 2018-01-23 | Julie Bretherton | Simon Harris |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-30 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4593 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Removal of Backbiling Exceptions (BB02, BB04, BB05) | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 28.83% |  |  | R & N | 2018-01-23 | Jo Duncan | Donna Johnson | 50 |  | Minor Enhancements Team | XO3645 | No Date | No Date | 2018-06-30 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 2018-06-30 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4595 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | SAP T-Code Access – Modification to ISU & BW Permissions for Data Office Aligned Resources | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 27.63% |  |  | R & N | 2018-01-23 | Steve Concannon | Donna Johnson | 50 |  | Minor Enhancements Team | XO3646 | No Date | No Date | 2018-02-28 | AMT | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3667a | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Provision of Prospective Formula Year AQ/SOQ and Historic RAQ to Proposing Users | CP | LIVE | A5 - CP in capture with DSG | 46.85% |  |  | R & N | 2018-04-04 | James Rigby | Simon Harris |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-12-01 | ISU | SPA | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Medium | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | 2018-04-11 | No Date | No Date | No Date
4670 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 18.02% |  |  | R & N | 2018-05-14 | Karen Marklew | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-11-01 | ISU | Reads | 30-60 days | TRUE | Xoserve | Monthly | One | Medium | 2019-01-31 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4677 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 53.15% |  |  | R & N | 2018-05-21 | Dan Donovan | Matt Rider | IA |  | Third Party SI / Service Provider | XO3683 | 2018-07-30 | No Date | 2018-07-31 | BW | Invoicing | 30-60 days | TRUE | Xoserve | Monthly | Ten Plus | High | 2018-07-31 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4665 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Creation of new End User Categories | CP | LIVE | A7 - CP awaiting ChMC solution approval | 46.25% |  |  | R & N | 2018-05-02 | Emma Smith | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-10-01 | ISU | Invoicing | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | TRUE | TRUE | Service Area 15: Demand Estimation | Two to Five | Medium | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4686 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Smart Metering Report | CP | LIVE | A5 - CP in capture with DSG | 28.83% |  |  | R & N | 2018-06-04 | Liam Percy (CNG) | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-01 | BW | RGMA | 0-30 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4676 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Reconciliation issues with reads recorded between D-1 to D-5. | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 62.16% |  |  | R & N | 2018-05-21 | Rachel Martin | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-07-31 | ISU | Reads | 30-60 days | TRUE | Xoserve | Monthly | Two to Five | High | 2018-12-03 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | Five to Twenty | High | TRUE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4679 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | CP | LIVE | A2 - CP proposed for ChMC | 36.64% |  |  | R & N | 2018-05-22 | Dave Addison | Emma smith | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-08-01 | ISU | Reads | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Medium | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4044 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Extension of ‘Must Read’ process to include Annual Read sites | CP | LIVE | A5 - CP in capture with DSG | 34.83% |  |  | R & N | 2017-12-05 | Andy Clasper | Julie Bretherton | Jun2019 |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-01 | ISU | RGMA | 0-30days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | FALSE | Service Area 22: Specific Services | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-01-10 | No Date | No Date | No Date
4642 | 1. Start-Up (Progressing through change governance) | 2019-06-01 | Address Maintenance Solution | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 43.84% |  |  | R & N | 2018-04-03 | Nandini Kundu | Linda Whitcroft | Jun2019 |  | Third Party SI / Service Provider |  | 2018-10-01 | No Date | 2018-10-01 | ISU | SPA | 60-100 days | FALSE | [5 empty] | License Condition | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4541 | 1. Start-Up (Progressing through change governance) | 2019-11-01 | Read Design Gaps - Missing Overide Flags In RGMA and Retro Files Linked to Retro (4474) | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 31.23% | Low | Low - to be reviewed in 3 months time | R & N | 2015-02-10 | Emma Smith | Lee Chambers | Nov2019 | UKLP IADBI073 | Third Party SI / Service Provider |  | 2018-06-28 | No Date | 2018-11-01 | ISU | RGMA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4378 | 3. Change delivered, awaiting closure approval/sign-off | Solman | Solution Manager Upgrade | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 27.63% |  |  | R & N | 2017-10-02 | Smitha Pichrikat | Neil Morgan |  |  | Third Party SI / Service Provider |  | 2018-04-16 | 2018-04-16 | 2018-04-03 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4575 | 3. Change delivered, awaiting closure approval/sign-off | R&N Minor Release/Impact Assessment (Mar'18) | Introduction of a R&N Minor Release Delivery Mechanism | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 27.63% |  |  | R & N | 2018-01-09 | Lee Chambers | Matt Rider |  |  | Third Party SI / Service Provider |  | 2018-05-15 | No Date | 2018-05-15 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4474 | 1. Start-Up (Progressing through change governance) | 2019-11-01 | Delivery of Retro | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 38.44% | TBP | High | R & N | 2017-04-21 | Lee Chambers | Lee Chambers | Nov2019 | UKLP IADBI319 | Third Party SI / Service Provider |  | 2019-06-28 | No Date | 2019-02-01 | ISU | Other | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Five to Twenty | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4574 | 2. Change sanction/approved and in project delivery | R&N New Environment (Apr'18) | Provision of a New Project Track UK Link Environment | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | R & N | 2018-01-08 | Lee Chambers | Lee Chambers |  |  | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2018-06-15 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4584 | 1. Start-Up (Progressing through change governance) | CSS | Central Switching Services | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 21.02% |  |  | R & N | 2018-01-17 | Andy Earnshaw | Smitha Pichrikat |  |  | Third Party SI / Service Provider |  | 2022-02-28 | No Date | 2020-12-01 | Other | Other | 100+ days | FALSE | [5 empty] | MOD/Ofgem | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4627 | 1. Start-Up (Progressing through change governance) | CSS | Consequential Central Switching Services | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 57.36% |  |  | R & N | 2018-03-09 | Andy Earnshaw | Smitha Pichrikat |  |  | Third Party SI / Service Provider |  | 2020-06-01 | No Date | 2020-06-01 | ISU | SPA | 100+ days | FALSE | [5 empty] | License Condition | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Five to Twenty | High | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | No Date | No Date | No Date | No Date
4612 | 1. Start-Up (Progressing through change governance) | MR Drop 2 | RGMA Activity on Transfer Date | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 69.97% |  |  | R & N | 2018-02-20 | John Harris | Matt Rider | Sep2018 |  | Third Party SI / Service Provider |  | 2018-09-10 | No Date | 2018-04-01 | ISU | Reads | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | FALSE | FALSE | Service Area 23: Internal | Two to Five | High | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
4645 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 37.24% |  |  | R & N | 2018-04-03 | Rachel Hinsley | Rachel Hinsley |  |  | Third Party SI / Service Provider | 4622 | No Date | No Date | 2018-11-02 | ISU | Invoicing | 60-100 days | TRUE | Xoserve | Daily | One | High | 2018-11-02 | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4658 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Read validation – increasing outer tolerance value for specific AQ bands for Class 3 & 4 Meter Points | CP | LIVE | A5 - CP in capture with DSG | 64.26% |  |  | R & N | 2018-04-25 | Emma Smith | Dave Addison |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-01 | ISU | Reads | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Medium | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
4576 | 2. Change sanction/approved and in project delivery | MR Drop 2 | Class 4 Transfer Reads not visible to shippers in DES | CP | LIVE | D1 - Change in delivery | 27.03% |  |  | R & N | 2018-01-09 | Alison Cross | Matt Rider | Sep2018 |  | Third Party SI / Service Provider | XO3630 | 2018-09-14 | No Date | 2018-09-30 | BW | Portal | 30-60 days | TRUE | External Customer | Monthly | One | Low | 2018-03-30 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 23: Internal | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-03-07 | No Date | 2018-05-09 | No Date
4699 | 1. Start-Up (Progressing through change governance) | Internal Requirements Gathering (Capture) | Minor Release Drop 2 – Sept-18 | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 13.21% |  |  | R & N | 2018-06-12 | Julie Bretherton | Matt Rider |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-11-06 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date

## UK Link_2yr_view
Change Allocation | Count of XRNs
Solution Manager Update (Feb'18) | 1
Release Nov 19 | 2
Release Jun 19 | 7
Release Feb 19 | 0
R3.0 (Nov'18) | 15
R2.0 (Jun'18) | 17
R1.0 (Nexus) | 1
R&N New Environment (Apr'18) | 1
R&N Minor Release/Impact Assessment (Mar'18) | 1
Out for industry sponsorship/approval to reject | 3
Internal req Gathering (Capture) | 14
Minor Enhancement Delivered Change | 14
CSS | 2
Candidate for Minor Release Drop 2 | 2
Candidate for Minor Release Drop 1 | 5
Grand Total | 85
Please filter in column C within the 'R&N_Live_Changes' tab to view specific XRNs

## Sheet4 (hidden)
Row Labels | Count of XRN Ref
(blank)
2019-11-01 | 2 | X
2019-06-01 | 7 | X
Solman | 1 | X
R3.0 (Nov'18) | 15 | X
R2.0 (Jun'18) | 17 | X
R1.0 (Nexus) | 1 | X
R&N New Environment (Apr'18) | 1 | X
R&N Minor Release/Impact Assessment (Mar'18) | 1 | X
Out for industry sponsorship/approval to reject | 3 | X
MR Drop 2 | 2 | X
MR Drop 1 | 5 | X
Minor Enhancement Delivered Change | 14 | X
Internal Requirements Gathering (Capture) | 14 | X
CSS | 2 | X
Grand Total | 85

## Gemini & Data Stream POAP (hidden)
Gemini
Data Platform

## Gemini & Data Stream_Live_Chang (hidden)
XRN Ref | High-Level Status | R&N Release Allocation | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Xoserve Proposed Indicative Prioritisation Score | July'17 Change Demand Backlog ChMC Priority | July'17 Change Demand Backlog SDG Priority | Xoserve Platform Owner | Origination Date | Change Originator | Xoserve Project Manager | R&N Release Number | Previous UK Link CR Ref | Delivery Team | ClearQuest Ticket (Minor Enhancement Delivery) | Current Delivery Implementation Forecast Date | Actual Delivery Implementation Date | Customer Requested Implementation Date | Primary Application Impacted | Business Process Impact | Flash IA: Perceived Delivery Effort | Workaround Available? | Workaround Accountability | Workaround Frequency | No. of Xoserve FTEs required to service the workaround | Workaround Complexity? | Workaround Lifespan | Change Driver | Change Beneficiary | Shipper Impact | Network Impact | iGT Impact | Primary Impacted DSC Service Area | Number of DSC Service Areas impacted | Change Improvement Scale (Size of proposed change) | Customer System Changes Required? | Customer Testing Likely Required? | Customer Training Required? | Safety of Supply at risk? | Financial Loss Incurred to Customer? | Customer Switching at risk? | ChMC CP Approval date | ChMC EQR Approval date | ChMC BER Approval date | ChMC CCR Approval date
4700 | 1. Start-Up (Progressing through change governance) |  | Provision of data to Suppliers via API | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 28.53% |  |  | Data Office | 2018-06-18 | Mark Pollard | Simon Harris |  |  | Xoserve Resource |  | No Date | No Date | 2018-09-28 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4702 | 1. Start-Up (Progressing through change governance) |  | Opportunity 1: Switching Performance dashboard (s) to enable supplier incentivisation | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 32.13% |  |  | Data Office | 2018-06-18 | Rebecca Roden | Jo Duncan |  |  | Xoserve Resource |  | No Date | No Date | 2019-05-31 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4703 | 1. Start-Up (Progressing through change governance) |  | Opportunity 2: Duel fuel enquiry service to deliver improved consumption estimations | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 42.94% |  |  | Data Office | 2018-06-18 | Rebecca Roden | Mark Pollard |  |  | Xoserve Resource |  | No Date | No Date | 2018-05-31 | Other | AQ | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4704 | 1. Start-Up (Progressing through change governance) |  | (ASR) Peoples Energy Company – Gemini Gas Distribution by LDZ by Day Report | CR (ASR) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 28.83% |  |  | Data Office | 2018-06-25 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | No Date | No Date | 2018-07-31 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4706 | 1. Start-Up (Progressing through change governance) |  | (ASR) National Grid Gas – Test Support & Consultancy on Connectivity between Xoserve & Gemini | CR (ASR) | LIVE | A9 - Internal change progressing through capture | 24.02% |  |  | T & SS | 2018-06-25 | Greg Causon | Nicola Patmore |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-30 | Gemini | Other | 100+ days | FALSE | [5 empty] | Additional or 3rd Party Service Request | No Change Beneficiary | FALSE | TRUE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4707 | 1. Start-Up (Progressing through change governance) |  | (ASR) Cadent Gas - RA04 & RA05 Network Identifier Report Amendment | CR (ASR) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 28.83% |  |  | Data Office | 2018-06-25 | Greg Causon | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-07-30 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | FALSE | TRUE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4710 | 1. Start-Up (Progressing through change governance) |  | ASR – POW to be added to Eon Reports | CR (ASR) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 25.83% |  |  | Data Office | 2018-07-02 | Greg Causon | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-08-07 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4169 | 1. Start-Up (Progressing through change governance) |  | To update functionality in Gemini to ensure that all Cash Call Notices and TemplaRequest for Project Management resource to manage the analysis and resolution of the issues with the Amendment invoicees reflect UNC Section X and Energy Balancing Credit Rul | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 18.62% |  |  | T & SS | 2017-01-09 | Loraine O’Shaughnessy | Donna Johnson | 50 |  | Minor Enhancements Team | XO3452 | 2018-07-30 | No Date | 2018-09-13 | Gemini | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4672 | 2. Change sanction/approved and in project delivery |  | Extension of PCW API Service to Suppliers | CR (Internal) | LIVE | D1 - Change in delivery | 31.83% |  |  | Data Office | 2018-05-14 | Mark Pollard | Mark Pollard |  |  | Xoserve Resource |  | 2018-06-29 | No Date | 2018-06-29 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4673 | 2. Change sanction/approved and in project delivery |  | Identification of Short Haul in Non-standard Sites Reports | CR (Internal) | LIVE | D1 - Change in delivery | 39.04% |  |  | Data Office | 2018-05-14 | Thomas Rooney | Jo Duncan |  |  | Xoserve Resource |  | 2018-06-30 | No Date | 2018-06-30 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | Two to Five | Low | 2019-02-28 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | FALSE | Service Area 18: Provision of User Reports and Information | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4646 | 1. Start-Up (Progressing through change governance) |  | Amendment to plot to postal report | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 34.83% |  |  | Data Office | 2018-04-10 | Tahera Choudhury | Jo Duncan |  |  | Minor Enhancements Team | XO3678 | 2018-06-29 | No Date | 2018-05-04 | BW | SPA | 0-30 days | FALSE | [5 empty] | MOD/Ofgem | One Market Group | FALSE | TRUE | TRUE | No DSC Service Area | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4623 | 2. Change sanction/approved and in project delivery |  | XEC Customer Dashboard Development | CR (Internal) | LIVE | D1 - Change in delivery | 28.83% |  |  | Data Office | 2018-02-05 | James Verdon | Jo Duncan | 0 |  | Xoserve Resource |  | 2018-07-13 | No Date | 2018-05-11 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4639 | 2. Change sanction/approved and in project delivery |  | Customer KVI Reporting | CR (Internal) | LIVE | D1 - Change in delivery | 57.96% |  |  | Data Office | 2018-03-27 | Michele Downes | Jo Duncan |  |  | Xoserve Resource |  | 2018-07-15 | No Date | 2018-05-01 | Birst | Other | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 2018-04-27 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 19: Network Operator and User Relationship Management | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4618 | 3. Change delivered, awaiting closure approval/sign-off |  | ASR - Billing History by all NTS Capacity & Commodity Sites | CR (ASR) | LIVE | F1 - CCR/Closedown document in progress | 33.63% |  |  | Data Office | 2018-02-26 | Greg Causon | Jo Duncan | 50 |  | Minor Enhancements Team | XO3672 | 2018-07-13 | 2018-05-15 | 2018-05-15 | Gemini | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Group | FALSE | TRUE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4619 | 1. Start-Up (Progressing through change governance) |  | SAP BW MPRL Delta Table Creation | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 21.62% |  |  | Data Office | 2018-02-26 | Steve Concannon | Donna Johnson | 50 |  | Minor Enhancements Team | XO3665 | 2018-08-30 | No Date | 2018-08-30 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4683 | 1. Start-Up (Progressing through change governance) |  | Class 3 & 4 Energy Comparison Report | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 45.05% |  |  | Data Office | 2018-05-25 | Jo Tedd | Jo Duncan |  |  | Third Party SI / Service Provider |  | 2018-07-30 | No Date | 2018-07-01 | Gemini | Invoicing | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4684 | 1. Start-Up (Progressing through change governance) |  | SAP BW Accelerator: Table Migration | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 20.42% |  |  | Data Office | 2018-05-29 | Fay morris | Fay Morris |  |  | Third Party SI / Service Provider |  | 2019-02-01 | No Date | 2019-02-01 | BW | Other | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4668 | 2. Change sanction/approved and in project delivery |  | ASR – CNG supplier Short Code(ENY) Portfolio Report. | CR (ASR) | LIVE | D1 - Change in delivery | 31.83% |  |  | Data Office | 2018-05-10 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-08-30 | No Date | 2018-05-31 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4648 | 1. Start-Up (Progressing through change governance) |  | Service Desk Plus/ServiceNow B2B Design Change | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 18.02% |  |  | T & SS | 2018-04-16 | Luke Moise | Luke Moise | 0 |  | Third Party SI / Service Provider |  | No Date | No Date | 2019-01-12 | Other | Other | 0-30 days | TRUE | Xoserve | Weekly | One | Medium | 2018-05-15 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4666 | 1. Start-Up (Progressing through change governance) |  | Changes to Gemini system to provide Business User access to Class 1 & 2 Energy values, to view & update & include additional data items in existing system generated reports | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 45.65% |  |  | T & SS | 2018-05-04 | Jo Tedd | Nicola Patmore |  |  | Third Party SI / Service Provider | XO3676 | No Date | No Date | 2018-05-31 | Gemini | Invoicing | 60-100 days | TRUE | Xoserve | Daily | One | Medium | 2018-12-28 | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | TRUE | TRUE | Service Area 23: Internal | Two to Five | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4633 | 2. Change sanction/approved and in project delivery |  | New website for Xoserve | CR (Internal) | LIVE | D1 - Change in delivery | 23.42% |  |  | T & SS | 2018-03-19 | Sarah Bridge | Emma Rose |  |  | Third Party SI / Service Provider |  | 2018-08-31 | No Date | 2018-12-31 | Other | Other | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4549 | 3. Change delivered, awaiting closure approval/sign-off |  | Future Solution for Hosting and Support of www.xoserve.com | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 39.04% |  |  | T & SS | 2017-12-05 | Mohamed Abdel-Gadir | Emma Rose |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2017-12-20 | Other | No Process | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4552 | 1. Start-Up (Progressing through change governance) |  | ‘Front end’ development of new Company Intranet | CR (Internal) | LIVE | C1 - Delivery Business Case/BER in progress | 24.62% |  |  | T & SS | 2017-12-05 | Sarah Bridge | Emma Rose |  |  | Third Party SI / Service Provider |  | 2018-06-30 | No Date | 2017-06-30 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4625 | 1. Start-Up (Progressing through change governance) |  | Retrospective - Change of Supply API Prototype Development for British Gas | CR (Internal) | LIVE | C1 - Delivery Business Case/BER in progress | 17.42% |  |  | Data Office | 2018-02-05 | Iain Snookes | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-12-31 | No Date | 2018-12-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | Service Area 23: Internal | One | Low | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4626 | 1. Start-Up (Progressing through change governance) |  | Provision of an alternative Consumer Enquiry Service (Mnumber) | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 40.54% |  |  | T & SS | 2018-03-09 | Dave Ackers | Dene Williams |  |  | Third Party SI / Service Provider |  | 2019-06-28 | No Date | 2018-08-01 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4628 | 2. Change sanction/approved and in project delivery |  | National Grid (Gemini) – BBL Testing support Linked to 4376 (CP) | CR (Internal) | LIVE | D1 - Change in delivery | 59.16% |  |  | T & SS | 2018-03-12 | Manisha Bhardwaj | Donna Johnson | 50 |  | Minor Enhancements Team | XO3669 | 2018-06-26 | No Date | 2018-06-25 | Gemini | Other | 30-60 days | FALSE | [5 empty] | EU Legislation | One Market Group | TRUE | TRUE | FALSE | Service Area 20: UK Link Gemini System Services | One | High | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4602 | 3. Change delivered, awaiting closure approval/sign-off |  | ASR - BUS NS S1 Report | CR (ASR) | LIVE | F1 - CCR/Closedown document in progress | 31.83% |  |  | Data Office | 2018-01-31 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-05-25 | 2018-05-25 | 2018-05-25 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4695 | 1. Start-Up (Progressing through change governance) |  | Investigating causes and contributors to levels and volatility of Unidentified Gas | CP (Non System Impacting) | LIVE | C1 - Delivery Business Case/BER in progress | 51.35% |  |  | Data Office | 2018-06-05 | Rachel Hinsley | Rebecca Roden |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-07-31 | Other | Other | 100+ days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 3: Record/submit Data in Compliance with UNC | One | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4542 | 2. Change sanction/approved and in project delivery |  | Changes to the Shipper Portfolio Summary Report (new fields and removal of fields no longer applicable) | CP | LIVE | D1 - Change in delivery | 26.43% |  |  | Data Office | 2017-11-24 | Emma Smith | Jo Duncan |  |  | Xoserve Resource | XO3605 | 2018-06-29 | No Date | 2018-11-01 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2019-01-30 | ChMC endorsed Change Proposal | One Market Participant | TRUE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-01-10 | 2018-04-11 | 2018-04-11 | No Date
4525 | 2. Change sanction/approved and in project delivery |  | Transparency of the Rolling AQ Process | CP | LIVE | D1 - Change in delivery | 37.84% |  |  | Data Office | 2017-10-31 | Shane Preston/Rachel Hinsley | Jo Duncan |  |  | Xoserve Resource | XOS3584 | 2018-06-26 | No Date | 2018-05-25 | BW | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-02-07 | 2018-04-11 | 2018-05-09 | No Date
2831.5a | 3. Change delivered, awaiting closure approval/sign-off |  | Smart Metering UNC MOD 430 DCC Testing and Trialling Pre Nexus | CP | LIVE | F1 - CCR/Closedown document in progress | 36.64% |  |  | T & SS | 2015-12-22 | Jo Feguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2017-03-31 | 2017-03-31 | 2017-03-31 | Other | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | TRUE | TRUE | Service Area 17: UK Link Services | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4578 | 2. Change sanction/approved and in project delivery |  | Monthly AQ Calculations for Class 4 sites with AMR fitted | CR (Internal) | LIVE | D1 - Change in delivery | 45.05% |  |  | T & SS | 2018-01-10 | Rachel martin/Emma Lyndon | Donna Johnson | 50 |  | Minor Enhancements Team | XO3637 | 2018-06-29 | No Date | 2018-05-18 | ISU | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 23: Internal | Two to Five | Low | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4580 | 2. Change sanction/approved and in project delivery |  | Shipper Performance Birst Dashboard (by Data Cleansing Topic) | CR (Internal) | LIVE | D1 - Change in delivery | 21.62% |  |  | Data Office | 2018-01-16 | James Verdon | Jo Duncan |  |  | Xoserve Resource |  | 2018-08-10 | No Date | 2018-08-10 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4328 | 2. Change sanction/approved and in project delivery |  | Report of iGT Methe elected shipper | CP | LIVE | D1 - Change in delivery | 36.04% |  |  | Data Office | 2017-07-05 | Emma Smith | Jo Duncan | 50 |  | Minor Enhancements Team | XOS3615 | 2018-08-19 | No Date | 2018-08-10 | BW | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 18: Provision of User Reports and Information | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-07-13 | 2018-03-07 | 2018-04-11 | No Date
4426 | 2. Change sanction/approved and in project delivery |  | Impact Assessment on changes to Market Intelligence report and Change of Supplier reporting suite ahead of Ofgem RFI | CR (Internal) | LIVE | D1 - Change in delivery | 44.44% | TBP | High | Data Office | 2016-04-28 | Paul Orsler | Jo Duncan |  | UKLP IADBI192 | Xoserve Resource |  | 2018-08-30 | No Date | 2018-07-30 | BW | Other | 31-100days | FALSE | [5 empty] | CMA Order | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4611 | 1. Start-Up (Progressing through change governance) |  | Replacement/Upgrade of Demand Estimation Systems and Processes | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 29.43% |  |  | Data Office | 2018-02-20 | Fiona Cottam | Fay Morris |  |  | Third Party SI / Service Provider |  | 2019-02-28 | No Date | 2019-03-01 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4655 | 1. Start-Up (Progressing through change governance) |  | Electronic CRM system to Capture Customer Contact Details and Email Conversations | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 31.53% |  |  | T & SS | 2018-04-24 | Adam Jones | Dene Williams |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-01 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4610 | 1. Start-Up (Progressing through change governance) |  | ASR Request - Reporting to SPAA Secretariat in Support of SPAA Schedule 25 – Management of Prepayment Activities | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 30.03% |  |  | Data Office | 2018-02-20 | Greg Causon | Jo Duncan |  |  | Minor Enhancements Team | XO3679 | 2018-07-31 | No Date | 2018-06-30 | BW | SPA | 60-100 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3676 | 3. Change delivered, awaiting closure approval/sign-off |  | Amendment to the AQ &SOQ File and Field Length | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 18.62% | 0% | 0% | T & SS | 2015-03-24 | Jo Tedd/ Dan Donovan | Donna Johnson | 50 | UKLP IADBI080 | Minor Enhancements Team | XO3598 | 2018-05-08 | 2018-05-08 | 2018-10-01 | Gemini | SPA | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4493 | 3. Change delivered, awaiting closure approval/sign-off |  | BIRST Connect integration | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 27.63% |  |  | Data Office | 2017-06-26 | Steve Concannon | Emma Rose | 50 | UKLP IADBI353 | Third Party SI / Service Provider |  | 2018-01-26 | 2018-01-26 | 2017-11-30 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4555 | 1. Start-Up (Progressing through change governance) |  | Provision of a web portal to enable GDNs to access customer contact details | CP | LIVE | Y2 - ROM completed | 27.03% |  |  | Data Office | 2017-12-06 | Richard Pomroy | Murray Thomson |  |  | Third Party SI / Service Provider |  | 2018-02-20 | 2018-03-26 | 2018-02-20 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | No Change Beneficiary | FALSE | TRUE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4596 | 2. Change sanction/approved and in project delivery |  | Setup of File Transfer mechanism from BO to IX | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | Data Office | 2018-01-23 | Steve Concannon | Donna Johnson | 50 |  | Minor Enhancements Team | XO3647 | 2018-08-30 | No Date | 2018-04-30 | IX | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4689 | 2. Change sanction/approved and in project delivery |  | Aggregate Energy AQ Report | CR (Internal) | LIVE | D1 - Change in delivery | 28.83% |  |  | Data Office | 2018-06-04 | Lee Jackson | Jo Duncan |  |  | Xoserve Resource |  | 2018-07-15 | No Date | 2018-07-01 | BW | AQ | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4473 | 3. Change delivered, awaiting closure approval/sign-off |  | Sybase NLS Solution Design Gap | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 24.62% | TBP | Low | Data Office | 2017-04-11 | Lee Chambers | Jo Duncan |  | UKLP IADBI317 | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4354 | 3. Change delivered, awaiting closure approval/sign-off |  | Request for New DNO Report Nested CSEPs Hierarchy Report | CP | LIVE | F2 - CCR awaiting ChMC approval | 33.03% |  |  | Data Office | 2017-09-01 | Cadent Gas /Emma Smith | Jo Duncan | 50 |  | Minor Enhancements Team | XOS3577 | 2018-05-15 | 2018-05-22 | 2018-02-23 | BW | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-10 | 2018-03-07 | 2018-03-07 | No Date
4634 | 1. Start-Up (Progressing through change governance) |  | Data Catalogue | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 21.02% |  |  | Data Office | 2018-03-21 | Rachel Hinsley | Dave Addison |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2019-02-01 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4357 | 3. Change delivered, awaiting closure approval/sign-off |  | Offline Systems Database D096 Phase 3 | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 25.23% |  |  | T & SS | 2017-09-04 | Sandra Dworkin | Donna Johnson | 50 |  | Minor Enhancements Team | XO3559 | 2018-04-30 | 2018-04-12 | 2018-03-31 | Other | Invoicing | 0-30days | TRUE | Xoserve | Daily | One | Low | 2019-12-01 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4567 | 2. Change sanction/approved and in project delivery |  | Amendment to plot to postal report | CR (Internal) | LIVE | D1 - Change in delivery | 30.03% |  |  | Data Office | 2018-01-02 | Tahera Choudhury | Jo Duncan |  |  | Xoserve Resource |  | 2018-08-30 | No Date | 2018-02-28 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4571 | 2. Change sanction/approved and in project delivery |  | MAM and MAP asset data analysis and reporting | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% |  |  | Data Office | 2018-01-03 | Andy Miller | Jo Duncan |  |  | Xoserve Resource |  | 2018-06-29 | No Date | 2018-03-23 | BW | Reads | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4570 | 2. Change sanction/approved and in project delivery |  | BW Reports - RA/ RANTS Reporting Logic | CR (Internal) | LIVE | D1 - Change in delivery | 28.83% |  |  | Data Office | 2017-01-03 | Michael Maguire | Jo Duncan | 50 |  | Minor Enhancements Team | XO3639 | 2018-09-20 | No Date | 2018-01-31 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4590 | 2. Change sanction/approved and in project delivery |  | SLSP - Incorrect Seasonal Large Supply Point charging | CR (Internal) | LIVE | D1 - Change in delivery | 43.24% |  |  | Data Office | 2018-01-12 | Carole Elwell | Donna Johnson | 50 |  | Minor Enhancements Team | XO3644 | 2018-10-22 | No Date | 2018-08-31 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-03-31 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | TRUE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4592 | 2. Change sanction/approved and in project delivery |  | BIRST work item inclusion & multiple daily updates | CR (Internal) | LIVE | D1 - Change in delivery | 35.74% |  |  | Data Office | 2018-01-23 | Jo Duncan | Jo Duncan |  |  | Xoserve Resource |  | 2018-06-29 | No Date | 2018-06-29 | Birst | SPA | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 2018-03-30 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4594 | 2. Change sanction/approved and in project delivery |  | Customer Inclusion for BIRST Exceptions | CR (Internal) | LIVE | D1 - Change in delivery | 28.83% |  |  | Data Office | 2018-01-23 | Jo Duncan/Thomas Elce | Jo Duncan |  |  | Xoserve Resource |  | 2018-08-30 | No Date | 2018-03-23 | Birst | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-03-30 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4636 | 2. Change sanction/approved and in project delivery |  | ASR – AS20180277 ENGIE Enhanced Portfolio shipper pack (VOL) | CR (ASR) | LIVE | D1 - Change in delivery | 28.83% |  |  | Data Office | 2018-03-26 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-08-30 | No Date | 2018-05-25 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4638 | 2. Change sanction/approved and in project delivery |  | ASR – NGS Asset AS20180274 | CR (ASR) | LIVE | D1 - Change in delivery | 31.23% |  |  | Data Office | 2018-03-26 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-28 | No Date | 2018-06-29 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4653 | 1. Start-Up (Progressing through change governance) |  | National Grid Transmission iConversion Project | CR (ASR) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 25.83% |  |  | T & SS | 2018-04-24 | Greg Causon | Emma Rose |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-01 | Gemini | Other | 30-60 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | FALSE | TRUE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4675 | 1. Start-Up (Progressing through change governance) |  | Digital signage Links for Birst Connectivity | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 27.63% |  |  | Data Office | 2018-05-17 | Jo Duncan | Jo Duncan |  |  | Xoserve Resource |  | 2018-06-30 | No Date | 2018-06-30 | Birst | Other | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3457 | 3. Change delivered, awaiting closure approval/sign-off |  | Solution to meet the obligations of UNC MOD 425V & UNC MOD455 | CP | LIVE | F1 - CCR/Closedown document in progress | 32.43% |  |  | T & SS | 2014-08-28 | Joanna Ferguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2015-07-09 | 2015-07-09 | 2000-02-02 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | TRUE | FALSE | Service Area 1: Manage Supply Point Registration | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2014-09-03 | 2015-01-19 | 2015-01-26 | No Date
4110 | 3. Change delivered, awaiting closure approval/sign-off |  | Creation of a Service to Release Domestic Consumer Data to W’s & TPI’s | CP | LIVE | F1 - CCR/Closedown document in progress | 31.23% |  |  | T & SS | 2016-10-12 | Jo Ferguson | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2017-07-31 | 2017-07-31 | 2000-02-02 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | Five to Twenty | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | 2017-05-11 | No Date
3390 | 3. Change delivered, awaiting closure approval/sign-off |  | Billing History by all NTS capacity / commodity related charges (2003 - 2013) | CP | LIVE | F1 - CCR/Closedown document in progress | 28.83% |  |  | T & SS | 2014-05-16 | Sean McGoldrick | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2014-10-08 | 2014-10-08 | 2000-02-02 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 8: Credit Risk Management (including Cash Collection) and Management of Neutrality Accounting Processes | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3428 | 3. Change delivered, awaiting closure approval/sign-off |  | Correction of CWV data on the National Grid Operational website as a result of incorrect weather flows for NE LDZ | CP | LIVE | F1 - CCR/Closedown document in progress | 31.23% |  |  | T & SS | 2014-06-18 | Joanna Ferguson | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2014-06-23 | 2014-06-23 | 2000-02-02 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 15: Demand Estimation | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4009 | 3. Change delivered, awaiting closure approval/sign-off |  | Billing History by all NTS capacity / commodity related charges (applicable dates in 2014 to Nexus implementation) | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2016-04-12 | Beverley Viney | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2017-07-19 | 2017-07-19 | 2016-06-30 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4043 | 2. Change sanction/approved and in project delivery |  | DN Sales Outbound Services | CP | LIVE | D1 - Change in delivery | 33.63% |  |  | T & SS | 2016-05-26 | Chris Warner | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-06-29 | No Date | 2016-10-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 19: Network Operator and User Relationship Management | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4149 | 2. Change sanction/approved and in project delivery |  | NG Gateway Migration | CP | LIVE | D1 - Change in delivery | 40.54% |  |  | T & SS | 2016-11-28 | Beverley Viney | Rachel Addison |  |  | Third Party SI / Service Provider |  | 2018-10-15 | No Date | 2018-03-31 | Other | Other | 100+days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 19: Network Operator and User Relationship Management | One | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-07-19 | No Date | No Date | No Date
4376 | 2. Change sanction/approved and in project delivery |  | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | CP | LIVE | D1 - Change in delivery | 28.83% |  |  | T & SS | 2017-09-22 | Chris Gumbley/Darren Lond | Nicola Patmore |  |  | Third Party SI / Service Provider |  | 2018-11-15 | No Date | 2019-01-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-12 | No Date | 2017-12-13 | No Date
4550 | 1. Start-Up (Progressing through change governance) |  | Gemini Re-platform | CP | LIVE | B4 - EQR In progress | 19.22% |  |  | T & SS | 2017-12-04 | Phil Hobbins | Hannah Reddy |  |  | Third Party SI / Service Provider |  | 2020-01-01 | No Date | 2020-01-01 | Gemini | No Process | 60-100 days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 20: UK Link Gemini System Services | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-12-13 | No Date | No Date | No Date
4632 | 1. Start-Up (Progressing through change governance) |  | Analysis for Gemini Enhancements | CP | LIVE | C1 - Delivery Business Case/BER in progress | 36.34% |  |  | T & SS | 2018-03-19 | Celine Reddin/Beverley Viney | Hannah Reddy |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-20 | Gemini | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | FALSE | FALSE | Service Area 20: UK Link Gemini System Services | One | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-04-11 | 2018-05-09 | No Date | No Date
3907 | 3. Change delivered, awaiting closure approval/sign-off |  | Server Migration Support Project | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 27.63% |  |  | T & SS | 2015-12-03 | Emma Rose | Emma Rose |  |  | Third Party SI / Service Provider |  | 2017-01-13 | 2017-01-13 | 2015-12-08 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3151.1 | 3. Change delivered, awaiting closure approval/sign-off |  | Business to Xoserve to Business File Transfer Capability | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2014-01-16 | Lee Chambers | Jon Follows |  |  | Third Party SI / Service Provider |  | 2014-09-29 | 2014-09-29 | 2014-04-01 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3143 | 2. Change sanction/approved and in project delivery |  | COR3143 - Decommission XFTM & Server Farm & re-direct NG files Phase 1 | CP | LIVE | D1 - Change in delivery | 21.02% |  |  | T & SS | 2013-08-06 | Khawar Ahmed | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-07-31 | No Date | 2015-10-27 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3447 | 2. Change sanction/approved and in project delivery |  | COR3447 - XP1 Decommissioning | CP | LIVE | D1 - Change in delivery | 21.02% |  |  | T & SS | 2014-07-08 | Chris Fears | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-07-31 | No Date | 2000-02-02 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4216 | 2. Change sanction/approved and in project delivery |  | API Platform Implementation | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | Data Office | 2017-02-03 | Gareth Hepworth | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-06-30 | No Date | 2017-12-10 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4349 | 2. Change sanction/approved and in project delivery |  | Control-M/EM, Server and agent upgrade for Gemini and CMS | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% |  |  | T & SS | 2017-08-18 | Annie Griffith | Emma Rose |  |  | Third Party SI / Service Provider |  | 2018-12-29 | No Date | 2018-07-31 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4324 | 2. Change sanction/approved and in project delivery |  | Checkpoint Hardware Upgrade | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | T & SS | 2017-06-29 | Chris Fears | Tony Long |  |  | Third Party SI / Service Provider |  | 2018-07-06 | No Date | 2017-12-01 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4325 | 2. Change sanction/approved and in project delivery |  | Cisco Security Upgrade | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | T & SS | 2017-06-29 | Chris Fears | Tony Long |  |  | Third Party SI / Service Provider |  | 2018-07-06 | No Date | 2018-02-02 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4562 | 2. Change sanction/approved and in project delivery |  | Testing Lifecyle Improvements | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | T & SS | 2017-12-18 | Andy Simpson | Debi Jones |  |  | Third Party SI / Service Provider |  | 2018-12-31 | No Date | 2018-03-31 | Other | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4440 | 2. Change sanction/approved and in project delivery |  | Npower MPRN Information report | CR (ASR) | LIVE | D1 - Change in delivery | 31.83% |  |  | Data Office | 2016-08-04 | Emma Partlett | Jo Duncan |  | UKLP IADBI246 | Xoserve Resource |  | 2018-08-28 | No Date | 2018-04-27 | BW | Other | 31-100days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
2831.2 | 3. Change delivered, awaiting closure approval/sign-off |  | DSP Gateway Mechanism Analysis & Design | CP | LIVE | F1 - CCR/Closedown document in progress | 25.23% |  |  | T & SS | 2012-11-21 | Joanna Ferguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2014-04-16 | 2014-04-16 | No Date | Other | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | All UK Gas Market Participants | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3151 | 3. Change delivered, awaiting closure approval/sign-off |  | Communications Link Solution for Provision of Smart Meter Data from iGT's to Xoserve | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 27.63% |  |  | T & SS | 2013-08-15 | Lee Chambers | Jon Follows |  |  | Third Party SI / Service Provider |  | 2014-09-01 | 2014-09-01 | 2014-04-30 | ISU | Other | 100+days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
2831.4 | 3. Change delivered, awaiting closure approval/sign-off |  | Smart Metering UNC MOD 430: DCC User Gateway Network | CP | LIVE | F1 - CCR/Closedown document in progress | 9.009% |  |  | T & SS | 2014-03-13 | Jo Ferguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2016-09-22 | 2017-09-22 | No Date | ISU | Other | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4635 | 2. Change sanction/approved and in project delivery |  | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service (Number) | CP (Non System Impacting) | LIVE | D1 - Change in delivery | 29.13% |  |  | T & SS | 2018-03-21 | Charlie Hayley | Dene Williams |  |  | Xoserve Resource |  | No Date | No Date | No Date | Other | Portal | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | TRUE | TRUE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-06-13 | No Date | No Date | No Date
4643 | 1. Start-Up (Progressing through change governance) |  | Shipper Read Performance Reporting | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 47.15% |  |  | Data Office | 2018-04-03 | Rachel Hinsley | Jo Duncan |  |  | Xoserve Resource |  | 2018-06-30 | No Date | 2018-06-30 | BW | Reads | 30-60 days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Participants | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4647 | 2. Change sanction/approved and in project delivery |  | IS Operations - Service Management Performance Birst Dashboards | CR (Internal) | LIVE | D1 - Change in delivery | 27.03% |  |  | Data Office | 2018-04-13 | Luke Moise | Jo Duncan |  |  | Xoserve Resource |  | 2018-07-06 | No Date | 2018-05-15 | Birst | Other | 0-30 days | TRUE | Xoserve | Daily | One | Low | 2018-05-15 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4650 | 1. Start-Up (Progressing through change governance) |  | M-Number DVD Automation | CR (Internal) | LIVE | C1 - Delivery Business Case/BER in progress | 40.24% |  |  | Data Office | 2018-04-17 | Mark Pollard | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-08-30 | No Date | 2018-05-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | One | Medium | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4656 | 1. Start-Up (Progressing through change governance) |  | Customer Instant Feedback Mechanism for KVI Reporting | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 36.34% |  |  | T & SS | 2018-04-24 | Adam Jones | Dene Williams |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-01 | Other | Other | 30-60 days | TRUE | Xoserve | Daily | Two to Five | Low | 2018-12-28 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4697 | 1. Start-Up (Progressing through change governance) |  | Amendment Invoice - High Financial Values report from BIRST | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 26.43% |  |  | Data Office | 2018-06-06 | Dan Donovan | Jo Duncan |  |  | Xoserve Resource |  | 2018-07-30 | No Date | 2018-07-31 | Birst | Invoicing | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2019-02-26 | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | Service Area 23: Internal | One | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date