## Slide 1: Xoserve IX Refresh
Customer Overview Pack – August 2018

## Slide 2: IX Site Survey
Have you got all of the site information required
We issued site surveys to all of our customers in May and have been busy working with you over these past few weeks to obtain your site information.
As of the 27th July, we have received 140 completed responses (82%), and 27 (19%) of you are in contact with us and we hope to have your site information soon. We have yet to achieve contact with just 3 sites (2%) but we are still actively pursuing contact. If you would like to check whether your survey has been submitted, please contact us at box.xoserve.IXEnquiries@xoserve.com or call 0121 623 2773
We will not be actively chasing site responses after 31st July. Those we receive after this point will be planned in at the end of roll-out plan.

## Slide 3: Hardware Installations – Circuits
What’s the progress with the installations?
We have now issued communications to those customers included in the first batch of circuit installations. These are sites for which we have received a completed site survey and have little or no access requirements. The communication provides a high-level view of activities for your installation - based on your IX Option (see Appendix A).
The circuit installation appointments for these sites are now being issued from Gamma, and work has commenced from 23rd July. Statistics for these appointments (successful, failed, follow up appointments needed, etc.) will be available as we progress through the plan.
What if I haven't yet received a communication or appointment
We are still in the process of planning site visits, continuing to prioritise those sites with few access requirements. It may also be that we are still awaiting your Site Survey.
Those customers who have received a site communication can expect an appointment from Gamma (GNS Project Provisioning) to follow shortly. Please accept the appointment date if you are able to grant access to the BT OpenReach engineer on that day, otherwise, you will need to reject the appointment with a reason and confirm suitable dates for your circuit installation.

## Slide 4: Next Steps
Pursue the last few Site Surveys from organisations
First batch of New Circuit Installation & Connectivity Testing
July
Aug
Aug
Sep
Further planning and checking Site Access Requirements
Second batch of New Circuit Installation & Connectivity Testing

## Slide 5: Appendix A: IX Service Line Options
Xoserve are replacing your IX kit on a ‘like for like’ basis, therefore your replacement IX service option and contract will match the IX option you currently have, which will be one of the following:
Option 1 - Primary ADSL and Back-Up ADSL connection
Option 2 - Primary EFM and Back-Up ADSL connection
Option 3 - EFM Primary and EFM Back-Up connection
Option 4 - Primary Fibre/ Ethernet and Back-Up ADSL connection
The following slide displays the on-site installation process; the number of site visits that are required is dependant upon your IX service line option complexity.

## Slide 6: Appendix B: Your Customer Journey
The number of days required to complete the activity will be dependant upon your IX Service option
Circuit Installations
Router Installation
Server Installation
Legacy Kit
Decommissioning
IX Survey Response
Up to 4 Hours Service Interruption
Engineer(s) will visit your site to install new circuits; the number of site visits and the access method will vary according to your IX service option and site complexity
The Router Installation will take place in one site visit
The new server will be installed with the existing Vodafone server still in situ to enable a fall-back position. Where rack space concerns exist, we will address this on a case by case basis
Comms
Comms
Comms
Comms
Your survey responses are being used to define the roll-out plan
Your old service will be removed and wiped by Vodafone and disposed of in accordance with regulations
Day 1
A number of remote off-site activities also take place to assess your site’s requirements and to set-up and test connections and configure hardware
Key:
Site Visits
Notes
Xoserve and Gamma will communicate with you directly to agree your installation dates
Comms