## Slide 1: DSC ChMC CSS update 12th September 2018

## Slide 2: Ofgem Switching Programme – Consequential update
CSS Consequential
  We are on target to complete level 2 analysis as planned at the end of September
  The external BRDs split by Customer group are on track for completion and publication at the end of October
  DSG members have agreed to Xoserve’s request to hold a specific CSS Consequential session. It was agreed that the planned DSG meeting on the 15th October will be split into two parts, the normal DSG workgroup and the CSS Consequential discussions. Invites will be issued for this meeting shortly.
  I really want to take the opportunity during the session on the 15th for the meeting to be informative and as interactive as possible. Using the capture phase of the change process to evaluate solution options and agreeing preferred direction together. My aim is for our Customers to leave this meeting with an understanding of CSS Consequential which helps your own analysis for the consequential changes to your own system and processes.
  I am currently planning on running through the following artefacts during the session:
    As Is Process Models
    To Be Process Models
    Level 1 and Level 2 Heat Maps
    Shipper BRD as an example
  Please let me know if you feel there is anything further at this stage of the project Xoserve can provide to help our Customers’ analysis for the consequential changes to their own systems and processes

## Slide 3: Ofgem Switching Programme – Consequential update
CSS Bid
Phase 1 (Mod0666)
  The modification was granted Urgent status, which means the modification follows an enhanced timeline
  One workgroup was held on the 28th August. During this workgroup the legal text was presented and agreed. Workgroup attendees approved for the modification to be issued for consultation
  Consultation commenced on the 30th August and closes out for representations on the 6th September
  The final modification report will be available for panel on the 10th September with panels recommendation being issued to Ofgem on this date
  Ofgem decision will be made on the 13th September
Phase 2 Modification
  Xoserve are raising a second modification. This modification will seek to modify FGO governance to enable Xoserve to enter into a contract to provide CSS Services to DCC if selected.
  We are aiming for this modification to be presented at Octobers mod panel

## Slide 4: Engagement Activities
 | 27/08 | 03/09 | 10/09 | 17/09 | 24/09 | 01/10 | 08/10 | 15/10 | 22/10 | 29/10 | 05/11 | 12/11 | 19/11
Meetings |  |  | ChMC |  |  |  | ChMC |  |  |  | ChMC |  | 
 |  |  |  | CoMC |  |  |  | CoMC |  |  |  | CoMC | 
 |  | CSS/OSP |  |  |  |  | CSS/OSP |  |  |  | CSS/OSP |  | 
 |  |  |  |  |  |  | DSGC | DSGC |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  | CSSC |  | CSSC | CSSC
 |  |  | 1-2-1’s | 1-2-1’s | 1-2-1’s | 1-2-1’s | 1-2-1’s | 1-2-1’s | 1-2-1’s | 1-2-1’s |  |  | CSS Day?
Products |  |  |  |  |  |  |  |  |  | BRD’s Publish |  |  | 
 |  |  |  | As Is Models |  |  |  |  |  |  |  |  | 
 |  |  |  | To be Models |  |  |  |  |  |  |  |  | 
Mods | Phase 1 Work group |  | Phase 1 Approval |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | Phase 2 Publish |  | Phase 2 Work group |  | Phase 2 Workgroup |  | Phase 2 Workgroup | 
= Milestones