## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements.
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | Still undertaking discussions at DSG. We are looking at several distibution mechanisms and will test how the Change Pack process would work for each one.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | ANT File Format Change Pack | 2074.1 - RJ - RH | 2018-09-14 | 2018-09-28 | 2018-10-02 | X |  |  |  |  | TBC | 2018-10-10 | 2018-11-02 | 1 representation comment received in support

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 23rd July
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4525 | NA | Transparency of Rolling AQ Reports | 2043.5 | 2018-08-10 | 2018-08-24 | NA | X |  |  |  |  | NA | 2018-09-12 | 15th Working day each month from September 2018 | The CP confirmed the delivery and mechanism for the suite of reports. No representation comments were received.
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | Change Management Committee important dates 2019 | 2043.1 | 2018-08-10 | 2018-08-24 | 2018-08-30 | X | X | X | X | X | 2060 | 2018-09-12 | NA | Communication detailing ChMC dates, change pack dates, DSG dates and the three industry proposed release dates: Friday 1st March 2019 Friday 28th June 2019 Friday 1st November 2019 1 representation received confirming release dates

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
Outage Notification of Autumn Clock Change | UK Link | 2018-10-28 | 2:00 | 2018-10-28 | 05:00 (GMT) | System clocks change back to GMT at the normal time of 02:00 am UK BST | 2018-10-10
| Gemini | 2018-10-28 | 2:00 | 2018-10-28 | 05:00 (GMT) | System clocks remain on UK BST until 04:30 am (3:30 am UK GMT) when they change back one hour to GMT
| CMS | 2018-10-28 | 2:00 | 2018-10-28 | 05:00 (GMT) | System clock remain on UK BST until 04:30 am (03:30am UK GMT) when they change back one hour to GMT