## Slide 1: Release 3 Update
November 2018

## Slide 2: XRN4572 – UK Link Release 3
30th Oct 2018 |  | Overall Project RAG Status |  |  | G
 |  | Plan/Time | Risks and Issues | Cost | Resources
RAG Status |  | G | A | G | G
Status Explanation |  |  |  |  | 
Objective | Full project delivery of UK Link Future Release 3 Scope |  |  |  | 
Plan/Time | The progress against each track is as below:- Track 1 (13 Changes) – IDR successfully completed and Go Live readiness in place for Cutover activities commencing 2nd Nov Track 2 (XRN 4454) – Synergised Acceptance Testing underway and on track to complete in time for MT commencement. Certain BW elements may need extra contingency time Track 1 IDR successful - Implementation approach and file level transition plan published to participants. Cadent MT registration complete. MT information Inc. high level scenarios and MT approach being presented at DSG for MT starting 19th November. |  |  |  | 
Risks and Issues | Issue against XRN 4534 - resolution being prioritised within Xoserve Project and Production teams for a plan of delivery Complete All System and Acceptance Testing on time for XRN 4454 to ensure Cadent MT entry on time (being managed) |  |  |  | 
Cost | Full Delivery costs approved at ChMC in April 2018. Revision expected to accommodate XRN 4454 delivery date (ongoing discussions) |  |  |  | 
Resources | Additional resource support to deliver XRN 4454 in place SME resource requirements for Build, ST and AT phases is being managed weekly with internal Xoserve teams. |  |  |  | 

## Slide 3: UK Link Release 3 - Plan
Primary Scope | Scoping |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding | Initiation | Analysis and HLD | Detailed Design | Build & System Test | Acceptance Test | Performance Test | Market Trials | Regression Test | Imp. | PIS
Track 1 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 04/06/18 | 13/08/18 | 07/09/18 | 19/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 1 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 04/06/18* | 13/08/18 | 07/09/18 | 25/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 2 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 30/06/18* | 24/09/18 | 05/11/18 | N/A | 14/12/18* | 18/01/18 | 01/02/19 | 08/03/19
Track 2 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 30/06/18* | Build Complete ST synergised with AT | 19/11/18** | N/A | 14/12/18* | 18/01/18 | 01/02/19 | 08/03/19
RAG Key – Milestones are end dates;
*Closedown expected to finish this week ** Synergised ST and AT date
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed