## Slide 1: June 19 Timelines
Key Upcoming Dates:
Design Change Packs, Extraordinary Issue Date – 23rd Nov
  10 Day Review Period Completion (Excluding Bank Holidays) – 7th December
  5 Day Xoserve Response Period Completion – 14th December
  5 Day Notice of ChMC Materials – 3rd January
Design Change Packs Approved – 9th January
“6” Month Notice of June 28th Implementation – 9th January
BER Approved – 9th January at ChMC

## Slide 2: June 19 - Status Update
29th October 2018 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Design: Detailed Design activity is underway for the 3 XRNs agreed at ChMC on October 10th : 4670, 4676 and 4687. Change packs are due to be delivered extraordinarily on the 23rd of November, in order to meet the 28th of December deadline for providing 6 months’ notice of implementation. The title of the changes are: 4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date. 4676: Reconciliation issues with reads recorded between D-1 and D-5. 4687: PSR Updates for Large Domestic Sites. A baselined plan for all subsequent lifecycle stages will be provided at the end of the Design phase, and will be provided to the ChMC on December 12th |  |  | 
Risks and Issues | Currently tracking green from a risk perspective given that the project has only just mobilized. All risks will be regularly monitored throughout the project lifecycle |  |  | 
Cost | High-level, estimated, costs for each change were provided within the HLSOIAs. The BER is set to be approved by ChMC on January 9th |  |  | 
Resources | Weekly monitoring of SME resources ongoing |  |  |