## Slide 1: Change Management Committee – November 2019 Release Update
Nov 7th 2018

## Slide 2: November 19 Headlines
All 11 changes indicatively allocated to November 2019 are still progressing through the Capture phase:
  1 change (XRN 4621) is currently undergoing ‘High-Level Solution Option Impact Assessment’ (HLSOIA).
  6 changes (XRNs 4691, 4692, 4693, 4694, 4044, 4725) have completed HLSOIA. 4679 is under review.
  A further 3 changes (XRNs 4753, 4777, 4738) are in Requirements Gathering with the aim of progressing to HLSOIAs in time for 12th December ChMC. There is a risk that some of these changes may not be mature enough for assessment in time for the December ChMC.
As the preferred solution option for each change needs to be agreed, prior to being formally assigned to the November 19 Release, there is a tight timeframe to ensure that all changes are in a position to be agreed in the December 12th ChMC.
An extraordinary ChMC may also be required, following December’s ChMC, to approve the EQR for the progression of Design. Further analysis is underway by Xoserve to understand whether this is required or not, an update will be provided ASAP.

## Slide 3: Change Index
 | XRN | Change Title | Current Capture Status | Complexity | Impacted Parties | HLSOIA Due | Target Issue Date for Solution Packs | Target DSG Session to Confirm Preferred Option | Target Close-Out Date for Solution Packs | Target ChMC Session to Confirm Preferred Option & inclusion in Nov ‘19 release
 | 4691 | CSEPs: IGT and GT File Formats (CGI Files) | Undertaking HLSOIA | Medium | DN | Completed | N/A | Completed | N/A | Pending
 | 4692 | CSEPs: IGT and GT File Formats (CIN Files) | Undertaking HLSOIA | Medium | DN | Completed | N/A | Completed | N/A | Pending
 | 4693 | CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | Undertaking HLSOIA | High | DN | Completed | N/A | Completed | N/A | Pending
 | 4694 | CSEPs: IGT and GT File Formats (Create new data validations ) | Undertaking HLSOIA | High | DN | Completed | N/A | Completed | N/A | Pending
 | 4044 | Extension of ‘Must Read’ process to include Annual Read sites | Completed HLSOIA | Low | Cadent Gas | Completed | Out of Scope for Nov 19 Release |  |  | 
 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | Undertaking HLSOIA | Medium | Xoserve | Completed | N/A | tbc | *23/11/2018* | 12/12/2018
 | 4725 | New Read Reason Type for LIS estimate readings | Undertaking HLSOIA | Medium | Shippers | Completed | N/A | tbc | *09/11/2018* | 12/12/2018
 | 4621 | Suspension of the validation between meter index and unconverted index | Capture workshops in progress | TBC | Shippers | 15/11/18 | N/A | tbc | *23/11/2018* | 12/12/2018
 | 4753 | CMS - increase information provided in QCL response file | Capture workshops in progress | TBC | IGT / GT | TBC | `TBC | TBC | TBC | TBC
 | 4777 | Acceptance of contact details updates | Capture workshops in progress | TBC | Shippers | TBC | TBC | TBC | TBC | TBC
 | 4738 | Shipper Portfolio update of proposed formula year AQ/SOQ | Capture workshops in progress | TBC | Shippers | TBC | TBC | TBC | TBC | TBC
*Extraordinary change pack issue required.