## Sheet1
ISSUES LOG
| REF | Name | Description | issue type | Related Risk | Issue Priority | Issue severity | Date raised | Status | Actions | Review deadline | resolution | date resolved | NOTES
| 1 | Incorrect correction factors held for sites with an AQ of >732,000 | Sites with an AQ of greater than 732,000 are registered as having a standard correction factor | PARR observation (2A.9 Standard CF AQ>732,000kwh) | PACR016 |  |  | 2018-11-05 | In progress | Performance improvement letters sent | 2018-03-12
| 2 | High number of estimated reads being used in settlement in PC1 and PC2 | PARR report 2A.1 has confirmed that a high number of estimated meter reads are being used for settlement. In some cases 100%. | PARR observation (2A.1 Estimated and check reads) | PACR003 |  |  | 2018-11-20 | In progress | Performance improvement letters sent | 2018-03-12
3