## Slide 1: UKL Future Release 3
XRN4534 Deployment Options
December 2018

## Slide 2: Option Timelines
w/c | 3 Dec | 10 Dec | 17 Dec | 24 Dec | 31 Dec | 7 Jan | 14 Jan | 21 Jan | 28 Jan | 4 Feb | 11 Feb | 18 Feb | 25 Feb | 4 Mar
Option 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Option 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Option 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
AT
RT
IDR / Cutover
AT
RT
IDR / Cutover
Cont.
AT
RT
IDR / Cutover
Cont.

## Slide 3: Current options RAID & Platform View
 | Go Live Date | RAID |  | Platform View
 |  | Negative | Positive | 
1 | 1st Feb | 10th December assumes best case dates for remaining BAU defect fixes - no contingency IDR planned for 23/24th January - no contingency 3 weeks is bare minimum for AT and RT - no contingency for defects Very little allowance made for Christmas holidays, assuming work can be carried out on all non-bank holidays Creates dependency between this and Cadent which creates additional risk to the Cadent deployment | Deploys with rest of R3 track 2 - same governance, IDR, cutover etc. Full PIS window in line with R3 track 2 | There is a high probability of finding additional existing production defects during AT so given the time constraints, this is a very high risk option
2 | 16th Feb | Falls in line with Minor Release Drop 3 and adds dependency and risk to that deployment Allows no contingency against 3 week RT window for defect resolution. Still some potential dependency between this and Cadent deployment | Falls in line with Minor Release Drop 3 so governance would be streamlined Includes additional week contingency between AT and RT for code merge into MiR track Still allows 3 weeks of PIS before end of release 3 PIS | Whilst timelines are improved and more achievable, added risk and dependency on MiR drop 2 is undesirable
3 | 23rd Feb | Requires independent deployment governance around CAB etc Only allows 2 weeks of PIS before end of Release 3 PIS Still some potential dependency between this and Cadent deployment | Includes additional week contingency in each of AT and RT plus one full week in between for defect resolution. Removes any dependency and therefore risk on MiR drop 3 deployments Reduced dependency and therefore risk on Cadent deployment | Preferred to 16th Feb option in light of RAID

## Slide 4: Recommendation
The Xoserve Project team recommend that we continue to aim for deployment on 1st February with a contingency of moving to 23rd February endorsed by ChMC. This contingency can then be used if additional production defects are identified during testing or other dependencies and risks materialise.
If the impact of additional production defects uncovered are such that 23rd February is at risk then further engagement will be required at ChMC

## Slide 5: Contingency options beyond February 19
All options for February deployment carry a degree of risk based on potential to discover further defects in testing and also because of the need to protect Cadent delivery. Alternatives beyond February are:
Operationally, deployment would be possible in March but this would require project resource extensions to support deployment and PIS independent of Cadent
Alignment to June 19 release is possible but this would also require project resources to be available and would create a dependency and associated risk to that release
Beyond June 19 there is a Minor Release drop in July and a further major release proposed for November 19