## Slide 1: DSC ChMC CSS update 11th December 2018

## Slide 2: Ofgem Switching Programme – Consequential update
CSS Consequential Workgroups
We have completed two of our planned consequential workgroups. The workgroups have been well attended with good collaborative discussions around the topic areas.
As we have worked through the topics our first focus has been agreement and discussion of the business rules for the consequential UNC changes, with some high level design options discussed. We will continue discussions for the high level solution options during our forthcoming meetings.
We have scheduled in extra days in order to ensure we cover the full topic areas, therefore the schedule of meetings is now as follows:
  09th January 2019
  22nd January 2019
  TBC early February (date to be agreed with attendees on the 9th Jan)
  19th February 2019

## Slide 3: Ofgem Switching Programme – Consequential update
A timeline and plan will be provided prior to the Christmas break which will detail workshops and expected outputs for our consequential engagement activities.
Following each workgroup session the external BRDs will be updated with agreed/approved business rules and solution options, this principle was agreed at our first workgroup meeting.
Consequential Costs
The CSS Consequential Programme has been initiated. In order to progress project mobilisation activities including high level design and detailed design funding is required.
We will be submitting a request for release of funds at this months CoMC. This will allow us to progress with programme activities in order to meet programme timescales.

## Slide 4: Ofgem Switching Programme - Bid
CSS Bid
On the 28th November DCC announced their decision on which organisations to take forward to the next phase of the procurement process. I’m very pleased to confirm that Xoserve are one of the organisations selected.
This down-selection meant we were immediately into the next stage of the procurement process. On the 5th December, which was the first day of the demonstration evaluations, members of the Xoserve bid team presented a very strong delivery solution and delivery plan to DCC’s evaluation team. Our demonstration went really well, providing good strong coverage of solution and requirement understanding, resulting in the Q&A phase of the evaluation being fairly light.
We are now in the final phase of the process which involves preparing our Best and Final (BAFO). This has to be submitted on 2nd January 2019, this date has moved from the planned date of 21st December.
CSS Bid Group
Our next bid group is taking place on Monday 10th December. Agenda items for this meeting include:
  Draft assurance report
  Contract risk
  Contract budget risk range