## Slide 1: Change Proposals Capture to Delivery
December 2018

## Slide 2: Pre- Capture
XRN Closed
XRN Closed
Change Proposal (CP) raised
CP sent to Xoserve for initial processing and Xoserve Reference number (XRN)
Change proposed at DSC Change Management Committee (ChMC)
Change Approved
Sent for Initial Review
Change Rejected
Review Responses
Change Approved
Rejected
Initial Review can be 10, 20 or 30 working days
Xoserve starts
Capture Phase

## Slide 3: Capture
Requirements statement
Capture session
Define requirements
Capture session
Solution Options
XRN Closed
Requirements ratified
Requirements statement created and approved by CP’s proposer
Xoserve hold one or more capture sessions to define requirements
Requirements ratified with CP’s proposer and/or by DSC Delivery Sub Group (DSG)*
One or more capture sessions to evolve solution options
Solution options reviewed and evaluated at one or more DSG meetings*
The proposed Solution options go into Solution Option Assessment (SOA)
SOA may be reviewed at DSG prior to sending out for Solution Review
Responses
Solution Review 10 working days
Change Approved for Delivery
Change Rejected
CP handed to Xoserve project team for delivery
* May be presented/discussed at alternate groups e.g. PAC, UIG Workgroup

## Slide 4: Delivery
CP handed to Xoserve project team for delivery
Project Start up
Initiation and
Design
Planning & Design clarifications may be sought at one or more DSG meetings
EQR if needed
BER
Evaluation Quotation Report (EQR) and/or Business Evaluation Report (BER) for funding sent to at DSC ChMC for approval
XRN Closed
Change Rejected
BER Funding Approved
Detailed Design
Design Change Pack consultation
10 working days
If issues identified in responses to Design Change Pack - return to ChMC for further decision making
Design issues
EQR Approved
Design agreed
Build, and Test
Change added to Implementation plan and progress updates provided at ChMC and DSG
Training /
Awareness sessions
IDR and implementation
Closedown report approved at ChMC
Revisit Design
Design agreed

## Slide 5
E2E Change Process
Start Up
Planning and Design
Delivery
Implementation
Realisation
Start Up
Initiation
Design
Build
Test
Implementation
Closedown
Training
Stage:
Capture
Stage Gate
A
Stage Gate
B
Stage Gate
C
Stage Gate
D
Stage Gate
E
Stage Gate
F
Phase:
Capture Training Requirements
Capture Testing Requirements
Recommend Release
Type (i.e ME, Minor, Major)
Confirm funding arrangements
HL Customer Impact communicated
Recommend preferred
HL Solution Option
HL Cost & Delivery
Impact Assessment
Perform Privacy
Impact Assessment
Record change in
Central Register
Confirm Customer
Reqs / Consult
Define possible
Solution Options
Project Governance established
Agree Delivery Scope
(into Analysis/Design)
Project Initiation
Doc approved
Business Case
(Del.) approved
Target Delivery Timescales agreed
Business Case
(Design) approved
Initiation Funding
secured (e.g. EQR)
Mobilise delivery mechanisms (e.g. SI)
Del. mechanism established
Delivery Funding secured (e.g. BER)
Detailed Delivery Plan baselined
Environments /
Data provisioned
Test Plan
baselined
Training Needs Analysis complete
Training
Approach defined
Implementation Approach defined
Cust. Impacts communicated
Detailed Design approved
Non-Functional
Reqs baselined
Functional Reqs baselined
Test Execution Schedules defined
E2E Traceability finalised
Test Scenarios / Cases defined
Training Plan(s) defined
Training
Guides
Training
Delivery
Change Impact Assessment
SP to Live
Unit Testing
Tech
Specs
Performance Testing
Cutover Rehearsals
OAT
Penetration Testing
Regression Testing
UAT
Integration
Testing
System
Testing
PIS Approach and Exit Criteria defined
Ops Handover
Docs approved
Communicate
Imp Outcome
Update Industry
Documentation
Execute Go-Live / Cutover Plan
Conduct Delivery
Lessons Learnt
PIS Exit Criteria
achieved
Delivery Completion
Docs approved
Handover to enduring operations complete
Create Implementation Plan
Delivery Go/No-Go Criteria achieved
Industry Assurance
Commence change
Benefit Prioritisation
Customer
Change Initiative Entry
(Idea / MOD / CR / CP / ASR)
Tasks:
LEGEND
Major Customer Visibility / Engagement
Minor Customer Visibility / Engagement
No Customer Visibility / Engagement
* As presented at the Customer Day