## UNC Issue Register
UIG Workgroup: UIG Taskforce Recommendations Tracker Last Update:31/1/19
Issue Ref. | Issue Title | Issue Priority (H/M/L) | Status | Option (Taskforce recommendations in bold) | Level of Support (number) | Industry view on Option | Supporting Comments/Issues and blockers | Option/Action Owner | Next Steps/Actions/Timescales | Status Date | Status Summary/Update
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support
|  |  |  | 2. Engagement with Shippers – highlight the individual sites, provide support, encourage action to re-confirm. CDSP to monitor monthly and notify relevant Shippers | 17 | high |  | Xoserve | In Progress: Short to medium
|  |  |  | 3. PAC reporting and monitoring – add new reports to Performance Assurance Report Register | 13 | med | 1. Visibility required at PAC. | PAC | Xoserve to place on PAC agenda for further discusion. Medium (Mod 0660 now approved). Requires a CP to create reports
|  |  |  | 4. Notify Ofgem of individual sites and Shippers | 12 | med | 1. Possible a PAC role. | Xoserve | To be discussed with PAC first.
|  |  |  | 5. Improve NDM Profiles for EUC09, e.g. create WAR Band EUCs | 0 | No Support
|  |  |  | 6.UNC Mod: Reduce the qualifying period for Class 1 (currently 18 months or 6 consecutive calculations) | 0 | No Support
|  |  |  | 7. UNC Mod: CDSP automatically converts sites to Class 1 after qualifying period, CDSP arranges for fitting of Daily Read Equipment | 0 | No Support
|  |  |  | 8. UNC Mod: Use the UIG Weighting Factors to create a incentive to change to Class 1 (i.e. increased rate for Classes 2 to 4). | 0 | No Support |  |  | Long – UNC Mod timescales plus changes to AUG Table from next Gas Year. May also require system changes
|  |  |  | 9. UNC Mod: Create financial penalties for sites which have not been re-confirmed to Class 1 | 4 | low
|  |  |  | 10. UNC Mod: Automatically change meter read frequency to Monthly when AQ increases above 293,000 | 14 | med |  | Xoserve | Wait until after PAC discussions on other recommendations before seeking a sponsor. Long – UNC Mod timescales plus system changes
|  |  |  | 11. Ability for large sites to be in Class 2 before they are able to be Class 1 | 4 | low
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support
|  |  |  | 2. CDSP Analyse Read Rejections for asset mismatches. Highlight mismatched asset details to Shippers to review and either resubmit the read with the correct assets or the update the asset details on UK Link as appropriate. | 0 | No Support
|  |  |  | 3. CDSP NDM Sample validation – arrange site visits for a representative sample of the Xoserve managed sample sites to validate the daily read equipment is functioning normally and consistent with the physical asset setup on site and consistent with UK Link | 0 | No Support
|  |  |  | 4. CDSP to Review NDM Sample Site selection and validation process. This is underway following the implementation of UNC Modification 0645S (Mandating the provision of NDM Sample Data) | 0 | No Support
|  |  |  | 5. Xoserve defect resolution of issues impacting consumption calculations (BAU activity captured here for completeness) | 0 | No Support | 1. BAU so voting not required for continued support.
|  |  |  | 6. UNC Mod: CDSP Reconcile a representative sample of UK Link Asset Data (not the NDM Sample Data). Investigate mismatched asset details and update the appropriate user's records where necessary. This will give an indication of the potential level of asset data quality issues on UK Link. | 6 | low | 1. Can this be done from portfolio snapshot (SBl) - UNC 431 subject to permissions. |  | ACTION - to investigate 431 report (Workgroup does not believe it does) Low-Medium. Would potentially require UNC modification, sponsorship from shippers and / or the regulator and / or commercial arrangement with MAMs / the DCC / MRAs and or End User support
|  |  |  | 7a. UNC Mod: Asset Data Cleanse – CDSP to Reconcile entire UK Link Asset Data portfolio. Investigate mismatched asset details and update the appropriate user’s records where necessary. Assumes no approval of 0651 | 0 | No Support
|  |  |  | 7b Use UNC Mod 0651 - Changes to the Retrospective Data Update provisions reports if mod approved | 9 | med | 1. General comment - issue in relation to the need for data cleansing activities (LW). | Xoserve | To assess further following approval of 0651, to work out next steps
|  |  |  | 8. UNC Mod: Require validation of Meter Asset Details whenever an actual read taken by a Meter Read Agent. Mismatches flagged to the shipper for investigation and update where appropriate | 0 | No Support
|  |  |  | 9. UNC Mod/s: CDSP to obtain smart meter readings and asset data direct from the DCC rather than the shipper. Would also potentially need a data cleanse exercise to align asset data between the DCC and UK Link to minimise asset based read rejections | 2 | low |  |  | Would require multiple UNC Modifications, Changes to the Smart Energy Code and system / file flow changes
|  |  |  | 10. PAC investigation of read rejections reports | 4 | low | 1. New option proposed in meeting. | PAC | Although limited support it was suggested that it is taken to PAC for discussion/completeness.
1 | Use of estimates for Daily Metered (DM) Sites | High | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support
|  |  |  | 2. Engagement with DMSPs – monitor read rejections for Class 1. Resurrect previous initiatives to monitor and help resolution Engagement with Shippers – monitor read rejections for Class 2. Provide encouragement for action to be taken. CDSP to monitor monthly and notify relevant Shippers/DMSPs | 13 | med |  | Xoserve | Low to medium – requires Shipper/DMSP co-operation If UNC Mod 0647 goes ahead (Opening Class 1 Reads to Competition) could Class 1 read performance drop further?
|  |  |  | 3. Notify Ofgem of individual sites and associated Shippers | 13 | med |  | Xoserve | Low to medium – requires Shipper co-operation unless Ofgem can apply any financial leverage
|  |  |  | 4. PAC reporting and monitoring – PAC to engage with Shippers on basis of existing and/or new reports in Performance Assurance Report Register. Consideration of any additional reporting to PAC |  | No Support | 1. BAU as part of PAC reporting. | PAC | Although no support it was suggested that it is taken to PAC for discussion/completeness.
|  |  |  | 5. UNC Mod: Review DMSP read incentive framework (Class 1) | 2 | low
|  |  |  | 6. UNC Mod:Reduce the duration for the Class 2 Must Read trigger & extend to include Class 1 | 5 | low | 1. Option challenged by GDNs as there is already an obligation to provide reads(CW). 2. Monthly must read could work where there is an asset failure - would need a mod (CW). 3. Does not have long lead time (CW).
|  |  |  | 7. UNC Mod: Introduce incentives or liabilities for low submission rates for Class 2, and/or extend Class 1 liabilities to apply to Shippers | 11 | med | 1. npower mod is it going to be withdrawn? 2. Recommendation to inlcude with option 8. | PAC | SCP to progress 0674 that gives powers to PAC and step 2 is for PAC to consider introducing such an incentive UNC Mod timescales plus system changes
|  |  |  | 8. UNC Mod: CDSP obtains reads by installing AMR | 0 | No Support | 1. Recommendation to consider with 7.
|  |  |  | 9. UNC Mod: Amend the industry processes to allow CDSP to obtain the reads directly from the read provider (DMSP/DCC etc.) | 2 | low
12.1 & 12.3 | Site-specific conversion factors | Low | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support
|  |  |  | 2. CDSP Engagement with Shippers – highlight the individual sites, provide support, encourage action to update correction factors. CDSP to monitor monthly and notify relevant Shippers | 13 | med |  | Xoserve | This applies to all options involving customer engagement - call for Xoserve to develop a strategy/timescales for a co-ordinated engagement with Shippers (possibly new reports with priority rating) and possible escalation routes (if performance is not improved) To coincide with Change Proposal (XRN 4789) looking to review and streamlne Shipper reports
|  |  |  | 3. PAC reporting and monitoring – add new reports to Performance Assurance Report Register for 12.3 (already exists for 12.1) | 9 | med | 1. Dependent on other changes. | PAC | To consider extension of reporting to inlcude issue 12.3, as part of a future PAC meeting.
|  |  |  | 4. Notify Ofgem of individual sites and Shippers | 3 | low
|  |  |  | 5. Allow CF to be amended via Supply Point update (as alternative to RGMA updates) | 0 | No Support
|  |  |  | 6. UNC Mod: UNC Mod to introduce incentives or penalties on inappropriate CFs as an addition to the existing PAC reports | 3 | low |  |  | Medium/long – system changes
|  |  |  | 7. UNC Mod: New process to allow CDSP to liaise with MAM to obtain the new correction factor – either update UK Link or provide to Shipper to update | 0 | No Support
|  |  |  | 8. UNC Mod: New process to allow CDSP to trigger either a desktop process or a site visit to obtain the new correction factor – either update UK Link or provide to Shipper to update | 0 | No Support
|  |  |  | 9a. UNC Mod: Use the last non-standard CF (if present) if the site AQ increases above 732,000 | 10 | med | 1. Consider with 10 and 11. | E.ON UK | Sponsor = EON Long – UNC Mod timescales plus system changes
|  |  |  | 9b. UNC Mod: Introduce incentives or penalties as an addition to the new PAC reports | 0 | No Support |  |  | Long – UNC Mod timescales plus system changes
|  |  |  | 10. UNC Mod: Default the Conversion Factor to standard when the AQ drops below 732,000 | 11 | med | 1. Consider with 9a and 11. | E.ON UK | Sponsor = EON Long – UNC Mod timescales plus system changes
|  |  |  | 11.Change Proposal: Hold the standard CF as a central parameter rather than against meter points – ensures that calculation always uses correct value | 8 | med | 1. Consider with 10 and 9a. | E.ON UK | Sponsor = EON Long – UNC Mod timescales plus system changes
12.2 | Standard conversion factors | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support
|  |  |  | 2. Use actual LDZ temperatures to convert consumptions used to develop the NDM Profiles (ALPs and DAFs) – to be further refined at DESC forum | 3 | low |  |  | Short/medium – pending DESC review
|  |  |  | 3. Influencing strategy to amend Thermal Energy Regulations | 0 | No Support
|  |  |  | 4. UNC Mod: Add a new LDZ level factor to the volume-to-energy conversion formula to account for the net difference in energy. The factor could either be a fixed value reviewed periodically, or calculated daily using actual LDZ weather | 0 | No Support
|  |  |  | 5. Amend AUGE process to re-distribute UIG based on estimated impacts of conversion factors (forecast basis) | 1 | low
|  |  |  | 6. UNC Mod: to introduce retrospective adjustment to allocations based on actual weather for the year | 0 | No Support
|  |  |  | 7. UNC Mod: Introduce an LDZ level conversion factor (permanent/per year/per month) | 0 | No Support | 1. Linked to option 4
|  |  |  | 8. Amend UNC/legislation to require site specific conversion for every site | 0 | No Support | 1. Could this be done for smart metering as a long term solution? (MB)
|  |  |  | 9. Suggested by Shipper: UNC Mod: Create a new category of Energy, treated similarly to Shrinkage, where a percentage of daily throughput is allocated as a Correction Factor error. The percentage of energy would be set at LDZ level based on daily profiled seasonal normal temperature, and then retrospectively trued-up based on the actual LDZ temperature. | 4 | low | 1. Is a distinction needed between internally and externally located meters?
|  |  |  | 10. LDZ level adjustment of input gas. (SBl) | 4 | low
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support
|  |  |  | 2. Engagement with Shippers around monitoring read rejections and how CDSP can support through industry processes. We have shared specific sites we have identified with the Customer Account Managers and CDSP will work with the Shippers to resolve | 12 | med | 1. In progress. | Xoserve | To be defined.
|  |  |  | 3. XRN4690 will prevent the AQ defaulting to 1 where there is a negative consumption value held on UK Link. Additionally, we could run impacted MPRNs through the AQ correction tool once the code fix is deployed rather than waiting for rolling AQ to increase the AQ back to a suitable level | 9 | med |  | Xoserve | Medium. Would likely require user approval to correct their Aqs
|  |  |  | 4. There is an issue where a shipper cannot submit an AQ correction because there has not recently been an AQ calculation, but the shipper cannot submit a read because it is rejecting for AQ tolerance reasons. This would leave the shipper in a loop unable to correct the AQ. There is a pending change (XRN4803) to allow the AQ to be corrected in this scenario | N/A | high |  | Xoserve | This change is already underway and so will not be part of the recommendations but is captured here for completeness
|  |  |  | 5. Enhance PAC reporting around AQ corrections to include more detail and highlight areas of potential concern. PAC have visibility of AQ corrections and this will be enhanced to show the split between AQ increases and decreases and highlight any unusual activity | 10 | med |  | PAC | Existing Agenda item for PAC - Xoserve to work with PAFA to define proposal for next meeting. In progress; Medium
|  |  |  | 6. UNC Mod: We have been advised that some shippers are setting AQs to <10 using the AQ correction process where the site is vacant. We could raise a change to create a Vacancy flag on UK Link which would stop the AQ contributing to allocation, resulting in a benefit to the shipper without putting the AQ at risk........ | 2 | low | 1. Any further proposal would need to consider points raised by Ofgem in relation to (Mod 0282) |  | Would require a UNC Modification and system changes.
|  |  |  | 7. Raise a change so that where an AQ is corrected by the Shipper and a read received within [6] months with a metered consumption that is out of line with the corrected AQ, the AQ correction will be overridden by the usual AQ calculation process and the Shipper notified. | 0 | No Support
|  |  |  | 8. UNC Mod: Raise a change to shorten the required read period for AQ calculation to [3] months where the AQ is <[100] until a sufficient read history is available to calculate normally, | 0 | No Support | 1. Use of previous reads where an AQ correction has been used in the calculation.
|  |  |  | 9. UNC Mod: Create new “Vacant Site” AQ correction reason code and logic to allow an AQ correction where the AQ is 1 without the need to have a recently accepted read on UK Link | 0 | No Support | 1. See Mod 0282 (2011)
|  |  |  | 10. UNC Mod: Reducing the AQ below [100] kWh or by [95%] would trigger a requirement to provide a read or a site visit to obtain a read within [30] Days or the AQ correction would revert to the previous prevailing value. If the provided read energy does not align with the amended AQ then the AQ will revert to the previous prevailing value. If a subsequently submitted read calculates energy materially different from the deemed energy, the AQ will revert to the previous prevailing value and the site will be back billed | 0 | No Support
|  |  |  | 11. Increased validation (ES) - tighten up validation around an AQ correction | 1 | low
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support
|  |  |  | 2. Engagement with Shippers – highlight the individual sites, provide support, and shippers to raise tickets so CDSP can manually enter reads by exception | 15 | med |  | Xoserve | Low to medium – requires Shipper to work around UK Link validation issue
|  |  |  | 3. Users can increment the uncorrected read so it is higher than the read currently held on UK Link without going through the Zeros. The uncorrected read is not used for billing or AQ calculation so these process will not be impacted. There could be an impact on asset exchanges as the uncorrected read recorded on site will differ from that held on UK Link. As RGMA flows are normally pass through files, these may reject requiring the shipper to modify the uncorrected exchange reading | 0 | No Support
|  |  |  | 4. Shipper could submit a cosmetic corrector exchange alongside the lower uncorrected reading as this file format contains uncorrected TTZ count. Subsequent readings would then load normally assuming other validation checks pass | 0 | No Support
|  |  |  | 5. CDSP to monitor rejections for this rejection code. CDSP will manually load the read to UK Link if the read has passed all other validations. Subsequent reads will load normally if they pass validation checks | 13 | med |  | Xoserve | CDSP resource required to maintain this process Workaround option: Short to medium
|  |  |  | 6. The uncorrected read will be an optional field following the November 2019 UK Link release implementation, so it can be blank and the corrected read will load | 0 | No Support
|  |  |  | 7. Raise change to UK Link to remove validation on the uncorrected read as it is not used for billing | 0 | No Support
|  |  |  | 8. Raise a change to add an Uncorrected TTZ count to the incoming and outgoing read file format and any associated logic to ISU | 0 | No Support
|  |  |  | 9. Raise a change to alter the read load logic to derive the TTZ count for uncorrected reads. We would increment the uncorrected read TTZ count by 1 and load the read when the uncorrected read is lower than the previous uncorrected read and all other validation checks pass | 0 | No Support |  |  | Medium to Long CP required
2 | Low take-up of Winter Annual Ratio (WAR) Band EUCs | Medium | Live | 1. No action (“Do Nothing” option) or Park |  | No Support | No vote made as in progress.
|  |  |  | 2. Engagement with Shippers – highlight the individual sites, provide support, encourage read submission and use of the WAR Band Update process where reads not submitted in the winter acceptance periods |  | No Support | No vote made as in progress. | Xoserve | In progress; Short to medium
|  |  |  | 3. The WAR Band calculation can fail where the Meter Read Frequency is not Monthly for a site in a WAR Band eligible EUC. Meter Read Frequency should be added to the reports proposed in Modification proposal 0652 so shippers are aware where the MRF needs to be updated before the WAR Band can be applied |  | No Support | No vote made as in progress. | Xoserve | In progress; Medium
|  |  |  | 4. A new report to monitor sites which cross in to a WAR Band eligible EUC following Rolling AQ calculation. Proactively engage with Shippers to use the WAR Update process when needed |  | No Support | No vote made as in progress. | Xoserve | In progress; Medium
|  |  |  | 5. Notify Customer Account Managers when the T51 (WAR Band Calculation Failures) report is available so CDSP can proactively manage Next Steps with Customers |  | No Support | No vote made as in progress. | Xoserve | In progress; Medium
|  |  |  | 6. CDSP to fix the Read Variance issue in UK Link |  | No Support | No vote made as in progress. | Xoserve | In progress; Medium
|  |  |  | 7. Notify/escalate to Ofgem/PAC | 5 | low | 1. Dependent on progress of actions 2-6 and allowing processes to mature for example reporting arising from UNC 0652. |  | To be reviewed when other options are completed
13.2.2 | Accuracy of NDM Algorithm - Use of weather data - Sensitivity of components of the composite weather variable | High | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support
|  |  |  | 2. Provide Sensitivity analysis results to the Demand Estimation team for assessment and incorporation into SNCWV review via the Demand Estimation Subcommittee | 14 | med | 1. BAU as part of DESC work but any changes will not be implemented until Oct 2020. 2. Suggests areas in algortithm that DESC would not normally consider. |  | Long – may inform the current SNCWV review which will be implemented October 2020
13.2.5 | Accuracy of NDM algorithm - Use of additional weather data in the composite weather variable | High | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support
|  |  |  | 2. Next DESC review of Composite Weather Variable (CWV) formula to include the four other commonly available weather data items. | 14 | med | 1. BAU as part of DESC work but any changes will not be implemented until Oct 2020. |  | Medium/long – may inform the current SNCWV review which will be implemented October 2020
|  |  |  | 3. Replace NDM Allocation formula with a weather-based regression formula |  | No Support | 1. Did not vote, as it is a matter for DESC to consider as part of weather data/variable work.

## Lookups
Look Ups
Action Owner | Industry view on option | Priority | Status
PAC | Low Support (1-7) | Low | Live
Brittish Gas | Medium Support (8 -14) | Medium | Closed
Cadent Gas | High Support (15+) | High | Hold
Centrica
Xoserve
ConocoPhillips
Corona Energy
DNVGL
E.ON UK
EDF Energy
Energy 24
Engie
Exxon Mobil
First Utility
Flow Energy
Gazprom
Gemserv Ltd
Interchange
Joint Office
National Grid NTS
Northern Gas Networks
npower
Orsted
RWE Trading GmbH
Scotia Gas Networks
Scottish Power
Smartest Energy
SSE
Statoil UK
Tonik Energy
Total Gas and Power
Utility Warehouse
Wales & West Utilities
Waters Wye
Xoserve