## Sheet1
Action Reference | Decision /Issue /Risk /Action | Description of Action | Target Date | Owner | Update | Status
01-2901 | Issue | Section 3.26.1 of Mod 0678 and the impact of top-up charges on existing contracts and compliance with the TAR NC Article 35. |  | SSE (JCh) | Workgroup agreed this issue os a subset of action 2901-02. Closed 31 January | Closed
01-2901 | Action | National Grid to consider the impact of top-up charges on existing contracts and compliance with the TAR NC. | 11-Feb-2019 18-Feb-2019 22-Feb-2019 | National Grid Colin Williams (CW) | 31/01 - CW advised no change to view so far, action to remain open. 05/02 - The Workgroup requested a statement from National Grid for the Workgroup Report explaining how adding a top-up change is compliant with Article 35. CW agreed to provide a written response by 11-Feb-19. 14/02 - This will be incorporated into the updated drafting of modification 0678, ready for monday 18 February 18/02 - This will be covered in the updated mod expected by Friday 22 February 25/02 - This is covered in the amended modification 0678 | Closed
02-2901 | Action | Article 35: Joint Office to consider the topic list and confirm whether Article 35 fits into the timetable. Suggested for 31 January meeting under Revenue Recovery. |  | Joint Office | Action discussed within Recovery Topic discussions on 31 January. Action Closed 05 February. | Closed
03-2901 | Action | Workgroup to consider existing contracts and any potential discriminatory aspects relating to storage capacity (reference rules being developed under Modification 0662). | TBC | Workgroup | Action discussed within Recovery Topic discussions on 31 January. 05/02 The Workgroup believed that this needs to be considered further along with dicussiosn on combinied ASEPs. The solution does to cater for this at the moment and further clairty is required within the modification and Workgroup Report. National Grid beleive this is non-discreminatory against certain storage facilities. It was considered that certain elements of Modification 0662 needed to be incorporated into Modification 0678 for combined ASEP storage facilities. It was percieved that the soluton would work dependent on the definition of the ASEP site. There will be no differentaition for storage capacity and non-storage capacity for the importing of abandoned storage facilities. It was suggested there should be one holistic solution and avoid splitting elements out. 14/02 - a header to cover this principle will be placed in the Workgroup Report. 0678B dispences with that issue. 25/02 - More information is required in the Workgroup Report to cover this | Carried Forward
04-2901 | Action | National Grid to consider the consistent presentation of charges to enable comparative analysis of Alternatives. | 11-Feb-2019 | National Grid Colin Williams (CW) | CW confirmed that the logic will be included in the sensitivity tool template for the output of Entry and Exit prices. This will be provided for the next meeting. RF expressed the importance for the consistent presentation of numbers. CW explained that National Grid will provide a generic set of numbers based on a set of principles, the FCC numbers will be provided without the options. The options will need to be built in. The data can be overidden. Parties will need to approach National Grid for National Grid data. 14/02 - National Grid agreed to provide model for Modification 0678, other results can be added to any table which will be delieverd. | Closed
05-2901 | Issue | Regulatory Impact Assessment – impact on customers. | 14-Feb-2019 to 06-Mar-2019 | Workgroup | This will be covered as the WGR is updated throughout the Workgroup discussions | Closed
05-2901 | Action | Ofgem to consider the requirement to provide a regulatory impact assessment. | TBC | Ofgem David O'Neill (DON) | Action re-allocated to Ofgem from Workgroup. 14/02 - Ofgem will make a decision when the FMR is received. | Closed
06-2901 | Action | National Grid to consider traded capacity contracts and exposure to the capacity uplift charge and when it would attract the revenue recovery charge and if this was intended for this modification | 14-Feb-2019 | National Grid Colin Williams (CW) | CW confirmed that the general approach will be the same as before. More clarity was requested and will be provided within the Modification. Firm position on this subject. Questions encouraged from the Workgroup. CW agreed to provide an update within a presentation slide. 14/02 - This will be clarified in the draft amended Modification 0678 due to be delivered Monday 18 February, 0678A will follow suit. | Closed
07-2901 | Action | Ofgem to provide a formal View on the feasibility of achieving 01 October 2019 implementation date and the impact of not achieving this date and being compliant as soon as possible. (JO to action this) | TBC | Ofgem David O'Neil (DON) | Ofgem have requested as per 12.8.2 for the Workgroup to set out the “views and reasons for seeking a View from the Authority”. Pursuant to rule 12.8.4 “the Modification Proposal should proceed to Workgroup Assessment…” and that any implementation date has no bearing on the urgent process that is currently occurring. The Workgroup wished to have clarity on what methodology the industry will be working to for contract with start dates of 01 October 2019. Further clarity was required to understand the risks associated with the new Gas Year and to allow for correct negoataitions. 14/02 - Ofgem will make a decision when the FMR is received. | Closed
08-2901 | Action | Workgroup to review the draft Workgroup Report at the end of each session and provide any updates ahead of the start of the next session/meeting. | Ongoing | Workgroup | Confirmed that conclusion of conversations will be captured in the Workgroup Report as discussions progress. | Closed | close
01-3101 | Action | Extra clarity to be added to the Modification to clarify netting-off for existing contracts | 14-Feb-2019 22-Feb-2019 | National Grid Colin Williams (CW) | In progress expected w/c 11-Feb-19. 14/02 - This will be in the draft amended Modification 0678 expected Monday 18 Februray. All other proposers who are mirroring 0678 proposal, this includes 0678A (deadline Fri 25 Feb) and 0678B (no plans to update mod for this). A header will be put in the Workgroup Report gross/net for exisiting contracts under RPM general. Take into account Ofgem's views in 0621 letter 25/02 - More information is required in the Workgroup Report to cover this | Carried Forward
02-3101 | Action | Reference Price Methodology - Workgroup to consider the need for a mechanism to allow more equitable recovery | TBC | Workgroup | 14/02 - J Costa (EDF Energy) to supply wording for Workgroup Report by 18 Feb | Carried Forward
03-3101 | Action | National Grid to add commentary to the Modification as to the decision for choosing the Capacity Weighted Distance (CWD) approach. | 14-Feb-2019 18-Feb-2019 22 Feb 2019 | National Grid Colin Williams (CW) | In progress expected w/c 11-Feb-19. 14/02 - This will be in the draft amended Modification 0678 expected Monday 18 Februray. 18/02 - This will be covered in the updated mod expected by Friday 22 February | Carried Forward
04-3101 | Action | Workgroup to consider Article 7 as part of compliance discussions | 11-Feb-2019 | Workgroup | Considered within Workgroup 4 on 11-Feb-19. Action superceded, Workgroup will consider compliance for the Workgroup Report of all appropriate TAR NC Articles. See New Action 01-1102. | Closed
05-3101 | Action | National Grid to provide a set of principles / algorithm for the FCC methodology, and some back cast analysis. | 14-Feb-2019 20-Feb-2019 25-Feb-2019 | National Grid Colin Williams (CW) | In progress expected w/c 11-Feb-19. 14/02 - FCC methodology will be provided by National Grid by 20 feb 20/02 - FCC methodology will be provided by National Grid by 25 feb 25/02 - The updated FCC will be provided by 27 February 2019 | Carried Forward
06-3101 | Action | National Grid to provide the FCC methodology and figures | 14-Feb-2019 20-Feb-2019 25-Feb-2019 | National Grid Colin Williams (CW) | In progress expected w/c 11-Feb-19. 14/02 - FCC methodology will be provided by National Grid by 20 feb 20/02 - FCC methodology will be provided by National Grid by 25 feb 25/02 - The updated FCC will be provided by 27 February 2019 | Closed
07-3101 | Action | Anna Shrigley to provide suitable text regarding the existing capacity customer contracts for inclusion in the Workgroup Report | 05-Feb-2019 | Anna Shrigley | Provided. Comments to be captured. 11-Feb-19 update: now captured in WGR by RH | Withdrawn
8-3101 | Issue | Workgroup to review capacity hand-backs (not in scope of 0678) | TBC | Joint Office | Workgroup Report to capture considerations. 14/02 This has been put on the agenda for NTSCMF April 2019. | Closed
9-3101 | Action | Workgroup to consider previous 0621 considerations and Ofgem's Decision Letter | 05-Feb-2019 | Workgroup | Workgroup Report to capture appropriate extracts. | Closed
10-3101 | Action | Alex Nield requested that his views on Interim Contracts are considered and captured within the Workgroup Report | 14-Feb-2019 to 06-Mar-2019 | Workgroup | Interim Representation published. Potential Alternative. 14/02 - Alex Neild to highlight what, if anything, is to go into the Workgroup Report | Closed
01-0502 | Action | Multipliers and Discounts: National Grid (CWi) to provide an illustration of revenue alignment for Interruptible Capacity, including the resulting effect on revenue recovery and top-up charges for existing capacity holders. | 13-Feb-2019 or 14-Feb-2019 20-Feb-2019 22-Feb-2019 | Workgroup | 14/02 - reviewed - target date updated 20/02 - This will be included in the amended 0678 Modification or in supporting material expected Friday 22 Feb or in supporting material 25/02 - This is covered in the amended modification 0678 | Closed
02-0502 | Action | Shorthaul: National Grid to provide some analysis on Shorthaul and the effect of cessation of Shorthaul on existing users and customers currently using Shorthaul services. | 14-Feb-2019 22-Feb-2019 | Workgroup | 14/02 - Confirm aggregate volume of flows that benefit to shorthaul 20/02 - This will be included in the amended 0678 Modification or in supporting material expected Friday 22 Feb or in supporting material 25/02 - This is covered in the amended modification 0678 | Closed
03-0502 | Action | Workgroup Report: Workgroup to ensure that the Relevant Objectives are appropriately assessed when completing the Workgroup Report (14th Feb-6th March) | 14-Feb-2019 to 06-Mar-2019 | Workgroup |  | Closed
01-1102 | Action | Joint Office to formulate a TAR NC Compliance Table for Proposers and Workgroup to assess compliance for the Modification by Article. | 13-Feb-2019 | Joint Office |  | Closed
02-1102 | Action | Ofgem (NRA) to decide and confirm who should undertake the Cost Allocation Assessment under TAR NC Article 5. | 20-Feb-2019 | Ofgem James Thomson (JT) | 14/02 - capture in WGR that CAA will be done after UNC process finishes, Ofgem to update on this | Closed
03-1102 | Action | Ofgem (NRA) to decide and confirm who should undertake the TAR NC Article 26 Consultation. | 15-Feb-2019 20-Feb-2019 | Ofgem James Thomson (JT) David O'Neill (DON) | 14/02 - reviewed - target date updated 20/02 - Ofgem intends to carry out the final consultation for Article 26, National Grid will be asked to carry out the interim Article 26 consultation shortly after the UNC consultation with the same end date as the UNC consultation (05 April 2019). The CAA will be done by National Grid to be used in the final consultation by Ofgem. Letter from Ofgem expected withion the next week. CAA results will be available during the UNC consultation. | Closed
04-1102 | Action | National Grid to provide an update on the FCC methodology no later than 18 February 2019 and to consider using the past 5 Years historical gas flow data opposed to DN forecasted capacity data for offtakes. | 14-Feb-2019 20-Feb-2019 22-Feb-2019 | National Grid Colin Williams (CW) | 14/02 - this will be included in the FCC methodology to be received by 20 February 20/02 - will be included in supporting material expected Friday 22 Feb 25/02 - This was received 22 February | Closed
05-1102 | Action | Northern Gas Networks (EB) to confirm if the DNs 1in20 Demand Forecast data can be made publicy available (as provided by DNs to National Grid under UNC OAD Section H NTS Long Term Demand Forecasting) subject to any confidentiality concerns associated with the data. | 14-Feb-2019 | Northern Gas Networks Emma Buckton (EB) | 14/02 raise new issue for NTSCMF DN as Relevant Points should be publishing. This has been placed on the April 2019 agenda | Closed
06-1102 | Action | Joint Office to feedback concerns to the UNC Panel, that National Grid do not have sufficient resource to support the Workgroup development and the analysis required to satisfy Ofgem's expected robust analysis. | 14-Feb-2019 | Joint Office (RH) | This has been completed - see UNC Panel minutes from 12 February 2019 | Closed
01-1402 | Action | National Grid (CW) to provide clarity on where data is currently published that applies to each Article in the TAR NC. | 28-Feb-2019 | National Grid Colin Williams (CW) |  | Pending
01-1802 | Action | Any firm statements to be included in the Compliance section for Modifications that are currently live are to be provided by 22 February 2019 | 27-Feb-2019 | All Workgroup |  | Pending
02-1802 | Action | Any firm statements to be included in the Compliance section for Modifications that are NOT currently live are to be provided by 01 March 2019 | 01-Mar-2019 | All Workgroup |  | Pending
01-2502 | Action | Ofgem to provide a statement to clarify the expectations in terms of Legal Text provision (Target date 27 February 2019) | 27-Feb-2019 | Ofgem James Thomson (JT) |  | Pending
02-2502 | Action | National Grid (CWi) to provide a view on the significance of an PARCA Reservations and the possibility of updating the sensitivity tool to incorporate some recent PARCA Reservations (Target date 28 February 2019) | 28-Feb-2019 | National Grid Colin Williams (CW) |  | Pending
01-2602 | Action | EU/GB Project Team (Relevant National Grid project team) to provide a systems cost estimate and issues and feasibility update statement for inclusion in the Workgroup Report (Target date 01 March 2019) | 01-Mar-2019 | National Grid Colin Williams (CW) and Xoserve (Steve Pownall (SP) |  | Pending
01-2702 | Action |  |  |  |  | Pending

## Lookups
Action
Decision
Issue
Risk