## Sheet1
¦ | Decision/Issue/Risk/Action | Description of Action | Target Date | Owner | Update | Status
2901-01 | Issue | Section 3.26.1 of Mod 0678 and the impact of top-up charges on existing contracts and compliance with the TAR NC Article 35. |  | SSE (JCh) | Forms a subset of action 2901-02 | Closed
2901-01 | Action | National Grid to consider the impact of top-up charges on existing contracts and compliance with the TAR NC. |  | National Grid Colin Williams (CW) | CW advised no change to view so far, action to remain open. JCh hoping for statement in WGR from National Grid explaining why adding a top-up change is compliant with Article 35. | Carry Forward
2901-02 | Action | Article 35: Joint Office to consider the topic list and confirm whether Article 35 fits into the timetable. Suggested for 31 January meeting under Revenue Recovery. |  | Joint Office | To be covered in discussions within Revenue Recovery 31 January | Carry Forward
2901-03 | Action | Workgroup to consider existing contracts and any potential discriminatory aspects relating to storage capacity (reference rules being developed under Modification 0662). |  | Workgroup | To be covered in discussions within Revenue Recovery 31 January | Carry Forward
2901-04 | Action | National Grid to consider the consistent presentation of charges to enable comparative analysis of Alternatives. |  | National Grid Colin Williams (CW) | CW the logic will include a template for the output of Entry and Exit prices - formed as part of the Sensitivity Tool which will be provided next week. This will cover existing prices | Carry Forward
2901-05 | Issue | Regulatory Impact Assessment – impact on customers. |  |  | This will be covered as the WGR is updated throughout the Workgroup discussions
2901-05 | Action | Ofgem to consider the requirement to provide a regulatory impact assessment. |  | Ofgem David O'Neil (DON) | Action re-allocated to Ofgem from Workgroup. | Carry Forward
2901-06 | Action | National Grid to consider traded capacity contracts and exposure to the capacity uplift charge and when it would attract the revenue recovery charge and if this was intended for this modification |  | National Grid Colin Williams (CW) | CW the general approach will be the same as before. More clarity is requested and will be provided in the Modification. Firm position on this subject. Questions encouraged from the Workgroup. | Pending
2901-07 | Action | Ofgem to provide a formal View on the feasibility of achieving 01 October 2019 implementation date and the impact of not achieving this date and being compliant as soon as possible. (JO to action this) |  | Ofgem David O'Neil (DON) | JO have written to Ofgem; Now awaiting a response from Ofgem. | Carry Forward
2901-08 | Action | Workgroup to review the draft Workgroup Report at the end of each session and provide any updates ahead of the start of the next session/meeting. | Ongoing | Workgroup | PG clarified that conclusion of conversations will be captured in the Workgroup Report as discussions progress. | Carry Forward
3101-01 | Action | Extra clarity to be added to the Modification to clarify netting-off for existing contracts |  | National Grid Colin Williams (CW) |  | Pending
3101-02 | Action | Reference Price Methodology - Workgroup to consider the need for a mechanism to allow more equitable recovery |  | Workgroup |  | Pending
3101-03 | Action | National Grid to add commentary to the Modification as to the decision for choosing the Capacity Weighted Distance (CWD) approach. |  | National Grid Colin Williams (CW) |  | Pending
3101-04 | Action | Workgroup to consider Article 7 as part of compliance discussions |  | Workgroup |  | Pending
3101-05 | Action | National Grid to provide a set of principles / algorithm for the FCC methodology, and some back cast analysis. |  | National Grid Colin Williams (CW) |  | Pending
3101-06 | Action | National Grid to provide the FCC methodology and figures |  | National Grid Colin Williams (CW) |  | Pending
3101-07 | Action | Anna Shrigley to provide suitable text regarding the existing capacity customer contracts for inclusion in the Workgroup Report |  | Anna Shrigley |  | Pending
3101-08 | Issue | Workgroup to review capacity hand-backs (not in scope of 0678) |  |  |  | Pending
3101-09 | Action | Workgroup to consider previous 0621 considerations and Ofgem's Decision Letter | 2019-02-05 | Workgroup |  | Pending
3101-10 | Action | Alex Nield requested that his viewed on Interim Contracts are considered and views captured within the Workgroup Report |  | Workgroup |  | Pending

## Lookups
Action
Decision
Issue
Risk