## Slide 1: XRN4572 UK Link Release 3
27th February 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | The progress against each track is as below:- Track 1 (13 Changes) PIS Complete. Overall closure report to be issued to ChMC following completion of Track 2 Track 2 (XRN 4454 Cadent/ NG) PIS due to complete on 8th March 5 minor defects raised to date. 4 fixed and deployed, 1 fixed and to be deployed this week. Capacity, Commodity, Meter Asset, Amendment and LPG invoices all issuedd successfully |  |  | 
Risks and Issues | Issue against XRN 4534 RGMA Validation Rules (Unable to Implement in Track 1) Implementation completed on 1st March Next step Conclude PIS |  |  | 
Cost | Full Delivery costs approved at ChMC in April 2018. Revision to accommodate XRN4454 (Cadent) delivery approved at December ChMC. |  |  | 
Resources | SME resources in place to support XRN4454 Cadent/NG PIS and conclusion of XRN4534 RT |  |  | 

## Slide 2: UK Link Release 3 - Plan
Primary Scope | Scoping |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding | Initiation | Analysis and HLD | Detailed Design | Build & System Test | Acceptance Test | Performance Test | Market Trials | Regression Test | Imp. | PIS
Track 1 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 04/06/18 | 13/08/18 | 07/09/18 | 19/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 1 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 04/06/18* | 13/08/18 | 07/09/18 | 25/10/18 | 08/10/18* | 22/10/18 | 02/11/18 | 04/01/18
Track 2 Baseline Plan | 10/01/18 | 07/02/18 | 11/04/18 | 13/04/18 | 13/04/18 | 30/06/18* | 24/09/18 | 05/11/18 | N/A | 14/12/18* | 18/01/18 | 01/02/19 | 08/03/19
Track 2 Current Plan | 10/01/8 | 07/02/18 | 11/04/18 | 13/12/17 | 13/04/18 | 30/06/18* | Build Complete ST synergised with AT | 14/12/18** | N/A | 14/12/18* | 18/01/18 | 04/02/19 | 08/03/19**
RAG Key – Milestones are end dates;
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed
** On track for completion 08/03/19