## Slide 1: DSC ChMC CSS Consequential Update 13th March 2019

## Slide 2: Ofgem Switching Programme – Consequential update
CSS High Level Design Consequential Workgroups
The consequential workgroups concluded on the 7th March. The workgroups have been well attended and informative, thank you all for your support and input during this phase.
The outputs of high level design have been published and can be found on Xoserve.com under DSG extraordinary meetings and the meeting date of the 7th March. These include:
External BRD’s
Updated heat map
To Be Process flows
Solution option slides with selected option hi-lighted
These high level design artefacts are now being progressed into detailed design.

## Slide 3: Ofgem Switching Programme – Consequential update
CSS Detailed Design Consequential Workgroups
Detailed design commences early April and will run for five months, April through to the end of August.
Our Industry Engagement approach will mirror high level design with a series of CSS extraordinary DSG meetings being arranged for detailed design discussions. These workgroups will commence at the end of April, presently I am looking to arrangement nine workgroups. One in April and then two per month through to the end of August.
During these workgroup we will be working together to refine our high level design solutions in order to complete our detailed design. During this phase we will be releasing change packs alongside workshop information in order for you to have the lower level design detail as soon as possible.
I will shortly be providing the dates and topic schedule for these workgroups in order for you to arrange the correct attendance. Please do not hesitate to get in touch with me if you require any further information.
The next two slides of this presentation detail the Xoserve CSS Consequential Programme plan on the first slide and the second slide shows the UK Link detailed design phase.

## Slide 4
 | 2018 |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  | 
 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Ofgem/DCC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UK Link (ISU) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Reports |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Data Mig. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Infra |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Gemini |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Business Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Transition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1: First Physical Design Baseline
2: SIT Entry
3: DM Test Entry
4: Operational Test Entry
5: E2E Test Entry
6: Transition Stage 1 Entry
7. Go Live (cutover)
8. End of PIS
DBT
Physical Design
SIT
DMT
Operational Test
E2E Test
St1
St2
LR
St3
PIS
Operate
UEPT
Milestone
Xoserve Stage Gate
Contract
Procurement
1
2
3
4
5
6
7
8
Pen. test
Perf. test
Regression test
E2E Test
SM Design
SM Build/Configuration
Internal SM Testing
St1
St2
St3
IDR2
Cutover planning
C/O Strategy
UEPT
PIS
Report Testing
Analyse
Knowledge Transfer
Prepare & Assess
Training and adoption
IDR1
Develop
NFR Test Cont.
Operational Testing
1/12
Assumed Physical Design
Test Strategy
Data HLD
Data S2T
Data TC1
Data BUT
DataTC2
Potential further cycles
C/O App
IDR3
LR
NFR BUT
NFR OAT
NFR DD
BUT
ST
UAT
MT
Design
Integration test
Regression Test
Testing Support
Internal Acceptance Test
DM
Testing Support
Detailed Design
HLD
Incremental Mobilisation
ISU BUT
Test Preparation
System Test
SIT
Report BUT
DD
Gas Day testing
Operate
Capture
C++
C+
C
B/B+
A
E+
E
F
D
Planned time line
Indicative time line
Key:
CSS Consequential
HLD
Capture

## Slide 5
 | 2018 |  | 2019 |  |  |  |  | 
 | Feb | Mar | Apr | May | June | July | Aug | Sept
Ofgem/DCC |  |  |  |  |  |  |  | 
Programme |  |  |  |  |  |  |  | 
UK Link |  |  |  |  |  |  |  | 
Data |  |  |  |  |  |  |  | 
Reporting |  |  |  |  |  |  |  | 
Gemini |  |  |  |  |  |  |  | 
Batch & EFT |  |  |  |  |  |  |  | 
Network |  |  |  |  |  |  |  | 
Business Change & SM |  |  |  |  |  |  |  | 
Testing |  |  |  |  |  |  |  | 
Physical Design
Contract
UK Link Detailed Design
Incremental Mobilisation
B
Procurement
DBT
HLD
Next Phase Planning
CSS Physical
Design Baselined
DD Customer Engagement
DD Sign Off
Signed Off Requirements
fed into Build
DD Workshops
complete
Gemini Detailed Design
DD Workshops
complete
SUCs
Approved
Design Docs
Complete
Final Sign-Off
Gap Analysis
Agree High Level Solution Options
Detailed Design
UK Link Build & Unit Test
Build & Unit Test
Build & Unit Test
Batch, EFT, Design Build & Test
Data Assurance
Data Profiling
Data Mig Strategy
Data Migration Approach & Design
Build & Test Cycles
Capture
HLD
DD
Build & Unit Test
Detailed Design
Test Strategy & Approach
Test Planning
B