## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | Still undertaking discussions at DSG. We are looking at several distibution mechanisms and will test how the Change Pack process would work for each one. 30/10/2018 - The intention will be to include this within the scope of the new Xoserve website design plans. 30/01/2019 - We are currently working on some requirements to include this within a 'phase 2' implementation of the new website. 27/03/2019 - Build is expected to be completed in Mid-April, ready for May's Change Pack publication
NA | NA | Maintenance of a Capacity Plan | 2264.4 - RJ - ES | 2019-03-15 | 2019-04-26 | 2019-04-26 | X | X | X | X |  | NA | We have included this for all system Users to tell us of any Supply Meter Point Class movement or projects Xoserve needs to be aware of for system capability over the next 12 months. This is out for a 30 working day consultation. All responses will remain confidential between system Users and the CDSP.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4665 | N/A | Creation of New End User Categories | 2264.3 - RJ - ES | 2019-03-15 | N/A | N/A | X | X |  | X |  | N/A | 2019-04-10 | Part A - 03/08/2019 Part B - 31/08/2019 Contingency - 07/09/2019 | This was a revised version of the Design Change Pack we distributed on 21st December 2018 (2184 – RJ – ES), and is for information only. In the revised version, we have confirmed that no functional changes are required to Gemini, and there are no external impacts to existing Gemini processes. Furthermore, we have also included the two implementation dates as discussed at the Change Management Committee (ChMC) meeting on 13th March : • Part A on 3rd August 2019 to make new End User Category (EUC) bands allowable in SAP ISU to share new EUC bands with the industry via the T67 file • Part B on 31st August 2019 (with a contingency date of 7th September 2019 if required) to implement all code changes to processes affected by new EUC bands We will confirm the above implementation dates at the ChMC meeting on 10th April 2019.
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 13th March 2019
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
XRN4806 | N/A | Additional data at National Level to support UIG Allocation validation | 2234.8 - RJ - ES | 15/0/2019 | 2019-03-01 | 2019-03-01 | X |  |  |  |  | TBC | 2019-03-13 | 2019-03-01 | In February, ChMC permitted Xoserve to provide the additional information at national level to support customers with the validation of UIG Allocation on a monthly basis for the previous calendar month. As agreed at ChMC in February, this Change was sent out in the February Change Pack to confirm the an ad-hoc implementation within March 2019.
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
7445 | Gemini and Gemini Exit Disaster Recovery Test | 2019-04-13 | 3:15 | 2019-04-13 | 07:30 | Annual test to prove disaster recovery capabilities and procedures for Gemini and Gemini Exit. (Should it be necessary to fail back to the primary site, the outage window will be extended to 12:30 UK BST). | 13/02/2019 13/03/2019 10/04/2019
7445 | Gemini and Gemini Exit Disaster Recovery Test | 2019-04-14 | 3:00 | 2019-04-14 | 7:30 | Annual test to prove disaster recovery capabilities and procedures for Gemini and Gemini Exit (Should there be issues failing back to the primary site, the outage window will be extended to 12:30 UK BST). | 13/02/2019 13/03/2019 10/04/2019
7274 | Peterborough Power Outage | 2019-05-18 | 20:00 | 2019-05-19 | 8:00 | This is a planned annual activity and permits the site facilities contractor to complete essential maintenance to the high voltage electrical distribution equipment at the Peterborough Datacentre site. Infrastructure impacts: All TTD/DR/Standby servers and equipment at Peterborough will be powered down during the outage Application Impacts: There will be no impact to production Gemini and Gemini Exit systems as these operate from the primary datacentre at Kettering. There will be no impact to production CMS as this system operates from the primary datacentre at Kettering. There will be no impact to production UK Link as this system operates from the primary datacentre at Woking. | 2019-04-10