## Slide 1: XRN4828 - Nov 19 Release - Status Update
1st April 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Start Up and Initiation phase in progress and on track to complete in April Detailed Design plan to be finalised Market Trials phase discussed at ChMC and agreement reached in principle that this is not required for November 19 release. Consensus at DSG on 1st April was that a Test Summary report published by Xoserve would be sufficient Change Packs on track to be approved by 8th May Funding: BER for full delivery to be presented to ChMC in April 2019 |  |  | 
Risks and Issues | Risk: There is a risk that the Nov 19 Release may be impacted by Pre-Production environment congestion due to multiple deliveries running in parallel Risk: There is a risk that due to multiple UKLink deliveries running in parallel there may be limited access to resources. |  |  | 
Cost | The BER with full delivery costs will be presented to ChMC in April 2019. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Receive supplier responses – 13/02/19
Supplier contract approval – 05/04/19
Approve and issue EQR – 04/02/19
Gain Business Case approval at IRC - 13/03/19
PID approval 12/04/19
Detailed Delivery Plan approved – 05/04/19
BER Approval – 10/04/19
Design Change Packs Approval –08/05/19
Test Plan approval – 05/04/19
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
XRN4828
Nov-19
HLD & Change Pack Production
Design
Build & FUT
ST & SIT
UAT
RT
PT
Test Cont.
PIS
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Approval
GO LIVE 08/11/19 - TBC
IDR