## Slide 1: XRN – MiR Drop 4 - Status Update
30/04/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Design– Design workshops being held for 2 changes (XRN 4777 and XRN 4870) Build - Build has commenced for 1 change (XRN 4803) |  |  | 
Risks and Issues | Risk of environment unavailability due to environment pre prod refresh, this is being discussed and worked through with ECMS, expect this to be worked around |  |  | 
Cost | All costs tracked to budget |  |  | 
Resources | There is an ongoing risk that CPE’s will not be available when required, this is being closely monitored, currently there has been no issues |  |  | 

## Slide 2: Potential Minor Release Drop 4 Timeline & Scope
Minor Release Drop 4 Key Milestone Dates:
Initiation – 3/5/19
Design – 10/5/19
Build - 7/6/19
Test – 19/7/19
Implementation – 27/7/19
Closedown – 9/8/19
Design
Build
ST & Assurance
CM
PT / RT
IMP
PIS
Dec
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
MiR Drop 4
10/04: Scope Approval
27/7: Go Live

## Slide 3: Potential Minor Release Drop 4 Timeline & Scope
Potential Scope Items:
XRN4777 - Acceptance of Contact Details Updates
XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) – REDUCED SCOPE
XRN4803 - Removal of validation for AQ Correction Reason 4
XRN4871 - Modification 0665 – Changes to Ratchet Regime – Investigation only
Design
Build
ST & Assurance
CM
PT / RT
IMP
PIS
Dec
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
MiR Drop 4
10/04: Scope Approval
27/7: Go Live