## Slide 1: XRN4828 - Nov 19 Release - Status Update
8th May 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Start Up and Initiation phases complete Detailed Design plan finalised with execution commencing in June Change Packs published to plan on 12th April, to be approved on 8th May Funding: BER for full delivery approved in April 2019 XRN4866 UIG Recommendation – removal of validation on uncorrected read being considered for delivery in line with November 19 project subject to internal approval. Separate BER for this change to published to ChMC for approval. |  |  | 
Risks and Issues | Risk: There is a risk that the Nov 19 Release may be impacted by Pre-Production environment congestion due to multiple deliveries running in parallel Risk: There is a risk that due to multiple UKLink deliveries running in parallel there may be limited access to resources. |  |  | 
Cost | The BER with full delivery costs were approved at ChMC in April 2019. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Receive supplier responses – 13/02/19
Supplier contract approval – 05/04/19
Approve and issue EQR – 04/02/19
Gain Business Case approval at IRC - 13/03/19
PID approval 12/04/19
Detailed Delivery Plan approved – 05/04/19
BER Approval – 10/04/19
Design Change Packs Approval –08/05/19
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
XRN4828
Nov-19
HLD & Change Pack Production
Design
Build & FUT
ST & SIT
UAT
RT
PT
Test Cont.
PIS
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Approval
GO LIVE 08/11/19 - TBC
IDR