## Bubbling Under Report
Regulatory Reference | Status | Governance | Proposer/ Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed Platform | Customer Change Lead | Comments
Mod 0630R | Workgroup closed - Proposed to remove from Bubbling Under | UNC | Cadent Gas | Review of the consequential changes required in UNC as a result of the Ofgem Switching Programme | The vehicle in which the changes to the UNC required as a result of the review group is still to be determined. Once confirmed, the changes will be impact assessed and confirmed. | [5 empty] | CSS | David Addison | October Panel agreed to extend the Workgroup until March 2019. It will be used to develop the legal text required as part of the CSS Consequential changes. Workgroup has been extended until May. System changes will be covered under CSS work. Legal text has gone to Ofgem. Panel agreed for the WG to be closed but wanted confirmation around where the comments/concerns on legal text could be raised. Proposed to be removed from Bubbling Under.
Mod 0647 (IGT119) | With Workgroup - Expected to be closed and new Review Group raised | UNC - DWG | WWU | Opening Class 1 reads to Competition | 2020-06-01 | Rule Change & System change | NA | Impacts on UK Link and Portal access | Impacts to file flows and validations for Shippers to be able to send in reads for Class 1. We are not expecting impacts to Gemini | June 2020 Release | Retail & Network | David Addison / Ellie Rogers | Proposes to Open Class 1 reads to competition by introducing common arrangements for Class 1 and 2 by removing the DNO obligation to provide a Daily Read service to Shippers for non-telemetered Class 1 Supply Meter Points. Proposed solution is to keep the SMPs in Class 1 with the Shipper being responsible for submitting the reads with a transitional period of currently 3 months. A revised ROM for this change has been provided as the initial ROM cost was higher than anticipated. Costs are expected to be around £220,000 - £250,000 including the transitional phase. Despite the reduction in the anticipated cost, the WG identified disadvantages with the approach and agreed to pursue an alternative route whereby the CSDP provide the service centrally on behalf of Shippers. 0647 will be withdrawn and a new Review Group created (0694R) to explore this.
Mod 0661R | Workgroup closed - Proposed to remove from Bubbling Under | UNC - Stand alone | Winchester | Reconciliation and Imbalance Cash Out Prices | Any Modifications as a result of 0661R will be impact assessed and system implications considered. Should a Modification be raised, there are likely to be significant impacts as it will affect Gemini and UK Link. | [5 empty] | TBC | Steve Pownall | This Requests aims to seek a method of incentivising Shippers to purchase the correct amount of gas for NDM sites, in advance of the gas day and support de-risking Shipper imbalance costs. Mod 0661R is looking at options for modifying the application of System Marginal Prices for Meter Reconciliation. WG report expected to be finalised at next meeting. Likely that a subsequent request or proposal (based on Option C) will be raised following this. Business rules and Xoserve requirements must be defined in order to assess the impacts which are not currently known. Panel voted to close the WG. The proposer will be discussing the proposed change directly with Ofgem.
Mod 0662 | With Workgroup | UNC - Transmission | NTS | Revenue Recovery at Combined ASEPs | 2019-10-01 | Rule & System change | NA | UK Link and Gemini | Potential impacts to UK Link and Gemini. Please note - this is a single event change | NA | Transmission and Shared Services | Steve Pownall | The purpose of this modification is to allow entry capacity booked for the entry of gas into the NTS from storage sites within combined Aggregated System Entry Points (ASEPs), to be treated the same as a “Storage Site” as designated in National Grid’s Licence with respect to the application of any revenue recovery charge based on capacity bookings. The required changes will be captured as part of the EU GB Charging project. Xoserve systems have been impact assessed and the development of the modification solution is relatively simply. Dependent on 0678 decision. Ofgem have agreed to an extension.
Mod 0664 | With Workgroup | UNC -UIG | Npower | Transfer of sites with low read submission performance from Class 2 and 3 into Class 4 | No implementation specified | Rule & System change | NA | UK Link | Impacts on UK Link to bulk transfer invoicing to charge for avoided UIG weighting factors | NA | Retail & Network | Simon Harris | Modification looks to create an obligation for Shippers to move sites with low meter read submission performance from Product Class 2 and 3 into Product Class 4 in the first year of entry to the settlement class. Proposal is to give Shippers a timescale to move sites where there is poor read submission performance. If the move does not occur during the assigned time period, the CDSP will be expected to move the sites. Impacts for invoicing to charge for avoiding UIG weighting factors. ROM was requested but subsequently withdrawn. System impacts are dependent on the outcome of the modification which is currently undecided.
Mod 0667 (Urgent) | Awaiting Panel Consideration | UNC - Transmission | South Hook Gas Company Ltd | Inclusion and Amendment of Entry Incremental Capacity Release NPV test in UNC | No implementation specified | Contractual change & potential Rule change | NA | Confirmed as no system impact. | As the modification remains as a contractual change only, there will be no system impacts. | NA | Transmission and Shared Services | Steve Pownall | Modification seeks to insert the Net Present Value test required for Non-IP Entry Incremental Capacity Release into UNC, and amend the mechanics of the test to ensure that it works effectively with the current GB system. Modification should have no impact on central systems as it is purely contractual, moving National Grid methodology into UNC. It was thought that the solution may not only be contractual and could have system impacts and may interact with Modification 0671. Following discussions at Transmission WG, it has been confirmed that there will be 'no impact' to central systems. Consultation period closed on 20 May. 5 representations were submitted, 4 in support and 1 opposing the change. It is due to be discussed at June Panel. No central system impacts.
Mod 0669R | With Workgroup | UNC -Transmission | NTS | Review of the Gas Deficit Warning (GDW) and Margins Notice (MN) Arrangements | Any Modifications as a result of 0669R will be impact assessed and system implications considered. If a Modification to change the GDW processes, this could have Xoserve process impacts. | [5 empty] | Transmission and Shared Services | Steve Pownall | Review Group requested to review the processes, timeliness, and information provision associated with National Grid’s gas security of supply notices and to review the name of the Gas Deficit Warning notice. Panel agreed a Working Group should be set up for 6 months to review the processes. There may be process and system impacts dependent on the outcome of the review as Xoserve maintain certain offline GDW business processes but the current proposal does not change these. Modification 0685 has been raised following this Review Group. Panel agreed to WG extension. Second Modification expected, central impacts currently unknown.
Mod 0670R | With Workgroup | UNC - NTSCMF | NTS | Review of the charging methodology to avoid the inefficient bypass of the NTS | Any Modifications as a result of 0670R will be impact assessed and system implications considered. If Modification is raised, it is likely to have cross-platform impacts (Gemini and SAP ISU). | [5 empty] | Transmission and Shared Services | Steve Pownall | Review Group requested to conduct an assessment of the charging methodology that is a feature of the overall Gas Transportation Charging framework to avoid the inefficient bypass of the NTS (currently the NTS Optional Commodity charge). The review assesses the objectives, identify requirements, analyse potential options and propose an enduring proportionate solution. Workgroup will consider consultation responses from 0621, 0635 and 0653. Currently 3 ideas for a charging methodology to avoid the inefficient bypass of the NTS. 2 of the 3 have been raised as alternates to 0678. If a Modification is raised from the review group, it is likely to have central impacts as any new NTS short haul product will be based on NTS capacity rather than commodity
Mod 0671 | With Workgroup | UNC -Transmission | WWU | New Capacity Exchange process at NTS exit points for capacity below baseline | TBC | Rule & System Change | TBC | System Impacts | Gemini system impacts to transfer User's Capacity between NTS Exit Points | TBC | Transmission and Shared Services | Steve Pownall | Modification proposes changes to the User Commitment obligations in TPD Section B to improve the efficiency of NTS Firm Exit Capacity bookings. October Panel issued the Modification to Workgroup due to report back in February 2019. Central systems will be impacted to transfer User's Capacity between NTS Exit Points. ROM response has been provided. Main impacts to Gemini. WG discussions deferred until August.
Mod 0672 | With Workgroup | UNC - UIG | Scottish Power | Incentivise Product Class 4 Read Performance | No implementation specified | Reporting and Invoicing | NA | UK Link | A Change Proposal will be required to deliver the reports specified under the Modification. The incentive regime will need to be developed with considerations around the invoicing element | NA | TBC | Simon Harris | Modification seeks to reduce Unidentified Gas (UIG) volume by incentivising read submission performance for Product Class 4 sites. Proposes to measure performance against an agreed performance target for Energy reconciled after a defined period and apply incentive charges against those Shippers whose Energy reconciliation performance is below the target threshold. With WG for development. ROM expected to understand impacts once the business rules are developed.
Mod 0674 | With Workgroup | UNC - UIG | Scottish Power on behalf of PAC | Performance Assurance Techniques and Controls | No implementation specified | Reporting and Invoicing | NA | NA | A Change Proposal will be required to deliver the reports specified under the Modification. The incentive regime will need to be developed with considerations around the invoicing element. | TBC | NA | Emma Smith | Modification seeks to provide an effective framework for the governance of industry performance that gives industry participants mutual assurance in the accuracy of settlement volume allocation. Developing through the WG. System impacts currently unknown. Reporting is definitely expected but the way sanctions and incentives are to be applied must be developed and system impacts assessed.
Mod 0675S | With Workgroup | UNC - WG | National Grid | Enabling changes to the BBL Interconnection Agreement to facilitate physical reverse flow | No implementation specified | Contractual change | NA | NA | No central system impacts. Contractual change to ancillary agreement between NG and BBL | Nov-19 | NA | Steve Pownall | Modification to enable changes to be made to the BBL Interconnection Agreement to facilitate physical reverse flow and amendment to reference temperature conditions. December Panel agreed to issue modification to WG and report back in February. No central system impacts expected. Panel identified new issues following the consultation period and sent the Modification back to WG for consideration.
Mod 0676R | With Workgroup | UNC - WG | Gazprom Energy | Review of Gas Transporter Joint Office Arrangements | Any Modifications as a result of 0676R will be impact assessed and any implications considered. | [5 empty] | NA | TBC | To request a review of the Uniform Network Code (UNC) General, Modification Rules and Joint Gas Transporter Governance arrangements for the Joint Office of Gas Transporters. Output for the Review Group is to assess whether the current arrangements are fit for purpose and recommend modifications where appropriate. Discussed again at March Panel and agreed for the Workgroup to be extended to August. Any changes from the review group will be assessed for central impacts. Next meeting is 26 June.
Mod 0677R | With Workgroup | UNC - WG | First Utility | Shipper and Supplier Theft of Gas Reporting Arrangements | Any Modifications as a result of 0677R will be impact assessed and any implications considered. | [5 empty] | NA | Ellie Rogers | This request is to review and identify any discrepancies in Shippers and Suppliers theft of gas reporting arrangements. Any changes from the review group will be assessed for central impacts. Review Group extension will be requested for solution options to be discussed. Central system impacts could be possible depending on the solution options.
Mod 0678 (A-J) Urgent | Awaiting Ofgem Decision | 0678 WG | Various proposers | Amendments to Gas Transmission Charging Regime | October 2019 | Rule and System Change | No | UK Link and Gemini | Impact picked up through the Gemini project team | Oct-19 | Transmission and Shared Services | Steve Pownall | Modification proposal is to amend the Gas Transmission Charging regime in order to better meet the relevant charging objectives and customer/stakeholder provided objectives for Gas Transmission Transportation charges and to deliver compliance with relevant EU codes (notably the EU Tariff Code). There are currently 11 alternates. Modifications look to address the issues highlighted in the Ofgem rejection letter for 0621 and the alternatives. Impacts to be picked up as part of the project team. Urgent status has been granted by Ofgem. Panel did not recommend that 0678 or any of the alternates should be implemented. Panel also indicated no clear majority view on the preference around which Modification better facilitates the Relevant Objectives. Modification and alternates are with Ofgem for a decision. Once decision is confirmed, the central changes will be picked up through the Gemini project team and delivered in October 2019.
Mod 0681S | With Workgroup | UNC - UIG | E.ON | Improvements to the quality of the Conversion Factor values held on the Supply Point Register | TBC | Rule and System Change | No | UK Link | Changes to identify the required sites and automate updates | Jun-20 | Retail & Network | Simon Harris | The purpose of this Modification is to improve the quality of the Conversion Factor data item on the Supply Point Register, which will in turn improve the accuracy of measured energy and therefore AQs. Change Proposal will be raised with the CDSP to deliver the requirements once the modification is suitable developed. Change Proposal with the CDSP - XRN4932 has been raised to develop this change in parallel with the Modification. A ROM request has been raised to assess impacts. UK Link system changes expected. Propose to remove from Bubbling Under as an Change Proposal has been raised.
Mod 0682 | With Workgroup | DWG | E.ON | Market Participant MDD Migration to UNC Governance from the SPAA | Feb-2020 | Obligation Change | NA | No system impacts | Creation of an obligation on the CDSP to manage the industry Market Participant Identifiers | Feb-20 | NA | Dave Addison | This modification requires that the CDSP manages the gas Market Domain Data for Market Participant Identities which are required to align with the introduction of the Retail Energy Code via the Central Switching Service and to align with the corresponding SPAA Change Proposal 467. No system impacts expected at this stage through this modification as it simply places the obligation on the CDSP in UNC. CP has been raised with the CDSP to deliver this change and put in place the necessary processes. WG report complete and due to go to June Panel. No system impacts expected for the Feb 2020 implementation. Process updates only. Any future system impacts for example the introduction of file flows is expected to be picked up as part of CSS.
Mod 0683 | With Workgroup | Transmission | Cadent | Updating the Offtake Arrangements Document (OAD) with recommendations resulting from UNC Request Workgroup 0646R – Review of the Offtake Arrangements Document – Phase 1 | NA | Documentation Change | NA | No system impacts | No central system impacts. Document change only | NA | NA | NA | This modification seeks to update the OAD in order to bring it in line with industry changes made since 2005. The Request 0646R Review of the Offtake Arrangements Document, Workgroup has since identified a number of areas in OAD that can be updated now (Phase 1), with this being the first in a number of modifications. No central system impacts expected.
Mod 0684 | Approved - Proposed to be removed from Bubbling Under | DWG | Scottish Power | Amendment of the Data Permission Matrix to add Meter Asset Provider as a new User type | Jun-19 | Permissions Change | NA | No system impacts | No central system impacts, only adding MAP ID to the DPM | NA | NA | Simon Harris | This modification seeks to amend the Data Permissions Matrix to add Meter Asset Provider (MAP) as a new User type. Initially discussed during the March Panel meeting and assigned to the DWG for development. Workgroup report completed and due to go to Panel in April. No system impacts, simply added MAP ID to the DPM. Panel voted to implement Modification 0684 at the May Panel. Implementation date is 28 June 2019. A 'clean-up' Modification to Section V5 of code will be raised as a follow up to this Modification. 0684 and the new Modification to be raised are permissions only, no system impacts. Proposed to be removed from Bubbling Under.
Mod 0685 | Awaiting Panel Decision | NA | National Grid | Amendment of the UNC term ‘Gas Deficit Warning’ to ‘Gas Balancing Notification’ | Oct-19 | Documentation Change | NA | Do not believe there are any system impacts | Need to assess but do not believe there are any system impacts | Oct-19 | NA | NA | To change the name of the UNC defined term ‘Gas Deficit Warning’ to ‘Gas Balancing Notification’. This modification is an outcome of the 0669 Review Group. We do not believe there are any central system impacts but need to assess and confirm. Consultation closed on 21 May and will return to June Panel. No system impacts expected.
Mod 0686 (Urgent) | Out for Consultation | Transmission | Vermilion Energy Ireland Limited | Removal of the NTS Optional Commodity Rate with adequate notice | Oct-19 | Rule and System Change | No | UK Link and Gemini | Impact assessment required | TBC | Transmission and Shared Services | Steve Pownall | Removal of the NTS Optional Commodity Rate1 with adequate notice. “Adequate notice” here means a notice period that is consistent with both the TAR NC and the UNC requirements. As long a notice period as possible is desirable for Users who may be subject to contractual constraints. It is not considered as an alternative to 0678 because the proposer has stated that it will be possible to implement this proposal for effect on the OCR tariff from October 2019 and any one of the 0678 (or alternatives for effect on other tariffs at the same time or any subsequent date. Currently out for Consultation until 07 June and to be considered within June Panel. Modification must still be assessed to consider a phased implementation of the 0678 change.
Mod 0687 | With Workgroup | UNC - DWG | Total Gas & Power (on behalf of ICoSS) | Clarification of Supplier of Last Resort Cost Recovery Process | TBC | System Change | No | UK Link | Impact assessment required but changes to introduce a new charge at the minimum | TBC | Retail & Network | Dave Addison /Ellie Rogers | Modification seeks to provide clarity on how any costs incurred by the Gas Distribution Networks (Transporters) as part of a Last Resort Supply Payment arising from a Supplier of Last Resort event are recovered from Shippers. It proposes the introduction of a new customer charge (the SoLR customer charge) into the Gas Transportation charging statements in order to provide detail on how these costs are allocated. With WG for development. System impacts expected to introduce a new charge type at the minimum. Level of central system impact could vary depending on the solution options e.g. adding the charge to an existing invoice or manually creating the charges. Due to report back to Panel in August.
Mod 0688 | With Workgroup | Transmission | Contract Natural Gas (on behalf of ICoSS) | Recovery of Shipper Losses incurred in Supplier of Last Resort events | TBC | System Change | No | TBC | Impact assessment required as it is currently unknown what and if this has central impacts | TBC | TBC | Steve Pownall | A change is proposed to allow Shippers that have incurred unrecoverable costs from shipping for sites where the Supplier is subject to a Supplier of Last Resort event, to recover such costs via Balancing Neutrality Charges. With WG for development. As currently drafted, system changes are likely and need to be assessed. Due to report back to Panel in August.
Mod 0689 | With Workgroup | UNC - DWG | Gazprom Energy | Removing the requirement to support Invoice queries before the due date with information from the .AML file | TBC | Rule Change | No | TBC | Impact assessment required as it is currently unknown what and if this has central impacts or if it is processes only | TBC | TBC | Dave Addison /Ellie Rogers | The purpose of this Modification is to allow Shippers to provide alternative supporting data when querying invoices from the CDSP. Seeks to remove obligation on Shippers to use CDSP provided supporting data to challenge an invoice. This is proposed due to the issues with the .AML file output. With WG and due to report back to Panel in August. The CDSP are currently assessing whether the change involves any system impacts or just processes.
Mod 0690 | With Workgroup | UNC - UIG | British Gas (on behalf of the UIG Taskforce) | Reduce qualifying period for Class 1 | TBC | Rule and Reporting Change | No | TBC | Impact assessment required as system changes are expected as well as new reports | TBC | Retail & Network, Data | Simon Harris | This Modification proposes that the qualifying period for the requirement for a meter point to become Class 1 is reduced, to limit the time period when very large sites are subject to NDM Demand Estimation, as opposed to being Daily Metered. The Modification also proposes a new Performance Assurance report of sites which have met the qualifying criteria for Class 1 but are either Class 3 or Class 4. With WG for development to return to August Panel. A Change Proposal with the CDSP will be required to implement the change. As a minimum reports will be required. ROM has been requested to assess impacts.
Mod 0691 | With Workgroup | UNC - UIG | British Gas (on behalf of the UIG Taskforce) | CDSP to convert Class 3 or 4 meter points to Class 1 when G1.6.15 criteria are met | TBC | Rule, System and Reporting Change | No | TBC | Impact assessment required as system changes are expected as well as new reports | TBC | Retail & Network, Data | Simon Harris | This Modification proposes that where the requirement for a Class 3 or 4 meter point to become Class 1 (number of calculations and number of months) has been met, and the Shipper has not taken steps to convert the site to Class 1 within a [1 month] grace period, that the CDSP would take steps to convert the meter point to Class 1. The Modification also proposes a new Performance Assurance report of sites where the CDSP has taken action, over the previous 12 months. With WG for development to return to August Panel. A Change Proposal with the CDSP will be required to implement the change. Impacts expected to reclassify relevant sites. ROM has been requested to assess impacts.
Mod 0692 | With Workgroup | UNC - DWG | Total Gas & Power (on behalf the UIG Taskforce) | Automatic updates to Meter Read Frequency | TBC | Rule and System Change | No | TBC | Impact assessment required as system changes are expected | TBC | Retail & Network | Dave Addison /Ellie Rogers | To place an obligation on the CDSP to automatically update the Meter Read Frequency of a Class 3 or 4 Supply Meter Point to Monthly, if: a) The AQ increases to 293,000 kWh or above; or b) The Supply Point Register is updated to show that either Smart or Advanced metering equipment is in place. In addition to undertake a one-off exercise to update the Meter Read Frequency of all current registered Supply Meter Points to Monthly, where they meet at least one of the two criteria above. With WG for development. Potentially will be split into two Modifications to cover parts a and b. System impacts expected to make the update. .
Mod 0693R | Awaiting Panel Consideration | TBC | Scottish Power (on behalf of the UIG Taskforce) | Treatment of kWh error arising from statutory volume-energy conversion | Any Modifications as a result of 0693R will be impact assessed and system implications considered. | [5 empty] | TBC | TBC | The Request is to review the treatment of the error in kWh that arises from statutory volume to-energy conversion factors in order to mitigate the impact on gas settlement, reconciliation and Annual Quantities (AQs). Due to be discussed and assigned a WG at June 2019 Panel.
Mod 0694 | Awaiting Panel Consideration | TBC | WWU | CDSP provision of Class 1 Read service | Any Modifications as a result of 0694R will be impact assessed and system implications considered. | [5 empty] | TBC | Dave Addison /Ellie Rogers | Modification Proposal 0647 proposed that Shippers should become responsible for the provision of Class 1 Reads. Work on that solution has suggested that a better solution may be some form of central provision by the CDSP. This Request is to enable exploration of this option and to develop a proposal that can be raised as a Modification Proposal in due course. Due to be discussed and assigned a WG at June 2019 Panel.