## Slide 1: DSC Change Management Committee Change Assurance Report May 2019

## Slide 2: Change Assurance Health Checks – UK Link Releases
Two UK Link related health checks were carried out in May 2019
The projects are June’19 Release and EUC Release
The summary reports and findings closure can be seen below
Update on CSSC findings closure

## Slide 3: UK Link June’19 Release Summary Dashboard
Area | Date | Change Project | RAYG by Area | CA1 – CA4 | Summary
Programme Delivery | May 2019 | UK Link June’19 – Health check | Overall Business Case Team Sponsorship Plan Governance Customer Scope and Solution Info Sec Other: | CA1 CA2 CA3 CA4 | UK Link June’19 release is made up of three Change Requests, all of which are perceived to be relatively straightforward. The project has coped well with the challenges highlighted in the previous health check reports, and this report has no CA1 or CA2 findings. There are many positive aspects, stakeholder interaction, plans are clear, RAIDs updated and control logs are maintained. Appropriate preparations are underway for subsequent stages of the project.
Requirements traceability into testing
Knowledge transfer
Test tools knowledge
Environment availability
Defect Management
Test Reporting
At Healthcheck
Update 03/06/19
0
0
0
0
5
5
10
10

## Slide 4: UK Link EUC Release Summary Dashboard
Area | Date | Change Project | RAYG by Area | CA1 – CA4 | Summary | 
Programme Delivery | May 2019 | UK Link EUC – Health check | Overall Business Case Team Sponsorship Plan Governance Customer Scope and Solution Info Sec Other: | CA1 CA2 CA3 CA4 | There has been significant improvement in the EUC project since the last health check in January 2019, and there are no open findings from that report. In this report there are no CA1 or CA2 findings. For this reason the overall rating of the project is yellow as there is evidence of remedial action to ensure that the release keeps on track with its level one milestones. . | 
At Healthcheck
Update 03/06/19
0
0
0
0
11
11
7
7
Requirements traceability into testing
Knowledge transfer
Test tools knowledge
Environment availability
Defect Management
Test Reporting

## Slide 5: CSSC Programme Early Assurance Summary Dashboard
Area | Date | Change Project | RAYG by Area | CA1 – CA4 | Summary
Programme Delivery | March 2019 | CSS Consequential Programme Change Assurance | Overall Business Case Team Sponsorship Plan Governance Customer Scope and Solution Other | CA1 CA2 CA3 CA4 | A significant number of roles remain open in the Programme org structure. Although a resource model is in place and recruitment is in progress, there is a continuing risk of resources not being available when required, and of contractor engagement for urgently-required roles, in place of planned permanent resource. The Programme’s governance structure alongside existing Platform and functional Xoserve governance, needs to be consolidated and lean, to avoid duplication and unclear escalation and decision-making routes. The decision to bring design forward against a backdrop of requirement and solution uncertainty places risk on the HLD to DD transition, the mitigation and control of which needs to be clear in phase governance. The Programme needs to make clear how it will control the governance gap between Stage Gate governance and the actual lifecycle phase, which are not due to align until Gate C, end of design. There is a possibility of significant external scope change well into our Detailed Design phase and the Programme will need an effective Change Control process. Engagement of TCS for Detailed Design without significant prior Xoserve solution knowledge gives risk to Detailed Design and may impact response to scope change and delivery.
2
10
15
0
Assurance was performed ahead of Stage Gate B (Startup), against which only minor gaps were noted, and Gate pass is expected. As the Programme is actually transitioning from High-Level to Detailed design, the assurance also looked beyond Gate B to the wider health of CSS C, as reflected in the below findings.
Info Security
Business Readiness
Suppliers
Finances
Procurement
Contract Management
1
2
10
0
At Healthcheck
Update 03/06/19