## Slide 1: DSC ChMC Switching Programme Update 12th June 2019

## Slide 2: Switching Programme
Xoserve detailed design
We are now in our detailed design phase, this phase includes internal and external work groups.
Our first workgroup was held on the 9th May our second workshop was held this Monday 10th June.
The dates and topics for the planned programme of workshops is detailed on a later slide for your information. We would welcome your attendance and input into the external workshops as we work towards our final solutions.
CSS design, build and test phase
The programme is in it’s DBT phase.
The majority of DCC’s procurement activities has completed with the following roles now procured:
Central registration and address service provider – Landmark
Service Integrator – Netcompany
Core systems assurance – Expleo
Service management provision – TBC (procurement still ongoing)

## Slide 3: Switching Programme
CSS physical design
Landmark are working individually with existing service providers (ESP’s) to work towards the interface physical design. The interface physical design has a target milestone date of the 15th July for the baseline and publication. Approval will be sought via the appropriate governance groups.
Switching Programme Workgroups
Xoserve are actively engaged with the switching programme. We have representatives on each of the Ofgem workgroups that have currently been stood up, each of these workgroups meeting monthly and include:
Data working group
Testing working group
Security working group
Design working group
REC work group
Details of these workgroup can be found on Ofgems dedicated switching web page

## Slide 4: Switching Programme
In addition to these Ofgem working groups the SI are standing up work groups that will reside underneath the Ofgem work groups. These workgroups will be working through the lower level detail required for the various areas, it is envisaged these will also meet monthly. The sub groups identified to be stood up so far include:
Sub data work group
Sub testing work group
There will be further Ofgem and SI workgroups stood up as the programme matures. One known workgroup is transition and cutover.
Governance
DCC programme governance framework has been establish with the SI requesting weekly report from each ESP. The information we provide is being used to track progress of the switching programme as well as individual ESP consequential activities.
Xoserve are currently tracking at an amber status, this is due to the delay in the appointment of the CSS Provider as we have a key dependency on the CSSP’s early physical design being shared to avoid the risk of re-work for our design activities. We are currently tracking Green for our plan, however are proceeding at risk should the key milestone of the physical design being finalised and approved is not met.

## Slide 5: Ofgem Switching Programme – Xoserve Consequential Detailed Design Workgroups
DSG Meeting |  | Provisional Agenda |  | DSG Meeting |  | Provisional Agenda
1 | 13/05/2019 | API |  | 3 | 26/06/2019 | Meter Point Creation
 |  | Nomination Enquiry |  |  |  | Gemini
 |  | Nomination (RRN) |  |  |  | Reporting
 |  | Address Updates |  | 4 | 11/07/2019 | Supplier Switching
 |  | MAM Updates |  |  |  | Change of Shipper
 |  | MAP Updates |  |  |  | Opening Reads
2 | 10/06/2019 | Settlement Data Submission |  | 5 | 25/07/2019 | Shipper Withdrawals
 |  | Stakeholder Management |  |  |  | Forced Registration
 |  | Switching Domain Data Updates |  |  |  | Bulk Transfers
 |  | RGMA |  | 6 | 16/08/2019 | Data Enquiry
 |  | SPA Updates |  |  |  | File Formats & APIs
 |  |  |  | 7 | 04/09/2019 | Contingency
 |  |  |  | 8 | 17/09/2019 | Contingency

## Slide 6: Approval request
During our detailed design phase one of the artefacts that will be produced will be change packs. I would like to request ChMC approval for the following:
  CSSC change packs to be issued separately from the BAU change packs
  I want to be able to deliver you our design solutions as quickly as possible but ensuring you have the appropriate time along with BAU change packs to review and provide your representations. We have potential options:
    In line with BAU schedule
    In line with BAU schedule but giving CSS an increased response time for representation
    CSSC change packs at fortnightly increments in between BAU packs
  The consequential change programme has it’s own XRN (master), this will be retained. Each CSSC change pack will be given an individual XRN’s on issue, this will link back to the master
  Each CSSC change pack will be titled as CSSC to ensure these are easily identifiable for you as they are released