## Master
Original List of OAD Review Amendments | [6 empty] | NGG |  | NGN |  | SGN |  | WWU
v6 (11.04.19)
Clause | Category | Root Cause | Specific Issue | Proposed Change (CGL) | Current Status | Action Required | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Revised Status
Section A
A2.1.2 | Tri-Partate SA | Cadent has two tri-party sites where there is one site owner and two site users located at an offtake. OAD is currently written in a way that assumes there is only one site owner and one site users, and that gas flows from the NTS into one LDZ. In reality this is not the case and the definitions need to be update to cover both approaches. | Offtake Definition i.e. "one or more Individual Offtakes Points, located at each site, at each of which gas can flow into the same LDZ." does not cater for tri-party sites | Amend definition to "one or more Individual Offtakes Points, located at each site, at each of which gas can flow into the same LDZ; or multiple Individual Offtakes Points, owned by different operators, on which gas flows into separate LDZ's". This will cater for tri-party sites This may impact upon A2.3.1 also. | G | A way forward has been proposed and accepted in Principle. Definitions still to be revised and agreed. | AP | Business rules to resolve tri-party sites currently under discussion but agree this is an issue to be resolved in this workgroup. Note that B1.2 seems to cater for more than one offtake at the site. Unclear to the impact of amending this definition. | AP | Agreed but wording could be revised to alow more flexibility simply saying "...gas can flow into an LDZ" would suffice. |  |  | AP | Agree definition needs to be changed. Actual wording to be provided by Legal text provider when Modification raised. | A
A2.1.4 | Definition Update | See A2.1.2 | Offtake Definition 'An NTS/LDZ Offtake is an Offtake at which gas can flow from the NTS into an LDZ' is too vague. | Revise to 'An NTS/LDZ Offtake is an Offtake at which gas can flow from the NTS into an LDZ via one or more physical points of connection' | A |  | AP | Business Rules for shared sites are in submitted Cadent paper. Impact of changing definition of an offtake under review as part of action 0807 of Workgroup 646R | AG | Agreed | AG | Proposed change seems acceptable | AP | Agree definition needs to be changed. Actual wording to be provided by Legal text provider when Modification raised. Suggest using offtake point instead of physical point | A
A2.1.4 | Shared Sites | Cadent has a specific site where the systems are connected by closed valves and if opened gas could flow. This site is not covered by a Supplemental Agreement. | Offtake Definition does not allow for closed NTS/LDZ offtakes that have the potential to flow gas. | Add new clause similar to 2.2.3 (LDZ/LDZ Offtakes) | G | CGL to Develop proposal on "Shared" sites. | AP | Business Rules for shared sites are in submitted Cadent paper. Impact of changing definition of an offtake under review as part of action 0807 of Workgroup 646R. May also wish to include sites which are isolated and not flowing gas | NA | Disagree, closed valves would still constitute a connection as gas is able to flow between the points an offtake valve maybe closed its still an offtake. | AG | Proposed change seems acceptable | AG | Agree | G
A2.2.1. | Definition Update | Cadent has three types of LDZ/LDZ offtakes. These are: > 7bar PRS's that are like NTS/LDZ offtakes with multiple feeds > Governor Installations (1 feed only) > Closed Valves in Public Highways (1 feed only) | LDZ Definition needs to mirror revised offtake definition | Revise to 'An LDZ/LDZ Offtake is an Offtake at which gas can flow from one LDZ into another LDZ via one or more physical points of connection'. | A |  | AP | Requires confirmation by impacted DN's | AG | Agreed |  |  | AP | Agree specific issue. Actual wording to be provided by Legal text….. | A
A2.3.1. | Tri-Partate SA | See A2.1.2 | See A2.1.2 |  | G | A way forward has been proposed and accepted in Principle. Definitions still to be revised and agreed. | AP | Business rules to resolve tri-party sites currently under discussion but agree this is an issue to be resolved in this workgroup. Note that B1.2 seems to cater for more than one offtake at the site. Unclear to the impact of amending this definition. |  |  |  |  | AP |  | A
A3.1.5 | Definition Update | See A2.1.4 | There have been sites identified with NTS that have closed connections. | Amend text so that 'Closed Offtakes' apply to NTS/LDZ Offtakes also. | G | CGL to Develop proposal on "Shared" sites. | AP | Business rules to resolve currently under discussion but agree this is an issue to be resolved in this workgroup. |  |  | NA | Not sure if this would be applicable to SGN additional information needed | AG | Agree | R
A3.2.1 | Process | The process for updating and signing of a new revised SA now needs to be supported by a Restatement document and Sealing of the Deeds process. | Do we need to explicitly state that entering into a new agreement for an existing offtake will supercede the previous version of the SA. This may save having to execute deeds via a legal process to approve the SA's for both parties? |  | A |  | NA | Do not belive OAD change required. Simple process review and agreement with correct stakeholders can get this resolved quickly. |  |  |  |  | AP | There maybe obligations in the previous SA that need to endure like provision of updates, records etc. You may not be able to just terminate an agreement. | R
A4.2.1 | Definition Update | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | No definition for the term 'Point of Offtake'. | Definition: A point of offtake is any connection between the upstream and downstream operators where gas can flow from one operator to the other. | A |  | AP | Agree that a definition for point of offtake would be useful but would suggest that is potentially already clause 4.2.2. Are there deficiencies with this? | AP | suggest wording is chaned to Offtake point or individual Offtake point to avoid need for definition. However the statement is clarified in 4.2 | AG | Proposed change seems acceptable | AP | Agree there should be a definition for "Point of offtake" but proposed words are not precise enough. Should be marked on plans and physcially on site. | A
New | Shared Sites | Offtake sites are governed by OAD but due to the current offtake definition in Clause A2.1.4 it only covers where gas flows from the NTS to a LDZ. Cadent have a number of offtake sites where a connection back onto the NTS is required to facilitate pipeline inspections that only occur one every 10-15 years. | Need to consider shared sites where normally a connection (open or closed) does not exist, but a connection is required to enable one operator to inspect its pipelines (i.e. Milwich/Cambridge/Abridge) |  | G | CGL to Develop proposal on "Shared" sites. | AP | Confirmation of business rules required before implementing solution as per Cadent's paper on shared sites. |  |  |  |  | AG | Agree | G
New | Shared Sites | See above | Should the scope of an offtake site be revised to cover all operations at such sites i.e. NTS connections as well as the provision to offtake gas into a LDZ? |  | G | CGL to Develop proposal on "Shared" sites. | AP | Confirmation of business rules required before implementing solution as per Cadent's paper on shared sites. |  |  |  |  | AP | Only where gas could flow ie include closed sites. | A
Section B
B1.2.2 | Definition Update | See A2.1.1 and clarity around definitions | Clause does not align to the offtake definition stated in A2.1.2 i.e. "one or more Individual Offtakes Points, located at each site, at each of which gas can flow into the same LDZ." and does not cover sites such as Alrewas, Audley, Ross and Winkfield | Text to be revised so that it clear that an offtake can have: a) multiple offtakes supplying different LDZ's operated by the same network operator; and b) multiple offtakes supplying different LDZ's operated by numerous network operators | A |  | NA | Can we confirm the value of changing? What instances of issues has this caused? Agree all definitions should align. What is the impact of changing this definition | AG | wording needs to be revised to fit the document (offtake needs defining as individual offtake point) if Agreed but wording could be revised to allow more flexibility simply saying "...gas can flow into an LDZ" would suffice. | AG | Proposed change seems acceptable | AG | Agree definitions between sections must align | R
B1.3.1(a) | Definition Update | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | Definition of Connections Facilities to be expanded to include upstream party connections. | Revise as follows: "subject to paragraph (b), the "Connection Facilities" are all the plant, equipment and buildings installed or to be installed by such Party (as provided in paragraph 2) at the Offtake Site, including (where relevant) Measurement Equipment, NTS Telemetry Facilities, Telemetry Connection Facilities; Daily Read Facilities and Upstream Party connections." | A |  | NA | The OAD is a transporter to transporter document, impact of changing the defintion needs to be understood. | AP | I'm not aware of issues so I'm unclear on why this is required | AG | Proposed change seems acceptable | AP | Agree definition not clear, note it applies to both parties. Should be telemetry and not NTS telemetry but don't think revised definition works because upstream party definition is undefined and what does upstream party means when referring to the upstream party. | R
B1.3.1 | Definition Update | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | No definition for the terms 'plant, equipment and buildings' | Define as follows: • Plant - mechanical assets that form the network pipeline system to allow gas to flow from one party to another • Equipment - secondary support assets that enable an operator to manage the gas flow through its pipeline system or plant. This would cover E&I, metering and telemetry requirements • Buildings - physical buildings/structures on site to house, contain or protect assets (i.e. physical buildings, kiosks and enclosures etc) | A |  | NA | Can we request greater clarity and some examples of the type of issue that this is trying to fix? Current arrangements allow for dialogue between the operators. | AP | I'm not aware of issues so I'm unclear on why this is required | AG | Proposed change seems acceptable | AP | What about fencing as it is not a building? What about roads, cameras, lighting, security equipment etc | R
B1.5.2 (c) | Process | This arrangement needs to be reconsidered as there are times where the Supplemental Agreement needs to be updated but the change does not necessarily require an OAD notice to be raised. | Where connection facilities are replaced, only the Appendices C and D need to be updated. | The new approach for the SA will need to have all relevant information in the SA updated not just the Point of Offtake or Metering information. This is specifically important concerning electrical and telemetry changes which impact currently on Appendix E. | A |  | AP | In relation to Supplemental Agreement, as a matter of process, the whole document should be reviewed for accuracy as part of the amendment process. | AP | Needs clarification. |  |  | AP | Agree to amend 1.5.2 to require updates to be made when other works are carried out. 2. We should issue a notice when someone is onsite when carrying out the work. | A
B1.5.3 | Process | It is difficult for all operators to comply with agreeing the SA before the changes go live on site due to the way work is executed, and the policy and procedures the industry works to for then collecting the required asset data and drawings. | It difficult to adhere to this specific clause due to a timing issue between what happens on site and then ascertaining the relevant information needed for the SA. | Another approach is required that allows for a draft SA to be put in place prior to new or altered requirements, and then allows for the finalisation to take place thereafter, but within a reasonable timeframe. | A |  | AP | With the current SA proposal excluding drawings (which have the longest lead time for completion) and in tandem with clause b1.5.4 which calls for an "effective date" is this issue now resolved? | AG | Agreed |  |  | AP | Agree but what is the suitable notice period and when someone goes to site to carry out works etc during the notice period. | A
B1.6.1 (b) | Definition Update | Site owner does not own all buildings (i.e. buildings, kiosks, enclosures) at an offtake site. Some may even be owned by a 3rd Party i.e. telecommunication masks. | See Root Cause | Text to be revised to remove 'buildings' from (i) and (ii) as this is covered by connection facilities in B1.6.1 (a) | A |  | AP | Appreciate that there may be an issue but unclear that this is the correct solution. | NA | Disagree | NA | Don't agree - The OAD specifies that Connection Facilities can include Land and Buildings and that each party is responsible for its Connection facility. B 1.6.1 (b) (i) and (iii) place responsibility on the site owner for land and buildings except where they fall under the definition of a Connection facility OAD B1.3.1 (a) and (b) | AP | If a third party given permission to put mask onsite then the land owner needs to ensure that they maintain their equipment. And also ensure site security is maintained. | R
B1.8.3 | Code Update | There have been occasions where an OAD notice has been raised but could not be approved for the window requested due to operations planned downstream on the distribution network. Had both operations taken place at the same time this would have led to a security of supply issue or put demand at risk. The security of supply angle does not seem to be covered off by OAD. | Clause only focuses on the impact to another party's Connection Facilities at a stated site and does not include any operational aspect of balancing the network requirements or security of supply. | The scope of clause B1.8.3(a) needs to be widened to include the impact to maintain gas supply via the offtake, and balancing the operational gas needs of the downstream DNO network. | A |  | AP | Agree with the concept of the issue to be resolved. Unclear if this should be fixed in this clause in the context of 3.4.2 or whether it is a process gap within Section G. | AG | Agreed |  |  | AG | Agree | G
B2.1.2 | SA Template | The current version of the SA's do not 'specify' all the Connection Facilities in Appendices C and D. These are also contained within Appendix E. | See Route Cause | The new approach for the SA will need to have all relevant information in the SA updated not just the Point of Offtake or Metering information. This clause to be updated following agreement on the new version of the SA. | G | SA Template currently under review. A revised proposal showing minimum requirements is to be produced. | AG | SA template under review , |  |  |  |  | AG | Agree | G
B2.2 | Code Update | Recovery of costs where the affected party has to raise a design approval in order to support another operators amendments. The time and effort to support on-site supervisory activities such as access to RTU's or to undertake electrical isolations also needs to be recouped. | The section needs a clause to allow the "affected party" to recover any necessary costs, on and off site, to support the "Modifying Party's" proposed work. This is needed due to the shared arrangements at offtakes that often needs both parties engagement to see the activity through, and the "affected party" should recover the cost of their support in line with the arrangements in Section L. |  | A |  | NA | Believe that this conflicts with 6.2.1 where it quotes "Access Rights shall be free of charge of payment of any kind." Also, cost recovery is outlined in Appendix L, is this insufficient alongside the cost scenarios mentioned in B at a high level. Think we should collectively explore the the cost/benefit of implementing this change if we are supporting one another |  | Not sure whats being proposed the altering party should carry out all works "at its own expense" covers this. agree that the affected party should be able to recover reasonable costs. |  |  | AG | Seems reasonable | R
B2.2.3(b) | Code Update | Similar to Clause B1.8.3 this only focuses on the impact to another party's Connection Facilities at a stated site and does not include any operational aspect of balancing the network requirements or security of supply. | See Root Cause | The scope of clause B2.2.3(b) needs to be widened to include the impact to maintain gas supply via the offtake, and balancing the operational gas needs of the downstream DNO network. | A |  | NA | Believe that this links with Section G. Is this not covered in there? | NA | disagree |  |  | AG | Seems reasonable | R
B2.2.4 | Code Update | It is difficult to comply with 'The Modifying party shall give each affected party prior written notice, not less than twelve Months or shorter period if parties agree', as this does not take account of how networks process change and the information needed for the OAD notice may not be available as the work may still be in the feasibility stage and the full impact to the others operators is not known or cannot be determined at that point. | See Root Cause | Revise approach to state "as much notice as possible" but the changes need to be based upon the Modification Process (G17/G35/GL5) that all operators follow. An alternative approach needs to be agreed between the operators. | A |  | NA | Believe that the current version is workable to allow operation in all scenarios. Effectively, in an ideal world operators provide as much notice as possible but if they can't through collaboration we would look to facilitate later requests. | AG | Agreed |  |  | AP | Normally not less than 12 months notice required. | R
B2.2.4 | Code Update | OAD notices detail the offtake, the work, the reason why and when. What is missing is the impact to the operator such as a loss of telemetry, power arrangements or site access may be an issue. By detailing the impact this will assist the other operator in understanding what they may or not may need to consider when reviewing the notice. | The impact arising from the notified work is not a requirement. This should be stated i.e. "loss of electrical power for 1 day" or "2 hours Telemetry outage required'. | Include an additional sub clause (f) entitled "Impact to Other Operators on Site" | A |  | NA | At the time of raising we would give as much info as possible. Again is this more of a process gap rather than a code change? | NA | disagree - outages etc maynot be known as notifications are put in as early as possible to avoid conflicts operational arangements should be agreed with site landlords |  |  | NA | Disagree but this should be for the NRO. | R
B2.2.5 | Maintenance | We need to divorce the Maintenance activity from the Non-routine activity. Routine maintenance should be shared under Section G and non-routine requirements covered by Section B. If successful as an approach, this clause will need to be removed. | In Section G, operators need to share maintenance plans. This is a consolidated list of routine and non-routine activity. Whilst non-routine activity should be known in advance, it is difficult to say when this will happen in the year, and some activity is re-active which you cannot capture via the annual process. | Revise the Maintenance requirements under Section G so that they are fit for purpose and consistent across all operators. | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NA | Maintenance workshop to confirm however this clause is for major modifications and not routine maintenance. Our prefernce would be one plan covering Maintenance and Non-routine. Also proposing the potential use of the maintenance plan serving as the OAD notice. | NA | disagree |  |  | NA | The issue is between planned and unplanned activitiy not routine/non routine activity or maintenance or investment work | R
B2.3.2 (c) | Maintenance | As above | In line with the revisions for B2.2.5 the clause needs to be updated to state it should be covered by Section B as Non-routine rather than Maintenance under Section G. | Revise clause depending upon outcome for clause B2.2.5 | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Maintenance workshop to confirm however this clause is for major modifications and not routine maintenance. Our prefernce would be one plan covering Maintenance and Non-routine. Also proposing the potential use of the maintenance plan serving as the OAD notice. | NA | disagree |  |  | NA | As above | R
B2.6.1 | Tri-Partate SA | Site Services need to be revised to take into account tri-party sites. Normally there are two SA's in place between the upstream and downstream operators. However, as the DNO's are normally the site owners, one SA will be between the site owner and site user, and the other SA will be between the site user and site user. Where an SA is between two site users, the site services are not confirmed by the site owner as they are not a party to the agreement therefore how can two site users agree these services without the site owner. | The "Services Party" can be a third operator who is the site owner but not a party to the Supplemental Agreement because this is between the upstream and downstream party only - as in the case at Ross-on-Wye and Winkfield (i.e. tri-partite sites) | Clause B2.6.1 to be revised to state that the "Services Party" must be named in the Supplemental Agreement who is recognised as the Site Owner and has a presence on site. | G | A way forward has been proposed and accepted in Principle. Definitions still to be revised and agreed. | AP | Business rule still to be confirmed however agree that site service party could be part of the Supplemental Agreement | AP | Still unsure on this |  |  | AP | Agree but requires debate around tripartite agreement | A
B2.6.1 | Tri-Partate SA | As above | The "Services Party" can be a third operator who is the site owner but not a party to the Supplemental Agreement because this is between the upstream and downstream party only - as in the case at Ross-on-Wye and Winkfield (i.e. tri-partite sites) | Clause B2.6.2 to be revised to include sub-clause (d) where the site owner is neither the upstream or downstream party named in the SA. Note: This will have a significant impact upon the agreements for tri party sites. | G | A way forward has been proposed and accepted in Principle. Definitions still to be revised and agreed. | AP | Business rule still to be confirmed however agree that site service party could be part of the Supplemental Agreement. This has an impact on 2 contracts only. |  |  |  |  | AP | As above | A
B2.6.4 | Code Update | The site services only outline what power is provided to the site user. Cathodic Protection and Electrical arrangements at offtakes are complex with shared boards and assets found on sites. These are not detailed anywhere in the SA which can lead to "interference" as ownership and maintenance is not clear. It recommended that Electricals should be a mandatory site service rather than an optional one as confirmed in Annex B2. | "Site services at NTS/LDZ offtake shall include the services specified in Part 1 of Annex B-2, and…..may include [those] in Part 2 Annex B-2". Both Parts need to be reviewed as Electricals should be mandatory but this is only stated in Part 2. | Propose mandatory site services are: Cathodic protection; Electricals/Power, Telemetry Arrangements; and Site Security. All others are non-mandatory or additional. | A |  | AP | Open to the idea of the change, however worth noting that we believe the current format SA allows us to put this in one of the sections without a code change. | AG | agreed |  |  | AP | Disagree as some sites the site user may have a separate site services as listed in part 2 so you cannot mandate itms from part 2 into part 1. (unless it is always the case). | A
B3.1.1 | Redundant Assets | Clause states that "right to the Site User to retain such Connection Facilities on the Site Owner land." as per the date of the SA or following relocation. The issue here is that this right allows the Site User to leave assets in place even though they are not operational and there are no clauses in OAD that allow the Site Owner to request the removal of redundant assets so it free's up land for other use. | Clause states that "right to the Site User to retain such Connection Facilities on the Site Owner land." as per the date of the SA or following relocation. The issue here is that this right allows the Site User to leave assets in place even though they are not operational and there are no clauses in OAD that allow the Site Owner to request the removal of redundant assets so it free's up land for other use. | Revise clause so that it relates to operational assets and non-operational assets of less than 12 months. An additional clause is then needed to allow the Site Owner to request the removal of any assets that have been non-operational for a period of 12 months or more. | G | Proposal Developed and refinements required following feedback. | AP | Business rule needs to be agreed before considering if a code change is required to facilitate that. N.b. The site owner may propose to the site user relocation of it's connection facilities as part of b3.3 | NA | 12month timescale maybe an issue, arangements should be made to remove redundant assets as and when there is an issue. |  |  | AP | We can request them to remove the assets and pay the reasonable costs to remove the assets (no profit). Speak to Grant. We could insert within the OAD that when assets are installed after a certain date then the party should remove them when they become redundant or unused. The removal of redundant plant or buildings should normally be undertaken within a reasonable period (group to decide) unless being retained for future reuse. In any event, remaining redundant plant or buildings should not expose either party to unreasonable costs or additional risk. | A
B3.4.2 | Code Update | Refer to B1.8.3 | This clause implies that the Site Owner can refuse consent to modifications if it falls in the scenarios listed in sub-clauses a-f. These sub clauses focus on the impacts to the physical site and do not take into account security of supply or balancing of the network issues. | Additional sub clauses needed to include the impact to maintain gas supply via the offtake, and balancing the operational gas needs of the downstream DNO network. | A |  | NE | Would like to understand how this interacts with Section G | NA | disagree |  |  | ? | Is related to a timing issue and not absolute yes/no consent? | A
B3.4.3 | Code Update | Recovery of costs where the affected party has to raise a design approval in order to support another operators amendments. The time and effort to support on-site supervisory activities such as access to RTU's or to undertake electrical isolations also needs to be recouped. | Clause focuses on the impacts to buildings only and needs to be expanded to include the impact to connection facilities as well. | Amend to "Where the Site Owner consents to the alteration, relocation or addition of or to Site User's Facilities, the Site Owner shall perform or procure any such minor alterations or works to existing buildings or structures as are referred to in paragraph 3.4.2(d), or its Connection Facilities, the Site User shall reimburse to the Site Owner the costs incurred by the Site Owner in doing so." | A |  | NE | Would like to understand how this fits in with section 4 (Compatibility). | AG | agreed |  |  | AP | Agree definition needs to be changed. Actual wording to be provided by Legal text provider when Modification raised. | A
B3.4.4 | Code Update | This clause should be expanded for the site user to consider options that will enable greater clarity on asset separation. | See Root Cause | Amend to "Notwithstanding paragraph 2.2 and the foregoing provisions of this paragraph 3.4, where the Site User wishes to alter or replace any of the Site User's Facilities, it shall, prior to altering or replacing such Connection Facilities, consider the feasibility of: a) relocating the Connection Facilities in question onto the Site User's own land b) consider delivery options that will reduce shared arrangements and to greater clarity on asset separation." | A |  | NA | Unclear as to the true value and practicality of adding this clause. As assets are coming to the end of life likely to see more shared assets being separated. | AP | What is the benefit to this proposal? |  |  | AG | Seems reasonable | R
B3.6 | Redundant Assets | This clause focuses on the Removal of Site User Facilities from only a Site User perspective. OAD provides no coverage for Site Owners to request the removal of Site Users assets, especially redundant assets given the right to retain stated in B3.1.1. | See Root Cause | New clauses need to be added that allow the Site Owner to request the Site User to remove redundant assets or assets that have been non-operational for more than 12 months. | G | Proposal Developed and refinements required following feedback. | AP | Business rule needs to be agreed before considering if a code change is required to facilitate that. N.b. The site owner may propose to the site user relocation of it's connection facilities as part of b3.3 | AG | disagree |  |  | AP | See line 33 but note 3.6.3(a) on reinstatement costs. Also should the site user be able to request the site owner relocate/remove their assets? | A
B3.7 | CNI | Section needs to be over-hauled and detailed the revised access rights due to the developments of the CNI requirements. This needs to include a section on when access/security has been breached by a Site User and the sanctions that a Site owner can impose in such cases. | See Root Cause |  | A | Pending the creation of an Industry CNI group, who will look into matters and determine a way forward | NE | Subject to outputs of CNI group | AP | the statemenht is still apropriate as the site owner is the land owner. |  |  | AP | Need to come up with some principles | A
B3.8 | CNI | Section needs to be over-hauled and detailed the revised rights due to the developments of the CNI requirements. This needs to include the process of how access is given and the role of the ARC. | See Root Cause |  | A | Pending the creation of an Industry CNI group, who will look into matters and determine a way forward | NE | Subject to outputs of CNI group |  | subject to review. |  |  | AP | This will be agreed at the CNI working group . | A
B4.1.5 | Code Update | There have been occasions where the processes of OAD have been followed that have resulted in a material impact upon Cadent assets or operations by another operator. Whilst these have been followed up via appropriate channels, we have had one specific issues that has not been resolved adequately that needs to be escalated however, OAD does not really provide what that escalation route ought to be. | Clause needs to be enhanced to reflect what course of action can be taken in the event that the Parties cannot agree on a resolution, or one party is seen not to be addressing the issue. What routes of escalation should be taken i.e. offtake committee etc..... |  | A |  | AP | Please can we discuss the specfic instances off-line to identify the most appropriate fix. Dispute resolution already within UNC. |  |  |  |  | NA | General Terms A - Dispute procedures will apply. But should be resolved between both parties in the first instance. | R
B5.3.1 | Code Update | Shared telemetry can have several variations. It could mean the whole telemetry system i.e. RTU, routers, dish, ADSL lines are shared but other instances other assets such as Allen Bradleys/Micrbox Units have also been known to be shared. Given that the telemetry system contain key assets in obtaining information from site and for the telemetry owner to provide data back to the upstream party, this should have greater emphasis in the site services section as to what is meant by shared. | Requirement states shared telemetry should be recorded in the SA but this is not covered in Annex B-1 or Annex B-2. | Amend Appendix E Template to ensure Telemetry requirements are captured. | A |  | AG | Points of telemertry (Appendix E) were agreed as part of a previous modification but we can discuss what additional info is needed. | AP | agree in principal. |  |  | AP | Agree. Down to the CNI Group to resolve. | G
B6 | CNI | Similar to B3.6 and B3.7. Section needs to be over-hauled and detailed the revised access rights due to the developments of the CNI requirements. This needs to include a section on when access/security has been breached by a Site User and the sanctions that a Site owner can impose in such cases. | See Root Cause |  | A | Pending the creation of an Industry CNI group, who will look into matters and determine a way forward | NE | Subject to outputs of CNI group | AP | sanctions for a site user who has access breaching security please clarify? |  |  | AP | See above | A
B6 | Code Update | Access needs to cover when CDM applies as this restricts access during certain specific types of activity. | See Root Cause | Site owner to retain access to CDM areas in cases of emergency | A |  | NE | To be discussed internally with NGT |  |  |  |  | AG | Agree | A
B6.3.1 | Code Update | Alignment required with Section C of OAD | The clause should be expanded to ensure that the Site Party does not make it over onerous for site access to occur | include sub-clause "c) shall be no more onerous as respects the personnel of the other Party(ies) (as Access Party(ies)) than in respect of the Site Party's own personnel". | A |  | NA | Are Cadent thinking about specfic examples? Can this be resolved offline? |  |  |  |  | AG | Agree. Should be Site Owner not site Party. | R
Section C
C2.8 | Definition Update | If the definition for NTS/LDZ offtakes is to be expanded to cover closed offtakes as well, then this clause needs to be amended. | This section needs to be revised to include closed NTS/LDZ offtakes as well. |  | G | CGL to Develop proposal on "Shared" sites. | AP | Will agree business rule before determinng the best method for facilitating that. | AP | Need to understand Closed Offtakes | AG | Agree | AG | Agree | G
C5.1.2(b) | Code Update | For offtakes that are in the boundary of a National Grid terminal site, COMAH regulations have a significant issue upon site access and site safety. These regulations cause additional requirements that need to be complied with above and beyond those requirements for normal offtakes. This should be recognised within the code to make it explicit and clear. | Clause needs to be expanded to cover Top Tier COMAH regulations which will cover offtakes within Terminal Sites. | Amend text to: "shall take account of the Site Party's Safety Case, the Access Party(ies)'s Safety Case(s), the SCO Interface Procedure and the Site Party's Site Emergency Procedures, and any other relevant statutory requirements such as COMAH regulations. | A |  | NE | Will need to understand fully the outputs of the NGT investigation into Comah to understand if this is an appropriate change. |  |  |  |  | AG | Agree issue needs to be addressed. | G
Section G
G1.2.1 | Definition Update | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | The term "affected party" requires definition | For clarity use same text as stated currently in Clause B2.2.3 (b) | A |  | NE | Upcoming maintenance workshop to resolve |  |  | AG | Agree | AG | Seems reasonable | G
G1.2.1 | Code Update | See above | Sub categories to be revised. | Revise to: Routine or non-routine maintenance that has an: > Impact to gas flow by either party > Impact on electrical arrangements by either party > Impact to shared telemetry arrangements by either party > Impact to key measurement equipment i.e. P1 pressure transmitters or DNO Metering systems > Impact to Cathodic Protection systems > Impact to any of the above where testing information needs to be passed to the Site Owner in order to maintain site compliance | A |  | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Agree with revised bullet list, but need clarity on what is meant by routine or non-routine, isn't it all "relevant maintenance" as currently described? | A
G2.2.3 | Code Update | See G1.2.1 | Revise in line with new sub-categories |  | A |  | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AG | Agree | A
G2.2.4 | Code Update | See G1.2.1 | Revise in line with new sub-categories |  | A |  | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AG | Agree | A
G2.2.5 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Remove as not needed |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Agree remove because it is a reference to the previous bullet list change in section G1.2.1 | A
G2.2.6 (b) | Code Update | See G1.2.1 | Revise in line with new sub-categories |  | A |  | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AG | Agree | A
G2.4 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Given maintenance is reviewed 6-monthly is there a need to have a process to amend individual requirements as this seems over kill | Remove section as this is covered by the annual process | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G2.5 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | For any Flow Maintenance Days to be agreed this needs to be undertaken in consultation with the DNO taking into account security of supply and balancing of the network demand. |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G2.6 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Is this section needed as it just increases cost for the DNO's |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G3.2.3 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Should NRO's be shared for maintenance that has an impact upon another user? |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G3.3 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Again is this section necessary? If maintenance is postponed, it surely rolls over to the next planning cycle? | Remove section as this is covered by the annual process. | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G3.4 | Definition Update | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | Redefine urgent maintenance | Redefine to: Any maintenance that has an impact upon another operator that requires urgent addressing that cannot be confirmed ahead of time as part of the maintenance programme timescales or is reactive action where a modification has taken place that should have been notified under Section B. | A | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  | NA | ? | AG | Agree | R
G3.6.1 | Maintenance | There have been occasions where the processes of OAD have been followed that have resulted in a material impact upon Cadent assets or operations by another operator. Whilst these have been followed up via appropriate channels, we have had one specific issues that has not been resolved adequately that needs to be escalated however, OAD does not really provide what that escalation route ought to be. | This section very much focuses on the flows at offtakes only and not the wider security of supply issues. What happens if parties cannot agree what scenarios would take precedent? |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
New | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Need to ensure the maintenance section focuses on maintenance and does not include investment related activities as these are covered by Section B |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AG | Agree | G
Annex G1 | Code Update | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Minimum details to be revised as it is difficult for Cadent to provide, due to the way that it plans its maintenance activities | Revised details to: > Offtake Site > Period to be completed in > Type of Maintenance (in line with revised sub categories) > Details (if impact is significant) | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Need more dialogue | A
Section L
L2.3.1 | Code Update | Cost recovery is becoming more an issue for operators as they seek to recover costs to support another operators activities on site. The cost recovery process should be agreed upfront rather than just submitting an invoice and cost recovery arising from "interference" also needs to be articulated. | Process to be revised so that it is linked to the modification process or before an event occurs. | Process to be revised so that it is linked to Section B where recoverable costs are agreed before an event, and then L2.3.1 is retained for any other issue that has arisen where upfront engagement could not take place. | A |  | AP | Need to agree a consistant and appropriate philosophy on cost recovery before proposing a code change. |  |  |  |  | AP | Agree - consider a subsidiary documents that list the applicable chargers | A
Section M |  |  | No changes. R&EA to review
Section N
N2.1.2(c ) | Definition Update | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | The definition here states "A reference in this Document to a Party shall be construed as a reference...... (c) in the context of an Offtake Site, to a Party whose System is connected to another System at an Offtake located at that Offtake Site.". | Clarity is needed on what this definition means, and these definitions need tieing back to the definitions in Sections A & B for consistency. | A |  | AP | Definition analysis. |  |  | AG | Agree | AP | Definition is clear, however if it is inconsistent with sections A & B then it needs rectifying. | A
N3.2.2 | Process | The process for updating an SA document is cumbersome and is based on National Grid making all changes to the documents. This way is open to mis-interpretation of the information especially if it is not National Grid that has undertaken the work and that it is National Grid's commercial team making the changes rather than the engineering staff. | The clause states that "The Parties to a Supplemental Agreement are required (by certain provision of this Document) to amend the Supplemental Agreement to reflect and record changes in relation to the Offtake; and undertake to make such amendments promptly and in accordance with this Document." and inconsistent with Clause B1.5.3 | Clauses need to be aligned following the revision on B1.5.3. | A |  | NA | Does the phrase "In accordance with this document" not already link us back to B.1.5.3 |  |  |  |  | AG | Agree | R
N3.3.1 (a) + (b) | Process | See N3.2.2 | Section needs to be over-hauled as the process does not work. | If would be far better that if a DNO wants to update a SA, they request the latest version from National Grid who provide a copy with tracked changes on it. The DNO updates the information and returns the document to National Grid to review in the timescales agreed. This will be a more efficient process as the information provided could be mis-understood by the National Grid commercial team, which will then lead to delays from having to clarify and explain the updated text. | A |  | AG | Agreed: process change rather than a code change |  |  |  |  | AP | Agree process needs reviewing, suggest the party making the changes proposes the changes to the other party. | G
N3.3.2 | Process | The process for updating and signing of a new revised SA now needs to be supported by a Restatement document and Sealing of the Deeds process. | Clause refers to the executing of the SA following agreed revisions. | Do we need to amended this clause to add in that once an SA is signed by both parties, this then supercedes the previous version. It is hoped that this will avoid the need to revise the deed for the site and thus reduce the time taken to formally agree a new SA between the parties. | A |  | AP | Process for execution to be discussed and agreed. Appropriate changes can be made if required. |  |  |  |  | AP | Are they suggesting that SAs are amended or are they terminiated and a new one issued on the same date? And if so what about the clauses in the original agreement that need to survive. | A
N7 | Other |  | Loss and Liability | Need R&EA (MS) to review | A |  |  | Would appreciate further clarify on the issue at hand here. | [5 empty] | We will review your proposals. | A
New | Tri-Partate SA | There have been occasions for tri-party sites where one SA has been updated between the Site Owner and site user, but the changes have not been mirrored across to the other SA in place between the site user and site user. This is critical as issues such as there are data items that are common between the two SA's in place, such as access, security, cathodic protection, utilities supply and drawings i.e. GA and HAZ resulting in mis-match of data between the two SA's. | Section N does not contain any clauses outlining that National Grid are the custodians of the Supplemental Agreements. | If National Grid are the custodians of the SA's, then additional requirements are needed i.e. to maintain the integrity of information between SA documents for where there is more than one offtake at a location including tri-party sites. If one document is updated, they should have a duty to inform the other operator highlighting the changes that need to be made. | G | A way forward has been proposed and accepted in Principle. Definitions still to be revised and agreed. | AP | Amendment process in OAD mentiones upstream and downstream processes. Process improvements are now in place to ensure tri party sites are kept consistent. |  |  |  |  | AP | This suggests the site owner should be responsible for ensuring consistency between SAs agreements. | A
New | SA Template | General point. Should the SA's have version control so that you could see what changes were implemented when and arising from what work. | No version control for SA's | Should the SA's include a version control to highlight the history of changes? | G | SA Template currently under review. A revised proposal showing minimum requirements is to be produced. | AP | Currently under review but intial feedback suggests that it is not normal practice to include version control within contracts |  |  |  |  | AG | Agree | G
N9.1.1 | Code Update | This clause needs to be linked back to 'material' impact in Section B for modifications. We have experienced outages in the past to telemetry systems at offtakes which has resulted in a loss of control of the site, albeit for a short period of time, without an OAD notice being raised to cover the activity. When challenged this N9.1.1 was used as justification whereas it was felt that the planned change and outage should have been notified via an OAD notice under Section B. | The section covers "The “Transmission System Operator to Distribution System Operator Agreement Guidelines”... re the co ordination and management of changes, faults and outages on the information systems and communications network infrastructure. | Additional clause needed that any planned changes, repair of faults and outages need to be reviewed in line the requirements set out under Section B. | A |  | AP | Agree that some sort of communication is required. Need to come to consensus as to what that is |  |  |  |  | AG | Agree | G
Appendix | SA Template | Current Supplementals do not document all the connection facilities on site as per Section B of OAD. Specifically, whilst the mechanical drawing is in include the SA, there is no mention of the electrical assets on site which often can be shared and therefore lead to confusion on who owns them and thus maintains them. The SA should cover asset ownership plus the other relevant information needed for commercial purposes in managing the conveyance of gas from one operator to another. | Appendix SA to be revised to the new OAD Pack. |  | G | SA Template currently under review. A revised proposal showing minimum requirements is to be produced. | AG | Supplemental Agreements under review. Correct level of information required to be determined to prevent continuous cycle of updating agreements |  |  |  |  | AG | Need a proposal of what could be included - not 30 E & I diagrams | G

## 0683
Proposed OAD Amendments (MOD 0683) | [6 empty] | NGG |  | NGN |  | SGN |  | WWU
v6 (11.04.19)
Clause | Category | Root Cause | Specific Issue | Proposed Change (CGL) | Current Status | Action Required | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Revised Status
Section A
A2.1.2 | Tri-Partate SA | Cadent has two tri-party sites where there is one site owner and two site users located at an offtake. OAD is currently written in a way that assumes there is only one site owner and one site users, and that gas flows from the NTS into one LDZ. In reality this is not the case and the definitions need to be update to cover both approaches. | Offtake Definition i.e. "one or more Individual Offtakes Points, located at each site, at each of which gas can flow into the same LDZ." does not cater for tri-party sites | Amend definition to "one or more Individual Offtakes Points, located at each site, at each of which gas can flow into the same LDZ; or multiple Individual Offtakes Points, owned by different operators, on which gas flows into separate LDZ's". This will cater for tri-party sites This may impact upon A2.3.1 also. | G | Covered by Tri-partite proposals. Does definition need to be reviewed? | AP | Business rules to resolve tri-party sites currently under discussion but agree this is an issue to be resolved in this workgroup. Note that B1.2 seems to cater for more than one offtake at the site. Unclear to the impact of amending this definition. | AP | Agreed but wording could be revised to alow more flexibility simply saying "...gas can flow into an LDZ" would suffice. |  |  | AP | Agree definition needs to be changed. Actual wording to be provided by Legal text provider when Modification raised. | A
A2.1.4 | Shared Sites | Cadent has a specific site where the systems are connected by closed valves and if opened gas could flow. This site is not covered by a Supplemental Agreement. | Offtake Definition does not allow for closed NTS/LDZ offtakes that have the potential to flow gas. | Add new clause similar to 2.2.3 (LDZ/LDZ Offtakes) | G | Covered by new shared sites arrangements | AP | Business Rules for shared sites are in submitted Cadent paper. Impact of changing definition of an offtake under review as part of action 0807 of Workgroup 646R. May also wish to include sites which are isolated and not flowing gas | NA | Disagree, closed valves would still constitute a connection as gas is able to flow between the points an offtake valve maybe closed its still an offtake. | AG | Proposed change seems acceptable | AG | Agree | G
A2.3.1. | Tri-Partate SA | See A2.1.2 | See A2.1.2 |  | G | Covered by Tri-partite proposals. | AP | Business rules to resolve tri-party sites currently under discussion but agree this is an issue to be resolved in this workgroup. Note that B1.2 seems to cater for more than one offtake at the site. Unclear to the impact of amending this definition. |  |  |  |  | AP |  | A
A3.1.5 | Definition Update | See A2.1.4 | There have been sites identified with NTS that have closed connections. | Amend text so that 'Closed Offtakes' apply to NTS/LDZ Offtakes also. | G | Covered by new shared sites arrangements | AP | Business rules to resolve currently under discussion but agree this is an issue to be resolved in this workgroup. |  |  | NA | Not sure if this would be applicable to SGN additional information needed | AG | Agree | R
A3.2.1 | Process | The process for updating and signing of a new revised SA now needs to be supported by a Restatement document and Sealing of the Deeds process. | Do we need to explicitly state that entering into a new agreement for an existing offtake will supercede the previous version of the SA. This may save having to execute deeds via a legal process to approve the SA's for both parties? |  | A | Covered by revised recitals | NA | Do not belive OAD change required. Simple process review and agreement with correct stakeholders can get this resolved quickly. |  |  |  |  | AP | There maybe obligations in the previous SA that need to endure like provision of updates, records etc. You may not be able to just terminate an agreement. | R
New | Shared Sites | Offtake sites are governed by OAD but due to the current offtake definition in Clause A2.1.4 it only covers where gas flows from the NTS to a LDZ. Cadent have a number of offtake sites where a connection back onto the NTS is required to facilitate pipeline inspections that only occur one every 10-15 years. | Need to consider shared sites where normally a connection (open or closed) does not exist, but a connection is required to enable one operator to inspect its pipelines (i.e. Milwich/Cambridge/Abridge) |  | G | Covered by new shared sites arrangements | AP | Confirmation of business rules required before implementing solution as per Cadent's paper on shared sites. |  |  |  |  | AG | Agree | G
New | Shared Sites | See above | Should the scope of an offtake site be revised to cover all operations at such sites i.e. NTS connections as well as the provision to offtake gas into a LDZ? |  | G | Covered by new shared sites arrangements | AP | Confirmation of business rules required before implementing solution as per Cadent's paper on shared sites. |  |  |  |  | AP | Only where gas could flow ie include closed sites. | A
Section B
B1.8.3 | Code Update | There have been occasions where an OAD notice has been raised but could not be approved for the window requested due to operations planned downstream on the distribution network. Had both operations taken place at the same time this would have led to a security of supply issue or put demand at risk. The security of supply angle does not seem to be covered off by OAD. | Clause only focuses on the impact to another party's Connection Facilities at a stated site and does not include any operational aspect of balancing the network requirements or security of supply. | The scope of clause B1.8.3(a) needs to be widened to include the impact to maintain gas supply via the offtake, and balancing the operational gas needs of the downstream DNO network. | A | Covered by revised arrangements for "affected Party" | AP | Agree with the concept of the issue to be resolved. Unclear if this should be fixed in this clause in the context of 3.4.2 or whether it is a process gap within Section G. | AG | Agreed |  |  | AG | Agree | G
B2.1.2 | SA Template | The current version of the SA's do not 'specify' all the Connection Facilities in Appendices C and D. These are also contained within Appendix E. | See Route Cause | The new approach for the SA will need to have all relevant information in the SA updated not just the Point of Offtake or Metering information. This clause to be updated following agreement on the new version of the SA. | G | Covered by revised SA Template | AG | SA template under review , |  |  |  |  | AG | Agree | G
B2.2 | Code Update | Recovery of costs where the affected party has to raise a design approval in order to support another operators amendments. The time and effort to support on-site supervisory activities such as access to RTU's or to undertake electrical isolations also needs to be recouped. |  | The section needs a clause to allow the "affected party" to recover any necessary costs, on and off site, to support the "Modifying Party's" proposed work. This is needed due to the shared arrangements at offtakes that often needs both parties engagement to see the activity through, and the "affected party" should recover the cost of their support in line with the arrangements in Section L. |  | A |  | NA | Believe that this conflicts with 6.2.1 where it quotes "Access Rights shall be free of charge of payment of any kind." Also, cost recovery is outlined in Appendix L, is this insufficient alongside the cost scenarios mentioned in B at a high level. Think we should collectively explore the the cost/benefit of implementing this change if we are supporting one another |  | Not sure whats being proposed the altering party should carry out all works "at its own expense" covers this. agree that the affected party should be able to recover reasonable costs. |  |  | AG | Seems reasonable | R
B2.2.3(b) | Code Update | Similar to Clause B1.8.3 this only focuses on the impact to another party's Connection Facilities at a stated site and does not include any operational aspect of balancing the network requirements or security of supply. | See Root Cause | The scope of clause B2.2.3(b) needs to be widened to include the impact to maintain gas supply via the offtake, and balancing the operational gas needs of the downstream DNO network. | A | Covered by revised arrangements for "affected Party" | NA | Believe that this links with Section G. Is this not covered in there? | NA | disagree |  |  | AG | Seems reasonable | R
B2.6.1 | Tri-Partate SA | Site Services need to be revised to take into account tri-party sites. Normally there are two SA's in place between the upstream and downstream operators. However, as the DNO's are normally the site owners, one SA will be between the site owner and site user, and the other SA will be between the site user and site user. Where an SA is between two site users, the site services are not confirmed by the site owner as they are not a party to the agreement therefore how can two site users agree these services without the site owner. | The "Services Party" can be a third operator who is the site owner but not a party to the Supplemental Agreement because this is between the upstream and downstream party only - as in the case at Ross-on-Wye and Winkfield (i.e. tri-partite sites) | Clause B2.6.1 to be revised to state that the "Services Party" must be named in the Supplemental Agreement who is recognised as the Site Owner and has a presence on site. | G | Covered by Tri-partite proposals. | AP | Business rule still to be confirmed however agree that site service party could be part of the Supplemental Agreement | AP | Still unsure on this |  |  | AP | Agree but requires debate around tripartite agreement | A
B2.6.1 | Tri-Partate SA | As above | The "Services Party" can be a third operator who is the site owner but not a party to the Supplemental Agreement because this is between the upstream and downstream party only - as in the case at Ross-on-Wye and Winkfield (i.e. tri-partite sites) | Clause B2.6.2 to be revised to include sub-clause (d) where the site owner is neither the upstream or downstream party named in the SA. Note: This will have a significant impact upon the agreements for tri party sites. | G | Covered by Tri-partite proposals. Does definition need to be reviewed? | AP | Business rule still to be confirmed however agree that site service party could be part of the Supplemental Agreement. This has an impact on 2 contracts only. |  |  |  |  | AP | As above | A
B2.6.4 | Code Update | The site services only outline what power is provided to the site user. Cathodic Protection and Electrical arrangements at offtakes are complex with shared boards and assets found on sites. These are not detailed anywhere in the SA which can lead to "interference" as ownership and maintenance is not clear. It recommended that Electricals should be a mandatory site service rather than an optional one as confirmed in Annex B2. |  | "Site services at NTS/LDZ offtake shall include the services specified in Part 1 of Annex B-2, and…..may include [those] in Part 2 Annex B-2". Both Parts need to be reviewed as Electricals should be mandatory but this is only stated in Part 2. | Propose mandatory site services are: Cathodic protection; Electricals/Power, Telemetry Arrangements; and Site Security. All others are non-mandatory or additional. | A |  | AP | Open to the idea of the change, however worth noting that we believe the current format SA allows us to put this in one of the sections without a code change. | AG | agreed |  |  | AP | Disagree as some sites the site user may have a separate site services as listed in part 2 so you cannot mandate itms from part 2 into part 1. (unless it is always the case). | A
B3.1.1 | Redundant Assets | Clause states that "right to the Site User to retain such Connection Facilities on the Site Owner land." as per the date of the SA or following relocation. The issue here is that this right allows the Site User to leave assets in place even though they are not operational and there are no clauses in OAD that allow the Site Owner to request the removal of redundant assets so it free's up land for other use. | Clause states that "right to the Site User to retain such Connection Facilities on the Site Owner land." as per the date of the SA or following relocation. The issue here is that this right allows the Site User to leave assets in place even though they are not operational and there are no clauses in OAD that allow the Site Owner to request the removal of redundant assets so it free's up land for other use. | Revise clause so that it relates to operational assets and non-operational assets of less than 12 months. An additional clause is then needed to allow the Site Owner to request the removal of any assets that have been non-operational for a period of 12 months or more. | G | Proposal Developed and refinements required following feedback. | AP | Business rule needs to be agreed before considering if a code change is required to facilitate that. N.b. The site owner may propose to the site user relocation of it's connection facilities as part of b3.3 | NA | 12month timescale maybe an issue, arangements should be made to remove redundant assets as and when there is an issue. |  |  | AP | We can request them to remove the assets and pay the reasonable costs to remove the assets (no profit). Speak to Grant. We could insert within the OAD that when assets are installed after a certain date then the party should remove them when they become redundant or unused. The removal of redundant plant or buildings should normally be undertaken within a reasonable period (group to decide) unless being retained for future reuse. In any event, remaining redundant plant or buildings should not expose either party to unreasonable costs or additional risk. | A
B3.4.2 | Code Update | Refer to B1.8.3 | Query concenring the gas flow test for "affected party" | This clause implies that the Site Owner can refuse consent to modifications if it falls in the scenarios listed in sub-clauses a-f. These sub clauses focus on the impacts to the physical site and do not take into account security of supply or balancing of the network issues. | Additional sub clauses needed to include the impact to maintain gas supply via the offtake, and balancing the operational gas needs of the downstream DNO network. | A |  | NE | Would like to understand how this interacts with Section G | NA | disagree |  |  | ? | Is related to a timing issue and not absolute yes/no consent? | A
B3.6 | Redundant Assets | This clause focuses on the Removal of Site User Facilities from only a Site User perspective. OAD provides no coverage for Site Owners to request the removal of Site Users assets, especially redundant assets given the right to retain stated in B3.1.1. | See Root Cause | New clauses need to be added that allow the Site Owner to request the Site User to remove redundant assets or assets that have been non-operational for more than 12 months. | G | Proposal Developed and refinements required following feedback. | AP | Business rule needs to be agreed before considering if a code change is required to facilitate that. N.b. The site owner may propose to the site user relocation of it's connection facilities as part of b3.3 | AG | disagree |  |  | AP | See line 33 but note 3.6.3(a) on reinstatement costs. Also should the site user be able to request the site owner relocate/remove their assets? | A
B5.3.1 | Code Update | Shared telemetry can have several variations. It could mean the whole telemetry system i.e. RTU, routers, dish, ADSL lines are shared but other instances other assets such as Allen Bradleys/Micrbox Units have also been known to be shared. Given that the telemetry system contain key assets in obtaining information from site and for the telemetry owner to provide data back to the upstream party, this should have greater emphasis in the site services section as to what is meant by shared. |  | Requirement states shared telemetry should be recorded in the SA but this is not covered in Annex B-1 or Annex B-2. | Amend Appendix E Template to ensure Telemetry requirements are captured. | A |  | AG | Points of telemertry (Appendix E) were agreed as part of a previous modification but we can discuss what additional info is needed. | AP | agree in principal. |  |  | AP | Agree. Down to the CNI Group to resolve. | G
C2.8 | Definition Update | If the definition for NTS/LDZ offtakes is to be expanded to cover closed offtakes as well, then this clause needs to be amended. |  | This section needs to be revised to include closed NTS/LDZ offtakes as well. |  | G | CGL to Develop proposal on "Shared" sites. | AP | Will agree business rule before determinng the best method for facilitating that. | AP | Need to understand Closed Offtakes | AG | Agree | AG | Agree | G
G1.2.1 | Definition Update | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. |  | The term "affected party" requires definition | For clarity use same text as stated currently in Clause B2.2.3 (b) | A |  | NE | Upcoming maintenance workshop to resolve |  |  | AG | Agree | AG | Seems reasonable | G
N3.3.1 (a) + (b) | Process | See N3.2.2 |  | Section needs to be over-hauled as the process does not work. | If would be far better that if a DNO wants to update a SA, they request the latest version from National Grid who provide a copy with tracked changes on it. The DNO updates the information and returns the document to National Grid to review in the timescales agreed. This will be a more efficient process as the information provided could be mis-understood by the National Grid commercial team, which will then lead to delays from having to clarify and explain the updated text. | A |  | AG | Agreed: process change rather than a code change |  |  |  |  | AP | Agree process needs reviewing, suggest the party making the changes proposes the changes to the other party. | G
N3.3.2 | Process | The process for updating and signing of a new revised SA now needs to be supported by a Restatement document and Sealing of the Deeds process. |  | Clause refers to the executing of the SA following agreed revisions. | Do we need to amended this clause to add in that once an SA is signed by both parties, this then supercedes the previous version. It is hoped that this will avoid the need to revise the deed for the site and thus reduce the time taken to formally agree a new SA between the parties. | A |  | AP | Process for execution to be discussed and agreed. Appropriate changes can be made if required. |  |  |  |  | AP | Are they suggesting that SAs are amended or are they terminiated and a new one issued on the same date? And if so what about the clauses in the original agreement that need to survive. | A
Section N
New | SA Template | General point. Should the SA's have version control so that you could see what changes were implemented when and arising from what work. | No version control for SA's | Should the SA's include a version control to highlight the history of changes? | G | Covered by revised SA Template | AP | Currently under review but intial feedback suggests that it is not normal practice to include version control within contracts |  |  |  |  | AG | Agree | G
New | Tri-Partate SA | There have been occasions for tri-party sites where one SA has been updated between the Site Owner and site user, but the changes have not been mirrored across to the other SA in place between the site user and site user. This is critical as issues such as there are data items that are common between the two SA's in place, such as access, security, cathodic protection, utilities supply and drawings i.e. GA and HAZ resulting in mis-match of data between the two SA's. | Section N does not contain any clauses outlining that National Grid are the custodians of the Supplemental Agreements. | If National Grid are the custodians of the SA's, then additional requirements are needed i.e. to maintain the integrity of information between SA documents for where there is more than one offtake at a location including tri-party sites. If one document is updated, they should have a duty to inform the other operator highlighting the changes that need to be made. | G | A way forward has been proposed and accepted in Principle. Definitions still to be revised and agreed. | AP | Amendment process in OAD mentiones upstream and downstream processes. Process improvements are now in place to ensure tri party sites are kept consistent. |  |  |  |  | AP | This suggests the site owner should be responsible for ensuring consistency between SAs agreements. | A
Appendix | SA Template | Current Supplementals do not document all the connection facilities on site as per Section B of OAD. Specifically, whilst the mechanical drawing is in include the SA, there is no mention of the electrical assets on site which often can be shared and therefore lead to confusion on who owns them and thus maintains them. The SA should cover asset ownership plus the other relevant information needed for commercial purposes in managing the conveyance of gas from one operator to another. | Appendix SA to be revised to the new OAD Pack. |  | G | Covered by revised SA Template | AG | Supplemental Agreements under review. Correct level of information required to be determined to prevent continuous cycle of updating agreements |  |  |  |  | AG | Need a proposal of what could be included - not 30 E & I diagrams | G

## Pending Workstreams
Pending OAD Review Amendments | [7 empty] | NGG |  | NGN |  | SGN |  | WWU
v6 (11.04.19)
Clause | Category | Root Cause |  | Specific Issue | Proposed Change (CGL) | Current Status | Action Required | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Revised Status
B3.7 | CNI | Section needs to be over-hauled and detailed the revised access rights due to the developments of the CNI requirements. This needs to include a section on when access/security has been breached by a Site User and the sanctions that a Site owner can impose in such cases. | CNI Forum | See Root Cause |  | A | Pending the creation of an Industry CNI group, who will look into matters and determine a way forward | NE | Subject to outputs of CNI group | AP | the statemenht is still apropriate as the site owner is the land owner. |  |  | AP | Need to come up with some principles | A
B3.8 | CNI | Section needs to be over-hauled and detailed the revised rights due to the developments of the CNI requirements. This needs to include the process of how access is given and the role of the ARC. | CNI Forum | See Root Cause |  | A | Pending the creation of an Industry CNI group, who will look into matters and determine a way forward | NE | Subject to outputs of CNI group |  | subject to review. |  |  | AP | This will be agreed at the CNI working group . | A
B6 | CNI | Similar to B3.6 and B3.7. Section needs to be over-hauled and detailed the revised access rights due to the developments of the CNI requirements. This needs to include a section on when access/security has been breached by a Site User and the sanctions that a Site owner can impose in such cases. | CNI Forum | See Root Cause |  | A | Pending the creation of an Industry CNI group, who will look into matters and determine a way forward | NE | Subject to outputs of CNI group | AP | sanctions for a site user who has access breaching security please clarify? |  |  | AP | See above | A
Annex G1 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Maintenance | Minimum details to be revised as it is difficult for Cadent to provide, due to the way that it plans its maintenance activities | Revised details to: > Offtake Site > Period to be completed in > Type of Maintenance (in line with revised sub categories) > Details (if impact is significant) | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Need more dialogue | A
B2.2.5 | Maintenance | We need to divorce the Maintenance activity from the Non-routine activity. Routine maintenance should be shared under Section G and non-routine requirements covered by Section B. If successful as an approach, this clause will need to be removed. | Maintenance Workshop | In Section G, operators need to share maintenance plans. This is a consolidated list of routine and non-routine activity. Whilst non-routine activity should be known in advance, it is difficult to say when this will happen in the year, and some activity is re-active which you cannot capture via the annual process. | Revise the Maintenance requirements under Section G so that they are fit for purpose and consistent across all operators. | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NA | Maintenance workshop to confirm however this clause is for major modifications and not routine maintenance. Our prefernce would be one plan covering Maintenance and Non-routine. Also proposing the potential use of the maintenance plan serving as the OAD notice. | NA | disagree |  |  | NA | The issue is between planned and unplanned activitiy not routine/non routine activity or maintenance or investment work | R
B2.3.2 (c) | Maintenance | As above | Maintenance Workshop | In line with the revisions for B2.2.5 the clause needs to be updated to state it should be covered by Section B as Non-routine rather than Maintenance under Section G. | Revise clause depending upon outcome for clause B2.2.5 | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Maintenance workshop to confirm however this clause is for major modifications and not routine maintenance. Our prefernce would be one plan covering Maintenance and Non-routine. Also proposing the potential use of the maintenance plan serving as the OAD notice. | NA | disagree |  |  | NA | As above | R
G1.2.1 | Code Update | See above | Sub categories to be revised. | Revise to: Routine or non-routine maintenance that has an: > Impact to gas flow by either party > Impact on electrical arrangements by either party > Impact to shared telemetry arrangements by either party > Impact to key measurement equipment i.e. P1 pressure transmitters or DNO Metering systems > Impact to Cathodic Protection systems > Impact to any of the above where testing information needs to be passed to the Site Owner in order to maintain site compliance |  | A |  | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Agree with revised bullet list, but need clarity on what is meant by routine or non-routine, isn't it all "relevant maintenance" as currently described? | A
G2.2.3 | Code Update | See G1.2.1 | Revise in line with new sub-categories |  |  | A |  | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AG | Agree
G2.2.4 | Code Update | See G1.2.1 | Revise in line with new sub-categories |  |  | A |  | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AG | Agree
G2.2.6 (b) | Code Update | See G1.2.1 | Revise in line with new sub-categories |  |  | A |  | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AG | Agree
G2.2.5 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Maintenance Workshop | Remove as not needed |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Agree remove because it is a reference to the previous bullet list change in section G1.2.1 | A
G2.4 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Maintenance Workshop | Given maintenance is reviewed 6-monthly is there a need to have a process to amend individual requirements as this seems over kill | Remove section as this is covered by the annual process | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G2.5 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Maintenance Workshop | For any Flow Maintenance Days to be agreed this needs to be undertaken in consultation with the DNO taking into account security of supply and balancing of the network demand. |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G2.6 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Maintenance Workshop | Is this section needed as it just increases cost for the DNO's |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G3.2.3 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Maintenance Workshop | Should NRO's be shared for maintenance that has an impact upon another user? |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G3.3 | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Maintenance Workshop | Again is this section necessary? If maintenance is postponed, it surely rolls over to the next planning cycle? | Remove section as this is covered by the annual process. | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
G3.4 | Definition Update | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | Redefine urgent maintenance | Redefine to: Any maintenance that has an impact upon another operator that requires urgent addressing that cannot be confirmed ahead of time as part of the maintenance programme timescales or is reactive action where a modification has taken place that should have been notified under Section B. |  | A | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  | NA | ? | AG | Agree | R
G3.6.1 | Maintenance | There have been occasions where the processes of OAD have been followed that have resulted in a material impact upon Cadent assets or operations by another operator. Whilst these have been followed up via appropriate channels, we have had one specific issues that has not been resolved adequately that needs to be escalated however, OAD does not really provide what that escalation route ought to be. | Maintenance Workshop | This section very much focuses on the flows at offtakes only and not the wider security of supply issues. What happens if parties cannot agree what scenarios would take precedent? |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AP | Needs more dialogue | A
New | Maintenance | Maintenance requirements under OAD seems onerous and need to be simplified and fit for purpose. | Maintenance Workshop | Need to ensure the maintenance section focuses on maintenance and does not include investment related activities as these are covered by Section B |  | G | Workshop to be arranged so that Maintenance requirements can be reviewed. | NE | Upcoming maintenance workshop to resolve |  |  |  |  | AG | Agree | G

## Outstanding
Pending OAD Review Amendments | [5 empty] | NGG |  | NGN |  | SGN |  | WWU
v6 (11.04.19)
Clause | Category | Root Cause | Specific Issue | Progress | Status | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Current Status | Network Operator Comments | Current Status | Network Operator Comments | NGG | NGN | SGN | WWU | Sum | Mode
B1.5.2 (b) | Code/Clause Change | Two issues: Section B1.5.2(b) states the sections that need to be updated but E Site Services is not one of them; and This arrangement needs to be reconsidered as there are times where the Supplemental Agreement needs to be updated but the change does not necessarily require an OAD notice to be raised. | Rather stating what sections need to be updated should this be refined to updating the Supplemental Agreement as necessary. | To be reviewed | A | AP | In relation to Supplemental Agreement, as a matter of process, the whole document should be reviewed for accuracy as part of the amendment process. | AP | Needs clarification. |  |  | AP | Agree to amend 1.5.2 to require updates to be made when other works are carried out. 2. We should issue a notice when someone is onsite when carrying out the work. | 1 | 1 | 0 | 1 | 3 | 1 | ok
B1.6.1 (b) | Code/Clause Change | Site owner does not own all buildings (i.e. buildings, kiosks, enclosures) at an offtake site. Some may even be owned by a 3rd Party i.e. telecommunication masks. | Not all the building at an Offtake are owned by the site owner. Where a site user owns buidling, such as a regulated buidling or stores, they too should maintain these buidling in compliance with any legislatory, regulatory or relevant enforceable standards. We need to distinguish between the site owner and site users responsibilities as it is not as black and white as OAD seems to imply. | To be reviewed | R | NE | Appreciate that there may be an issue but unclear that this is the correct solution. | NA | Disagree | NA | Don't agree - The OAD specifies that Connection Facilities can include Land and Buildings and that each party is responsible for its Connection facility. B 1.6.1 (b) (i) and (iii) place responsibility on the site owner for land and buildings except where they fall under the definition of a Connection facility OAD B1.3.1 (a) and (b) | AP | If a third party given permission to put mask onsite then the land owner needs to ensure that they maintain their equipment. And also ensure site security is maintained. | 0 | -1 | -1 | 1 | -1 | -1 | ok
B2.2.4 | Code/Clause Change | It is difficult to comply with 'The Modifying party shall give each affected party prior written notice, not less than twelve Months or shorter period if parties agree', as this does not take account of how networks process change and the information needed for the OAD notice may not be available as the work may still be in the feasibility stage and the full impact to the others operators is not known or cannot be determined at that point. | This clause needs to be revised as it is difficult for all operators to comply with 12 months notice. This clauses needs to be consistent across all operators to provide a level playing field for all especially when DNO's interact with each other concerning Inter-LDZ sites. An alternative way forward is required one that is pragmatic and avoids any admin burden in maintaining notice details. | To be considered. Suppliers to consider what alternative arrangements would work. | R | NE | Believe that the current version is workable to allow operation in all scenarios. Effectively, in an ideal world operators provide as much notice as possible but if they can't through collaboration we would look to facilitate later requests. | AG | Agreed | AP | SGN would expect 12 months notice for major works that impacts flows and 6 to 3 months notice for minor works | AP | Normally not less than 12 months notice required. | 0 | 2 | 1 | 1 | 4 | 1 | ok
B2.2.4 | Code/Clause Change | OAD notices detail the offtake, the work, the reason why and when. What is missing is the impact to the operator such as a loss of telemetry, power arrangements or site access may be an issue. By detailing the impact this will assist the other operator in understanding what they may or not may need to consider when reviewing the notice. | The impact arising from the notified work is not a requirement. This should be stated i.e. "loss of electrical power for 1 day" or "2 hours Telemetry outage required'. | Provisionally Agreement. Additional clause to cover "Impact to other operator." to be included. | A | NA | At the time of raising we would give as much info as possible. Again is this more of a process gap rather than a code change? | NA | disagree - outages etc maynot be known as notifications are put in as early as possible to avoid conflicts operational arangements should be agreed with site landlords | AP | Support an outlined scope of the works which could then be updated nearer to when the works commence | NA | Disagree but this should be for the NRO. | -1 | -1 | 1 | -1 | -2 | -1 | ok
B3.4.3 | Code/Clause Change | Recovery of costs where the affected party has to raise a design approval in order to support another operators amendments. The time and effort to support on-site supervisory activities such as access to RTU's or to undertake electrical isolations also needs to be recouped. | Clause focuses on the impacts to buildings only and needs to be expanded to include the impact to connection facilities as well. | Fuirther dialogue required | A | NE | Would like to understand how this fits in with section 4 (Compatibility). | AG | agreed |  | Same principle as B2.2 | AP | Agree definition needs to be changed. Actual wording to be provided by Legal text provider when Modification raised. | 0 | 2 | 0 | 1 | 3 | 0 | check
B3.4.4 | Code/Clause Change | This clause should be expanded for the site user to consider options that will enable greater clarity on asset separation. | Shared Assets are a concern for all operators especially when maintenance is needed or modifications required as this causes issues. All operators agree in principle that there should be a moved towards separation where possible. | Separtion of shared further | R | NA | Unclear as to the true value and practicality of adding this clause. As assets are coming to the end of life likely to see more shared assets being separated. | AP | What is the benefit to this proposal? |  |  | AG | Seems reasonable | -1 | 1 | 0 | 2 | 2 | #N/A | ok
B4.1.5 | Code/Clause Change | There have been occasions where the processes of OAD have been followed that have resulted in a material impact upon Cadent assets or operations by another operator. Whilst these have been followed up via appropriate channels, we have had one specific issues that has not been resolved adequately that needs to be escalated however, OAD does not really provide what that escalation route ought to be. | Clause needs to be enhanced to reflect what course of action can be taken in the event that the Parties cannot agree on a resolution, or one party is seen not to be addressing the issue. What routes of escalation should be taken i.e. offtake committee etc..... | To be reviewed | R | AP | Please can we discuss the specfic instances off-line to identify the most appropriate fix. Dispute resolution already within UNC. |  |  | AP | Established processes should be followed, it would be useful to point people to the correct part of code | NA | General Terms A - Dispute procedures will apply. But should be resolved between both parties in the first instance. | 1 | 0 | 1 | -1 | 1 | 1 | ok
B6 | Code/Clause Change | Access needs to cover when CDM applies as this restricts access during certain specific types of activity. | Due to differening SCO arrangements that are used between operators, when a CDM area is put in place it often means that the other operator cannot enter that space unless he has the specific permitry. However, this causes an issue with the access rights as they stand currently in OAD especially if the CDM areas include the opther operators assest and these to be maintain whilst the CDM area is in place, and also the Site Owner should retain to access any area on site espacially in the case of any emergency. CDM needs to be covered by OAD and check is needed to ensure the relevant sections in OAD (A, B and C) are aligned. | To be reviewed | A | NE | To be discussed internally with NGT |  |  | AP | This requirement under the OAD must be captured under CDM projects. | AG | Agree | 0 | 0 | 1 | 2 | 3 | 0 | ok
B6.3.1 | Code/Clause Change | Alignment required with Section C of OAD | Section B6 of OAD requires a review to establish if the arrangements reflect shared sites. Normally there are only two parties, the site owner and the site user. The site owner grants access to the site user and therefore in this clause the "access party" is the site user and the "site party" is the site owner. Are there any instances where the site owner does not own all the land within an offtake? The clause B6.3.1 should be expanded to ensure that the Site Party does not make it over onerous for site access to occur similar to the clause C5.1.2(a). This is for consistency between Sections B and C. | To be reviewed | R | NA | Are Cadent thinking about specfic examples? Can this be resolved offline? |  |  | AG | Agree | AG | Agree. Should be Site Owner not site Party. | -1 | 0 | 2 | 2 | 3 | 2 | ok
C5.1.2(b) | Code/Clause Change | For offtakes that are in the boundary of a National Grid terminal site, COMAH regulations have a significant issue upon site access and site safety. These regulations cause additional requirements that need to be complied with above and beyond those requirements for normal offtakes. This should be recognised within the code to make it explicit and clear. | Clause needs to be expanded to cover Top Tier COMAH regulations which will cover offtakes within Terminal Sites. | Under consideration | G | NE | Will need to understand fully the outputs of the NGT investigation into Comah to understand if this is an appropriate change. |  |  | AG | We agree with this proposal | AG | Agree issue needs to be addressed. | 0 | 0 | 2 | 2 | 4 | 0 | ok
L2.3.1 | Code/Clause Change | Cost recovery is becoming more an issue for operators as they seek to recover costs to support another operators activities on site. The cost recovery process should be agreed upfront rather than just submitting an invoice and cost recovery arising from "interference" also needs to be articulated. | The current clause seems to indicate that consideration to any cost recovery is to be undertaken after the event. However, if any cost recovery is needed this should be addressed, agreed and confirmed as part of the OAD notification process as the operator undertaking the repair, replace or relocation may not have budgeted for such costs. It is suggest that the process in L2.3 is revised so that it is linked to the modification process or before an event occurs but retains the possibility of cost recovery after an event as well. The norm should be before and not after. | To be reviewed | A | AP | Need to agree a consistant and appropriate philosophy on cost recovery before proposing a code change. |  |  | AG | Costs of any work need to captured up front in advance of works commencing | AP | Agree - consider a subsidiary documents that list the applicable chargers | 1 | 0 | 2 | 1 | 4 | 1 | ok
N2.1.2(c ) | Code/Clause Change | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | Does this section need to be reviewed to take into account Tri-partite and other shared sites or is this still fit for purpose? | To be reviewed | A | NE | Definition analysis. |  |  | AG | Agree as long as it is consistent with Sections A & B | AP | Definition is clear, however if it is inconsistent with sections A & B then it needs rectifying. | 0 | 0 | 2 | 1 | 3 | 0 | ok
N9.1.1 | Code/Clause Change | This clause needs to be linked back to 'material' impact in Section B for modifications. We have experienced outages in the past to telemetry systems at offtakes which has resulted in a loss of control of the site, albeit for a short period of time, without an OAD notice being raised to cover the activity. When challenged this N9.1.1 was used as justification whereas it was felt that the planned change and outage should have been notified via an OAD notice under Section B. | The section covers "The “Transmission System Operator to Distribution System Operator Agreement Guidelines”... re the co ordination and management of changes, faults and outages on the information systems and communications network infrastructure. | Under consideration | G | AP | Agree that some sort of communication is required. Need to come to consensus as to what that is |  |  | AG | Agree | AG | Agree | 1 | 0 | 2 | 2 | 5 | 2 | ok
A2.1.4 | Definition Amendment | See A2.1.2 | Offtake Definition 'An NTS/LDZ Offtake is an Offtake at which gas can flow from the NTS into an LDZ' is too vague. | To be reviewed | A | NE | Business Rules for shared sites are in submitted Cadent paper. Impact of changing definition of an offtake under review as part of action 0807 of Workgroup 646R | AG | Agreed | AG | We agree with the principle however we need the wording to be revised to give us clarity on the proposal | AP | Agree definition needs to be changed. Actual wording to be provided by Legal text provider when Modification raised. Suggest using offtake point instead of physical point | 0 | 2 | 2 | 1 | 5 | 2 | ok
A2.2.1. | Definition Amendment | Cadent has three types of LDZ/LDZ offtakes. These are: > 7bar PRS's that are like NTS/LDZ offtakes with multiple feeds > Governor Installations (1 feed only) > Closed Valves in Public Highways (1 feed only) | LDZ Definition needs to mirror revised offtake definition | To be reviewed | A | NE | Requires confirmation by impacted DN's | AG | Agreed | AG | We agree with the definition | AP | Agree specific issue. Actual wording to be provided by Legal text….. | 0 | 2 | 2 | 1 | 5 | 2 | ok
A4.2.1 | Definition Amendment | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | No definition for the term 'Point of Offtake'. | To be reviewed | A | Ne | Agree that a definition for point of offtake would be useful but would suggest that is potentially already clause 4.2.2. Are there deficiencies with this? | AP | suggest wording is chaned to Offtake point or individual Offtake point to avoid need for definition. However the statement is clarified in 4.2 | AG | Proposed change seems acceptable | AP | Agree there should be a definition for "Point of offtake" but proposed words are not precise enough. Should be marked on plans and physcially on site. | 0 | 1 | 2 | 1 | 4 | 1 | ok
B1.2.2 | Definition Amendment | See A2.1.1 and clarity around definitions | Clause states that "At certain offtake sites, one or more Individual Offtakes Points, located at each site, at each of which gas can flow into the same LDZ." Do we need to refer to these as Trip-partite sites going forward? | To be reviewed | R | NE | Can we confirm the value of changing? What instances of issues has this caused? Agree all definitions should align. What is the impact of changing this definition | AG | wording needs to be revised to fit the document (offtake needs defining as individual offtake point) if Agreed but wording could be revised to allow more flexibility simply saying "...gas can flow into an LDZ" would suffice. | AG | Proposed change seems acceptable | AG | Agree definitions between sections must align | 0 | 2 | 2 | 2 | 6 | 2 | ok
B1.3.1 | Definition Amendment | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | No definition for the terms 'all the plant, equipment and buildings'. These are needed to ensure that there is a consistent understanding between operators as to what assets fall under these terms, which then will assist when OAD notices are required. For buildings, this needs to cover structures too as this is referred to in B3.4.2 and B3.4.3. | To be reviewed | R | NA | Can we request greater clarity and some examples of the type of issue that this is trying to fix? Current arrangements allow for dialogue between the operators. | AP | I'm not aware of issues so I'm unclear on why this is required | AG | Proposed change seems acceptable | AP | What about fencing as it is not a building? What about roads, cameras, lighting, security equipment etc | -1 | 1 | 2 | 1 | 3 | 1 | ok
B1.3.1(a) | Definition Amendment | In order to manage OAD effectively, the framework is used to understand the requirements so that they can be complied with. In Cadent's experience issues have arisen from the lack of clear, concise clarity surrounding the terms in OAD and specifically the definitions. Definitions need to be enhanced so that they are clearly understood by all operators. | The Connections Facilities for the upstream party sometimes include connections for a power station or large industrial user. Do we need to cover this off in OAD or are operators happy that this covered by the general term that the Connection Facilities are "all the plant, euqipment and buildings.... install by such Party at an Offtake site.". | To be reviewed | R | NA | The OAD is a transporter to transporter document, impact of changing the defintion needs to be understood. | AP | I'm not aware of issues so I'm unclear on why this is required | AG | Proposed change seems acceptable | AP | Agree definition not clear, note it applies to both parties. Should be telemetry and not NTS telemetry but don't think revised definition works because upstream party definition is undefined and what does upstream party means when referring to the upstream party. | -1 | 1 | 2 | 1 | 3 | 1 | ok
N7 | Other |  | Loss and Liability Section. Does this need a review? | To be reviewed | A | NE | Would appreciate further clarify on the issue at hand here. |  |  |  | We unsure what the issue is further explanation needed |  | We will review your proposals. | 0 | 0 | 0 | 0 | 0 | 0 | check
Section M | Other |  | Does this section need to be reviewed in line with the SCO Interface Document? | To be reviewed | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | check
B1.5.3 | Process | It is difficult for all operators to comply with agreeing the SA before the changes go live on site due to the way work is executed, and the policy and procedures the industry works to for then collecting the required asset data and drawings. | It difficult to adhere to this specific clause due to a timing issue between what happens on site and then ascertaining the relevant information needed for the SA. This may increase the work needed by operators so a pragmatic way forward is required and one that takes into account the type of work as one size fits all may not be suitable. | To be reviewed | A | NE | With the current SA proposal excluding drawings (which have the longest lead time for completion) and in tandem with clause b1.5.4 which calls for an "effective date" is this issue now resolved? | AG | Agreed | AG | Agreed - We would suggest four working weeks to provide an update. | AP | Agree but what is the suitable notice period and when someone goes to site to carry out works etc during the notice period. | 0 | 2 | 2 | 1 | 5 | 2 | ok
N3.2.2 | Process | The process for updating an SA document is cumbersome and is based on National Grid making all changes to the documents. This way is open to mis-interpretation of the information especially if it is not National Grid that has undertaken the work and that it is National Grid's commercial team making the changes rather than the engineering staff. | The clause states that "The Parties to a Supplemental Agreement are required (by certain provision of this Document) to amend the Supplemental Agreement to reflect and record changes in relation to the Offtake; and undertake to make such amendments promptly and in accordance with this Document." and inconsistent with Clause B1.5.3 | The process for updating an SA is currently being developed being the operators. | R | NE | Does the phrase "In accordance with this document" not already link us back to B.1.5.3 |  |  | AG | Agree | AG | Agree | 0 | 0 | 2 | 2 | 4 | 0 | ok

## Validation
Code/Clause Change | Review UNC to enhance, revise or widen specific clauses
CNI | CNI sites
Definition Amendment | Review, revise, append existing UNC code to provide clarity concerning existing definitions
Drawings | Review and agreement on industry drawing process for updating Site Owner drawings
Maintenance | Review of Maintenance Sharing Arrangements
Other
Process | Review existing arrangements to revise or clarify supporting process for updating Supplemental Agreements
Redundant Assets | Issues concerning Site User Redundant Assets at offtakes
SA Template | Structure and content for revised Supplemental Agreement Appendices
Shared Sites | Sites not covered by OAD but where two operators have assets at a same site
Tri-Partate SA | Amendment to the SA's to cover offtake sites where three network operators are present
R | Red. No progress
A | Amber. Some Progress
G | Green. In Flight
B | Blue. Complete
AG | Agreed
AP | Agreed in Principle with cavaet or comments
NA | Not Agreed
NE | Neither agreed or disagreed