## Slide 1: XRN4732 - June 19 Release - Status Update
30th July 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS: 1st usage files monitored and assured by SME’s and IS Ops. Only 1 functional production defect identified during PIS. PIS Exit: Formal exit of PIS agreed on 26th July. Closedown: Closedown documentation in progress, awaiting final supplier invoices to finalise total Release costs and present the CCR at the September 19 ChMC. |  |  | 
Risks and Issues | No open risks or issues for the project |  |  | 
Cost | Project delivery costs expected to be on budget |  |  | 
Resources | Following PIS exit, no further SME resource requirements for the project |  |  | 

## Slide 2: XRN4732 - June 19 Release Timelines
Key Milestone Dates:
1st usage received and PIS completed
Project closedown in progress, awaiting final supplier invoices

## Slide 3: June 19 Release Summary
June 19 Release consists of 3 changes:
  XRN4670 - Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date
  XRN4687 - PSR updates for large domestic sites
  XRN4676 - Reconciliation issues with reads recorded between D-1 to D-5
Changes were successfully implemented on the 29th June with the changes going live at 09:00:00