## Slide 1: XRN4914 MOD 0651- Retrospective Data Update Provision
ChMC – 7th August 2019

## Slide 2: Proof of Concept: Progress update
30th July 2019 | Capture Progress update
Schedule | Procurement: 10th July: NDA contract issued to 3rd parties 12th July: Request for Quote (RFQ) reviewed by procurement and issued to 3rd parties 24th July: RFQ updated and re-issued with Stage 2 requirements; deadline extended by 2 days 25th July: Review of response templates and agreement on process 30th July: Agreement on selection criteria for assessing RFQ responses 31st July: RFQ responses due back by 10am Stage 2 requirements: 11th & 18th July: Capture of requirements 26th July: SME approval received 1st Aug: outstanding approval being sought
Risks and Issues | Issue: project is behind original draft plan Issue: data team / security team resources not allocated to project; options being discussed internally Risk: that cost required to deliver project is greater than project funding (2017 day rates used) Risk: availability of resources (environments/people) may impact plan for Retro
Cost | Project cost: to be re-confirmed Project funding: £1.5 mill; £700k for 2019 and £800k for 2020
Resources | Project mobilising Engaged with other programmes of work for consequential impacts / synergies (CSSC, AML/ASP,UIG) SI agreed for data cleanse / enduring solution of project Engagement approach to be agreed with Customers
XRN4914 MOD 0651 - Retrospective Data Update Provision - DSG Update 5th August
Key: highlighted text :update from last meeting

## Slide 3: Next Steps
XRN4914 MOD 0651 - Retrospective Data Update Provision DSG Update 5th August
Activity | Update | By | Done
Stage 2 requirements - detailed requirement workshops to draft business rules to help derive the meaning of the data mismatches | postponed to 1st August | 31st July | 
Continue engagement with 3rd parties for the RFQ and receive responses | extended to 31st July 10am | 26th July | 
Prepare assessment criteria Review and assess responses from RFQ; including review from Solution Architect | Completed Scheduled for 1st August | 9th Aug | 
Prepare Business Case for IRC (14th August) |  | 9th Aug | 
Identify an internal recommendation and take to DSG |  | 19th Aug | 
Agree Customer engagement approach and take to DSG |  | 19th Aug |