## Slide 1: 2019 / 2020 UK Link Delivery Timeline
Imp
PIS
Imp #1
PIS
Imp #2
PIS
Design
Build & UT
ST & SIT
UAT
RT
Test
IDR
PT
Build / Testing
SIT / Reg Test
MT
IMP
Retro
SUPT
UKL PT
UT
UKL RT
UAT
IDR
IMP
PIS
PIS
MiR 5
Documentation Release
June 2020
Jun | Jul | Aug | Sep | Oct | Nov | Dec
Jun-19
EUC
Nov-19
MiR 4
CSS
Retro
Mod678 – Uk Link Impacts
MiR 5
Feb - 20
Jun-20
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Testing
PIS
Design
MiR 6
MiR 6 – Potential Activity
2019 | 2020

## Slide 2: 2019 / 2020 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this includes potential activity within UK Link over the next 24 months
Sep-19 / EUC
BER Approval
09/01/19
Nov-19
BER Approval
10/04/18
EQR Approval
06/02/19
MiR 4
ChMC Scope Approval
10/04/19
RETRO
Potential Activity
Governance Approval dates tbc
On track
At risk
Key
Complete
Feb-20
BER Approval / Change Pack Issue
10/04/19
Jun - 20
Change Pack Issue
Dec-19
BER Approval
Oct-19
Scope Approval
10/07/19
MiR 5
ChMC Scope Approval
10/07/19
EQR Approval
Aug-19
Scope Approval
10/07/19
MiR 6
Scope Approval
Oct-19

## Slide 3: Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
June 19 | 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | In PIS | June 2019 | Low | Xoserve
 | 4687 | PSR updates for large domestic sites | In PIS | June 2019 | Low | Shippers
 | 4676 | Reconciliation issues with reads recorded between D-1 to D-5. | In PIS | June 2019 | Medium | Xoserve
MiR 4 | 4777 | Acceptance of Contact Details Updates | In PIS | MiR 4 | Medium | Shipper
 | 4803 | Removal of validation for AQ Correction Reason 4 | In PIS | MiR 4 | Low | Shipper
 | 4780 (A) | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | In PIS | MiR 4 | Medium | Shipper
MiR 5 | 4871 (A) | Modification 0665 - Changes to Ratchet Regime | In Delivery | MiR 5 | Low / Medium | Shippers / DNs
Sept 19 | 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | In Delivery | September 2019 | High | NTS
 | 4665 | Creation of new End User Categories (EUC) | In Delivery | June/Sep-2019 | High | Shippers
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | In Delivery | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | In Delivery | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | In Delivery | November 2019 | High | Shipper
 | 4866 | UIG Recommendation – removal of validation on uncorrected read | In Delivery | November 2019 | Low | Shipper
Feb-20 | 4955 | Amendments of MDD PSR needs code descriptions | In Project Start-Up | February - 2020 | Low | Shippers / GT/IGTs
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Project Start-Up | June-2020 | Low | Shippers
 | 4691 | CSEPs: IGT and GT File Formats (CGI Files) | In Project Start-Up | June-2020 | Medium | DNs / IGTs
 | 4692 | CSEPs: IGT and GT File Formats (CIN Files) | In Project Start-Up | June-2020 | Medium | DNs / IGTs
 | 4772 | Composite Weather Variable (CWV) Improvements | In Project Start-Up | June-2020 | Medium | tbc
 | 4780 – B | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | In Project Start-Up | June-2020 | Medium | Shippers
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Project Start-Up | June-2020 | Low | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Project Start-Up | June-2020 | Medium | Tbc
CSS | 4627 | Consequential Central Switching Services | In Delivery | 2021 | High | Shippers

## Slide 4: Change Index – UK Link Unallocated External Impacting Changes
XRN | Change Title | Current Status | Indicative R&N Release | Complexity
4851 | Moving Market Participant Ownership from SPAA to UNC/DSC | CP in Capture | Feb 2020 | TBC
4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CP in Capture | Major Release | TBC
4801 | Additional information to be made viewable on DES | HLSO in progress | Major Release | TBC
4850 | Notification of Customer Contact Details to Transporters | HLSO In review | Major Release | Medium
4871 – B | Modification 0665 – Changes to Ratchet Regime | HLSO in progress | Major Release | TBC
4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | HLSO in progress | Major Release | TBC
4931 | Submission of Space in Mandatory Data on Multiple SPA Files | CP in Capture | Major Release | TBC
4941 | Auto updates to meter read frequency (MOD0692) | Awaiting Solution Approval | Major Release | Medium
4978 | Notification of Rolling AQ value (following transfer of ownership between M5 and M) | In Capture | Major Release | TBC
Mod647 | Opening Class 1 Reads to Competition | Awaiting Solution Approval | Major Release | High - Med
4914 | Mod 651 - Retrospective Data Update Provisions | CP in Capture | Major Release 2020 | TBC
4896 | Failure to Supply Gas System and Template Amendment | HLSO in review | Minor Release | Low
4923 | AQ Calculation for RGMA (ONUPD) Estimate Reads | Awaiting Solution Approval | Minor Release | Low
4716 | Increased Field Length – ‘Updated by’ data item | Solution approved | Minor Release | Medium
4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | In Capture | Unallocated | TBC
Mod700 | Class 3 – Emergency MOD | In Capture | Unallocated | TBC
Feb 2020
Major Release
Retro 2020
Minor Release
Unallocated
KEY