## Slide 1: KPI and KVI Review Approach & Plan
16th October 2019

## Slide 2: KPI & KVI Review Background
As a result of discussions at CoMC, the following slides provide the approach & plan to review & update KPIs and KVIs
  Xoserve to review what the Key Performance Indicators for success are (action 0704)
  Xoserve to review current KPI and KVI monitoring for improvements (action 0701)
  Present proposals & plan to CoMC (action 0701)

## Slide 3: Background
Discussed at a number of CoMC meetings that Xoserve may not be measuring the areas that concern customers or the measures may no longer be appropriate
Agreed during KVI development that the KVIs would be reviewed annually and changed if required
Currently rely on customer surveys to measure 4 of the 7 KVIs. Intention is for Xoserve to proactively monitor and not rely on customers to measure our performance

## Slide 4: DSC Service Line & KPI Review Plan
Activity | Owner | Start Date | End Date | Status
Review all DSC service lines against UNC & other relevant non UNC docs. | Xoserve | 01/10/2019 | 29/11/2019 | On target
Review all KPIs and any DSC services line that should be considered as a KPI | Xoserve | 15/10/2019 | 13/12/2019 | On target
Present approach & plan to CoMC | Xoserve | 16/10/2019 | 16/10/2019 | On target
Review performance measures for all service lines and supporting MI requirements | Xoserve | 21/10/2109 | 10/01/2020 | On target
Update Service Description Table (track changes) | Xoserve | 04/11/2019 | 10/01/2020 | On target
Develop performance measures & reporting | Xoserve | 04/11/2019 | 15/02/2020 | On target
Provide progress update to November CoMC | Xoserve | 20/11/2019 | 20/11/2019 | On target
Provide progress update to December CoMC | Xoserve | 18/12/2019 | 18/12/2019 | On target
First review of the draft DSC service lines & KPIs at January CoMC | CoMC | 15/01/2020 | 15/01/2020 | On target
Provide any comments to Xoserve of the draft service lines & KPIs | CMs | 15/01/2020 | 07/02/2020 | On target
Second review of the updated DSC service lines & KPIs at February CoMC | CoMC | 19/02/2020 | 19/02/2020 | On target
Final review & approval of DSC Service Line and KPIs to March CoMC | CoMC | 18/03/2020 | 18/03/2020 | On target
New service lines and KPIs effective & published | Xoserve | 01/04/2020 | 01/04/2020 | On target

## Slide 5: KPI Review Plan
Activity | 30-Sep | 07-Oct | 14-Oct | 21-Oct | 28-Oct | 04-Nov | 11-Nov | 18-Nov | 25-Nov | 02-Dec | 09-Dec | 16-Dec | 23-Dec | 30-Dec | 06-Jan | 13-Jan | 20-Jan | 27-Jan | 03-Feb | 10-Feb | 17-Feb | 24-Feb | 02-Mar | 09-Mar | 16-Mar | 23-Mar | 30-Mar
Review all DSC service lines against UNC & other relevant non UNC docs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Review all KPIs and any DSC services line that should be considered as a KPI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Present approach & plan to CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Review performance measures for all service lines and supporting MI requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Update Service Description Table (track changes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop performance measures & reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Provide progress update to November CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Provide progress update to December CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First review of the draft DSC service lines & KPIs at January CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Provide any comments to Xoserve of the draft service lines & KPIs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Second review of the updated DSC service lines & KPIs at February CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final review & approval of DSC Service Line and KPIs to March CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
New service lines and KPIs effective & published |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 6: KVI Review Plan
Activity | Owner | Start Date | End Date | Status
Present approach & plan to CoMC | Xoserve | 16/10/2019 | 16/10/2019 | On target
Review KVIs and measures | Xoserve | 17/10/2109 | 10/01/2020 | On target
Carry out sessions to discuss KVIs with customers (via constituent groups) | Xoserve | 17/10/2019 | 28/02/2020 | On target
Develop strawman KVIs and measures | Xoserve | 04/11/2019 | 06/12/2019 | On target
Provide progress update & share view of proposed KVIs November CoMC | Xoserve | 20/11/2019 | 20/11/2019 | On target
Review strawman KVIs at December CoMC | CoMC | 18/12/2019 | 18/12/2019 | On target
Provide feedback on strawman KVIs | CMs | 19/12/2019 | 03/01/2020 | On target
First formal review of the draft KVIs and measures at January CoMC | CoMC | 15/01/2020 | 15/01/2020 | On target
Provide any comments to Xoserve of the draft service lines & KPIs | CMs | 16/01/2020 | 07/02/2020 | On target
Second review of the KVIs and measures at February CoMC | CoMC | 19/02/2020 | 19/02/2020 | On target
Provide any comments to Xoserve of the draft service lines & KPIs | CMs | 20/02/2020 | 06/03/2020 | On target
Final review & approval of KVIs at March CoMC | CoMC | 18/03/2020 | 18/03/2020 | On target
New KVIs effective & published | Xoserve | 01/04/2020 | 01/04/2020 | On target

## Slide 7: KVI Review Plan
Activity | 14-Oct | 21-Oct | 28-Oct | 04-Nov | 11-Nov | 18-Nov | 25-Nov | 02-Dec | 09-Dec | 16-Dec | 23-Dec | 30-Dec | 06-Jan | 13-Jan | 20-Jan | 27-Jan | 03-Feb | 10-Feb | 17-Feb | 24-Feb | 02-Mar | 09-Mar | 16-Mar | 23-Mar | 30-Mar
Present approach & plan to CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Review KVIs and measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Carry out sessions to discuss KVIs with customers (via constituent groups) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop strawman KVIs and measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Provide progress update & share view of proposed KVIs November CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Review strawman KVIs at December CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Provide feedback on strawman KVIs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First formal review of the draft KVIs and measures at January CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Provide any comments to Xoserve of the draft service lines & KPIs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Second review of the KVIs and measures at February CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Provide any comments to Xoserve of the draft service lines & KPIs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final review & approval of KVIs at March CoMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
New KVIs effective & published |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |