## Slide 1: 8.1 XRN4665 – EUC Release
13/11/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Post Implementation Support (PIS) PIS activities (including First Usage monitoring) continue to be successfully monitored as per plan Handover activities commenced with Xoserve Tech Ops for completion of PIS by 29/11 Preparation of Closedown activities commenced |  |  | 
Risks and Issues | No key Risks or Issues open that impact the continuation of Post Implementation Support activities for the EUC release |  |  | 
Cost | Project delivery costs are tracking to approved internal budgets (Revised BER to include Financial Risk margin approved at ChMC on 10/07/19) |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: 8.1 XRN 4665 - EUC Release Timelines
Key Milestone Dates:
PIS & First Usage monitoring activities ongoing and tracking to plan for completion by 29/11/19
Preparation of Closedown activities commenced
NRL Issued
T67 Issued

## Slide 3: 8.2 XRN4828 - Nov 19 Release - Status Update
13/11/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | All testing activities successfully completed Implementation preparation in progress Deployment of in scope changes on track for 09/11/19 Request submitted to Supplier to extend PIS by 2 weeks to align with First Usage of in scope changes |  |  | 
Risks and Issues | There are currently no major Risks or Issues impacting the delivery of the November 19 release. |  |  | 
Cost | The BER with full delivery costs were approved at ChMC in April 2019, BER for XRN4866 UIG Recommendation approved by ChMC on 12th June |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 4: 8.2 XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
System & UAT Completion – 27/09/19
Regression Test Completion - 25/10/19
Performance Test Completion – 25/10/19
Pre-Implementation Preparation – 08/11/19
Implementation – 09/11/19
PIS Completion – [20/12/19] – Awaiting Supplier confirmation
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
XRN4828
Nov-19
HLD & Change Pack Production
Design
Build & FUT
ST & SIT
UAT
RT & PT / Implementation Prep
PIS
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Approval
GO LIVE 09/11/19 - TBC

## Slide 5: 8.3 XRN4996 - June 20 Release - Status Update
4th November 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: MT costs and timelines have been included in the BER which has been shared for approval at ChMC. Design: Design workshops are nearing completion, however some challenges have been experienced due to limited SME availability and outstanding design assumptions, in particular for xrn4941. Change Packs: Aiming to deliver the change packs to ChMC in November for approval in December. |  |  | 
Risks and Issues | Risk – There is a risk that there is insufficient time to complete the design workshops due to limited SME resource which will impact our ability to issue Change Packs by 15th November There is a risk that for xrn4941 a number of assumptions will be required in design which may not be validated until after build because MOD0692 has not been approved leading to rework and delays |  |  | 
Cost | BER for full delivery shared and to be presented to ChMC in November 19, this will include Market Trial options. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 

## Slide 6: 8.3 XRN4996 - June 20 Market Trials Options
9 weeks | £210,750 | XRN4691, XRN4692, XRN4772, XRN4850, XRN4871(B), XRN4888, XRN4941, XRN4932 | CGI,CIN, AWV, FWV, AIA,PRN, RAT MRI, Capacity Invoice (Ratchet) | 45-50 | 10 (4 DN, 2 IGT, 4 Shippers)
Duration | High Level Cost | 8 Changes | Files considered | No. Of Test cases | Participants
Full Scale
Low Scale
6 weeks | £178,500 | XRN4691, XRN4692, XRN4772, XRN4850, XRN4941, XRN4932 | CGI,CIN, AWV, FWV, AIA,PRN, RAT MRI, Capacity Invoice (Ratchet) | 35-40 | 8 (4 DN, 2 IGT, 2 Shippers)
Duration | High Level Cost | 6 Changes | Files considered | No. Of Test cases | Participants
5 weeks | £128,650 | XRN4691, XRN4692, XRN4850, XRN4932 | CGI,CIN, MRI, Capacity Invoice (Ratchet) | 15-20 | 6 (2 DN, 2 IGT, 2 Shippers)
Duration | High Level Cost | 4 Changes | Files considered | No. Of Test cases | Participants
Medium Scale

## Slide 7: Slide 4
80%
Option 1
Full Scale
60%
Option 2 Medium Scale
40%
Option 3 Low Scale
8.3 XRN4996 - June 20 Market Trials Funding Arrangements
XRN Ref | Change Title | Shipper | DN | iGT | MT Recommended | Option 1 | Option 2 | Option 3
4691 | CSEPs: IGT and GT file formats (CGI files) |  | 90 | 10 | Yes | Yes | Yes | Yes
4692 | CSEPs: IGT and GT file formats (CIN files) |  | 90 | 10 | Yes | Yes | Yes | Yes
4772 | Composite weather variable (CWV) improvements | 50 | 50 |  | Yes | Yes | Yes | No
4850 | Notification of Customer Contact Details to Transporter |  | 90 | 10 | Yes | Yes | Yes | Yes
4865 | Amendment to Treatment & reporting of CYCL reads | 100 |  |  | No | No | No | No
4871(B) | Changes to Ratchet regime (MOD0665) |  | 100 |  | Yes | Yes | No | No
4888 | Removing Duplicate adderss update validation for IGT Supply Meter Points via Contact Management System (CMS) |  |  | 100 | Yes | Yes | No | No
4930 | Requirement to inform Shipper of Meter Link Code Change | 100 |  |  | No | No | No | No
4941 | Auto udpates to meter read frequency (MOD0692) | 100 |  |  | Yes | Yes | Yes | No
4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0618s) | 100 |  |  | Yes | Yes | Yes | Yes
 | Option 1 - Full MT all changes - £210,750 | £94,837.50 | £88,515 | £27,397.50 |  |  |  | 
 | Option 2 - Medium Scale MT 7 changes - £178,500 | £64,260 | £107,100 | £7,140 |  |  |  | 
 | Option 3 – Low Scale MT 4 changes - £128,650 | £32,162.50 | £86,838.75 | £9,648.75 |  |  |  | 

## Slide 8: 8.3 XRN4996 - June 20 Release Timelines
Key Milestone Dates:
Capture completion – 19/09/19
Design Completion – 29/11/19
Build & Unit Test Completion – 31/01/20 (provisional)
System & UAT Completion – 24/04/20 (provisional)
Regression Test Completion – 29/05/20 (provisional)
Implementation – 20/06/20 (provisional)
PIS Completion – 25/09/20 (provisional)

## Slide 9: 8.3 June 20 Release Summary
June 20 Release consists of 10 changes, Implementation is planned for June 2020:
XRN4691 - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692 - CSEPs: IGT and GT File Formats (CIN Files)
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4850 - Notification of Customer Contact Details to Transporters
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4871 (B) - Changes to Ratchet Regime (MOD0665)
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4830 – Requirement to Inform Shipper of Meter Link Code Change
XRN4941* - Auto updates to meter read frequency (MOD0692)
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
* Pending Solution/MOD approval by ChMC/DSG for remaining CRs.

## Slide 10: 8.4 XRN4914 – Retro Proof of concept Status Update
5th November | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: Capture complete; proof of concept in Start-up/initiation Level 1 milestones and detailed plan being produced Customer Engagement and Communication plan: Kick-off meeting took place; 3rd Nov in DSG Engagement and communication agreed Web Page: content being agreed; to go live 12th Nov |  |  | 
Risks and Issues | Risk that there will not be sufficient volume received from Shippers in the proof of concept to be able to quantify the size of the data mis-match activity. Action: Checkpoint 1 to be put in place after engagement period to understand the amount of volume and data types that Shippers will be providing Risk that the amount of time to complete the proof of concept is not currently known. Action: Checkpoint 2 to be put in place after step 1 comparison of Shipper data against UKL data; to understand amount of direct mis-matches and no of data items to take to step 3; agreement needed for checkpoint 3 to gain an understanding of how long it may take |  |  | 
Cost | The BER was approved 25th October; £270k |  |  | 
Resources | Contract and Statement of Work signed with 3rd party; initiation activities progressing SME resource: working with SME team to ensure resource available when required |  |  | 

## Slide 11: XRN4914 – Retro proof of concept - timeline
2019/2020
November | December | January | February
Customer Engagement
Key:
Completed
Slipped / High risk
Medium risk
On-target
Support
Analysis
Customer / Advocates encouraging participation
Checkpoint 2
24th Jan
Checkpoint 1
29th Nov
Design
Test files can be accepted
Initial Customer engagement
kick-off 4th Nov
today
Planning
Develop
Testing
Kick-off prep
Actual data
files in
Step 1 Compare / Outcome / Aggregate
Initial Customer engagement of File receipt
ends 3rd Jan
Actual data files can be accepted
Support
Step 2 – deep dive / Outcome / Aggregate
Weekly project update via external communication methods
Test data
files in
Checkpoint 3
3rd Feb
Date for slicing data
4th Dec
Output from Step 1
Output from Step 2
Recommendations

## Slide 12: What we need from participating customers
Step 1 – Engage with the Retro PoC Project team now
Step 2 – Sign up to the PoC by Thursday 28th November
Step 3 – Work with the Retro PoC
Project team to ensure your
data is included in the PoC
comparison and analysis
phases

## Slide 13: 8.5 XRN4991 – MOD0700 Status Update
13th November | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | MOD0700 Implementation was completed on 28th September Outstanding Inner Tolerance changes were deployed on 19th October Post Implementation Support formally completed on 25th October Closure Report to be issued Change Management Committee in November |  |  | 
Risks and Issues |  |  |  | 
Cost | The BER has been presented and approved by ChMC on the 11th Sept. The Closure Report will be issued in ChMC in November |  |  | 
Resources | Daily stand-up with all areas; resources being understood and prioritized for Inner Tolerance check and Reporting |  |  | 

## Slide 14: 8.5 XRN4991 - MOD0700 Timelines
2019
Aug | Sept | Oct
SAP - ISU
Key:
Completed
Slipped / High risk
Medium risk
On-target
Market Flow
Reporting
Design
Build & Test (Unit, System, UAT and Regression)
PIS
Performance Test
11/09: BER Approval
GO LIVE 28/09/19
28/08: Change Pack Approval
Design
Build & Test (Unit & System)
PIS
UAT and Regression
Received from AMT20/09
GO LIVE 28/09/19
Key: dashed line - proposed
today
Inner Tolerance
Planning
Reporting

## Slide 15: 8.6 UK Link Release Update
13th November ChMC

## Slide 16: 8.6 2019 / 2020 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
Assumes RETRO will deliver in Nov 2020
Assumes that there will be a Major Release in Nov 2020
Please note that this includes potential activity within UK Link over the next 24 months
Nov-19
BER Approval
10/04/18
EQR Approval
06/02/19
RETRO
Potential Activity
Governance Approval dates tbc
On track
At risk
Key
Complete
Feb-20
BER Approval / Change Pack Issue
10/04/19
Jun - 20
Change Pack Issue
Dec-19
Scope Approval
10/07/19
MiR 5
ChMC Scope Approval
10/07/19
EQR Approval
Aug-19
Scope Approval
10/07/19
MiR 6
Scope Approval
Nov-19
MOD 700
Imp Plan / BER Approval Sept-19
BER Approval
Nov-19
Nov -20
Scope Approval Dec 19 ChMC
BER Approval May 2020
EQR Approval Feb 19

## Slide 17: 8.6 Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
Sept 19 | 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | In PIS | September 2019 | High | NTS
 | 4665 | Creation of new End User Categories (EUC) | In PIS | June/Sep-2019 | High | Shippers
Mod 700 | 4991 | Enabling large scale utilisation of Class 3 - Mod 700 | In PIS | September 2019 | High | Xoserve
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | In Delivery | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | In Delivery | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | In Delivery | November 2019 | High | Shipper
 | 4866 | UIG Recommendation – removal of validation on uncorrected read | In Delivery | November 2019 | Low | Shipper
Feb-20 | 4955 | Amendments of MDD PSR needs code descriptions | In Delivery | February - 2020 | Medium | Shippers / GT/IGTs
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June-2020 | Small | Shippers / DNO
 | 4691 | CSEPs: IGT and GT File Formats (CGI Files) | In Delivery | June-2020 | Small | DNs / IGTs
 | 4692 | CSEPs: IGT and GT File Formats (CIN Files) | In Delivery | June-2020 | Medium | DNs / IGTs
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June-2020 | X-Large | Shippers / DNO
 | 4897, 4899 | Resolution of deleted Contact Details at a Change of Supplier event / Treatment of PSR data and contact details on a change of supplier event | In Design | June-2020 | Small | To be agreed
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June-2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June-2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June-2020 | X-Large | IGTs / DNO
 | 4871 – B | Modification 0665 – Changes to Ratchet Regime | In Delivery | June-2020 | Large | DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June-2020 | Medium | IGTs
 | 4941 | Auto updates to meter read frequency (MOD0692) | In Project Delivery - awaiting MOD approval | June-2020 | Large | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | 2021 | High | Shippers

## Slide 18: 8.6 Change Index – UK Link Unallocated External Impacting Changes
XRN |  | Change Title | Current Status | Indicative Release | Complexity
4851 |  | Moving Market Participant Ownership from SPAA to UNC/DSC (Documentation only) | CP in Capture | Major Release | TBC
4645 |  | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CP in Capture | Major Release | TBC
4801 |  | Additional information to be made viewable on DES | HLSO in Review | Major Release | TBC
4896 |  | Failure to Supply Gas System and Template Amendment | CP in Capture | Major Release | TBC
4923 |  | AQ Calculation for RGMA (ONUPD) Estimate Reads | CP in Capture | Major Release | TBC
4931 |  | Submission of Space in Mandatory Data on Multiple SPA Files | CP in Capture | Major Release | Small
4978 |  | Notification of Rolling AQ value (following transfer of ownership between M5 and M) | CP in Capture | Major Release | TBC
4990 |  | Transfer of sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (Mod 664) | CP in Capture | Major Release | TBC
4992 |  | Creation of new change type to recover last resort supply payment (Mod 0687) | CP in Capture | MiR Drop 6 | Medium
4914 |  | Mod 651 - Retrospective Data Update Provisions | Solution Approval | Major Release 2020 | TBC
4716 |  | Increased Field Length – ‘Updated by’ data item | On Hold | On Hold | Medium
4854 |  | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | In Capture | Unallocated | TBC
4780b |  | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Solution Approval | Nov 20 or CSSC | Large
4997 |  | Introducing new charge codes for pro-active payment of GSOP 3 and GSOP 13 | HLSO in Review | MiR Drop 6 | Medium
Feb 2020
Major Release
Retro 2020
Minor Release
Unallocated
KEY

## Slide 19: 8.6 June 2020 Release
Capture Estimates Vs Detailed Design Estimates

## Slide 20: 8.6 June 20 Release Sizing Update
XRN | Title | HLSO Complexity | Points | DD Complexity | Points | Delta
4865 | Amendment to treatment and reporting of CYCL reads | Small | 5 | Small | 5 | 0
4691 | CSEPs: IGT and GT file formats (CGI files) | Medium | 8 | Small | 5 | -3
4692 | CSEPs: IGT and GT file formats (CIN files) | Medium | 8 | Medium | 8 | 0
4772 | Composite weather variable improvements | Large | 13 | X-Large | 21 | +8
4930 | Requirement to inform shipper of meter link code | Small | 5 | Small | 5 | 0
4932 | Improvements to the quality of the conversion factor values held on the supply point register (MOD681) | Medium | 8 | Medium | 8 | 0
4888 | Removing duplicate address update validation for IGT supply meter points via CMS | Small | 5 | Medium | 8 | +3
4941 | Auto updates to meter read frequency (MOD692) | Medium | 8 | Large | 13 | +5
4871 B | Ratchet regime changes (MOD665) | Medium | 8 | Large | 13 | +5
4850 | Notification of customer contact details to transporters | Large | 13 | X-Large | 21 | +8
Totals |  |  | 81 |  | 107 | +26

## Slide 21: 8.6 Capture Estimation Refinement Actions
Where there are multiple systems impacted – assume increased complexity as integration and cross system / process testing needs to be factored in as well as multiple parties requiring engagement
Confidence in the requirements, at point of HLSO production, needs to be considered as there can be significant time lag where requirements can change
Testing – base UAT at 80% coverage as standard.

## Slide 22: 8.6 Minor Release Drop 6
Feb 2020 – Scope Approval Required

## Slide 23: 8.6 Minor Release Drop 6
Release date proposed as 29th Feb 2020.
In Scope:
XRN | Desc | HLSO Complexity | Points
4955 | MDD PSR needs codes descriptions | Medium | 8
4992 | Creation of new change type to recover Last Resort supplier payment (MOD687) | Small | 5
4997 | Introducing new charge codes for pro-active payment for GSOP 3 and GSOP 13 | Small | 5
 |  | Total | 18
Assumptions:
That option 4 will be agreed for 4992
That 4997 solution will be approved for the Dec 2019 ChMC
That 4997 and 4992 Billing testing can be combined
That AMT and BW changes will be accommodated.

## Slide 24: 8.6 November 2020 Release
Scope Candidates and Release Sizing

## Slide 25: 8.6 November 20 Major Release
Year | 2019 |  | 2020 |  |  |  |  |  |  |  |  |  | 
Month | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Phase | Start-Up |  | Init | Design |  |  | Build / Test / Implement |  |  |  |  |  | 
Points Available | 120 |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 100 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 75 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 34 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 21 |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 5 |  |  |  |  |  |  | 
Scope Approval
Change Packs issued for review
Change Packs issued
Implementation

## Slide 26
Chart: November 2020 Major Release - Available Points
| Nov | Dec | Jan | Feb | Mar | Apr | May
Available Points | 120 | 100 | 75 | 35 | 21 | 5 | 0

## Slide 27: 8.6 In Capture
XRN | Description | Current Status | High Level Complexity | Points | Indicative Release Type
4645 | Rejection of incrementing reads following Isolation (RGMA Flows) | In Capture with DSG | Medium | 8 | Major
4716 | Increased Field Length – ‘Updated by’ data item | Awaiting ChMC solution approval | Medium | 8 | Minor
4780b | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | In Capture with DSG | X-Large | 21 | Major
4801 | Additional information to be made viewable on DES | In Capture with DSG | Large | 13 | Major
4851 | Moving Market Participant Ownership from SPAA to UNC/DSC | In Capture with DSG | Medium | 8 | Minor
4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | In Capture with DSG | Medium | 8 | Minor
4896 | Failure to Supply Gas System and Template Amendment | Solution Development | Small | 5 | Minor
4904 | Supplier details to be accurately presented within primary billing supporting information files | In Capture | Medium | 8 | Major
4923 | AQ Calculation for RGMA (ONUPD) Estimate Reads | In Capture with DSG | Medium | 8 | Minor
4931 | Submission of space in mandatory data on multiple SPA files | In Capture with DSG | Medium | 8 | Major
4978 | Notification of Rolling AQ value (following transfer of ownership between M-5 and M) | In Capture with DSG | Medium | 8 | Minor
4989 | To implement the online solution for the Credit Interest process | In Capture | Medium | 8 | Minor
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | In Capture | Large | 13 | Major
5027 | UK Link Data Cleanse of Conversion Factor in line with MOD681S | In Capture with DSG | Large | 13 | Major
 |  |  |  | 137 | 

## Slide 28: 8.6 Major / Minor 2020
In Capture there are currently:
7 changes that are candidates for Major Release at an estimated points total of 84
7 changes that are candidates for Minor Release at an estimated points total of 53.

## Slide 29: 8.7 UK Link POAP

## Slide 30: 8.8. Change Assurance Health Check
Any queries raised at the meeting will be taken away and answered in Novembers meeting. If you wish to raise a question beforehand, please email uklink@Xoserve.com

## Slide 31
8.9 Customer Impacting Data Changes: XRNs
Change Proposals | Aug 19 | Sept 19 | Oct 19 | Nov 19 | Dec 19 | Jan 19 | Comments
4738: Shipper portfolio update of proposed Formula Year AQ/SOQ |  |  |  |  |  |  | 
4859: Increasing MAM Access to CDSP Data to Mitigate Reduced MAM Appointment Timescales |  |  |  |  |  |  | 
4824: National Grid Transmission Daily Gemini Report |  |  |  |  |  |  | Awaiting Customer Sign off
4860: National ‘Temporary’ UIG Monitoring |  |  |  |  |  |  | Data Strategy to confirm start up
4946: Reporting on Installed Meters with Conversion Capability |  |  |  |  |  |  | Change withdrawn – approved at DSG
XRN4928: BG Request for iGT Elected sites |  |  |  |  |  |  | 
4779: UNC Modification 0657S - Adding AQ reporting to the PARR |  |  |  |  |  |  | Change due for delivery for January PARR Report run
Capture
**Estimated Delivery
Delivery
**Estimated delivery dates will be confirmed on completion of Capture and align to the chosen solution.

## Slide 32
8.9 Data Changes: XRNs
Change Proposals | Aug 19 | Sept 19 | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Comments
4789: Updating Shipper Reporting Packs and glossary |  |  |  |  |  |  | Will remain in delivery until all requirements fulfilled through DDP drops
4980: Change Supply Point Enquiry API to add in extra field and make certain other fields visible. |  |  |  |  |  |  | BER Approval requested in October ChMC
4713: Actual read following estimated transfer read calculating AQ of 1 |  |  |  |  |  |  | 
5004: Golden Bullet Report |  |  |  |  |  |  | Options paper to be presented to DN’s

## Slide 33: 8.9.1 Automation and Optimisation
Change Management Committee – 13/11/19

## Slide 34: Purpose and Contents
Purpose
Seek agreement on next steps for Automation and Optimisation
Contents
High Level Options Previously Presented
Recommended Next Steps
Appendix

## Slide 35: 8.9.2 XRN5013 Data Access Platform – PAFA
Verbal Update

## Slide 36: High Level Options
Below is a high level breakdown of the options for consideration by the Change Management Committee. The options are split by recommended, additional and not technically feasible.
 | Option | Description | Timeline | Cost | Comments
Recommendation |  |  |  |  | 
Must Do | Continue DDP Delivery | Add KPMG recommendations which carry potential efficiency savings to the DDP product backlog and deliver DDP product backlog topics based on current priority | 2020/21 | Funded as part of BP20/21 | Recommendations added to backlog DDP in progress
Must Do | Consolidation of Reporting | Two internal changes will be raised to deliver the ‘Consolidation’ recommendations from KPMG | Completed | BAU Activity | XRNs will follow the normal process
1 | Analysis | Carry out detailed analysis with customers on reports identified, to reduce the number of reports delivered to Shippers via email. | 4 months | 96k | 8 week mobilisation period
Additional Available Option |  |  |  |  | 
2 | Expedite DDP Drops | Expedite DDP Drops but adding additional resources. | 4 months | 152k | 8 week mobilisation period
Not Technically Feasible |  |  |  |  | 
Unfeasible | KPMG Recommendations | KPMG recommendations delivered as a separate delivery from DDP is not technically feasible. Baseline data model needs to be completed before we produce any bespoke reporting | N/A | N/A | 

## Slide 37: Recommendation
Description: | Xoserve recommend that CHMC agree to postpone the Analysis option previously presented to the group. Xoserve will raise the CP for consideration at CHMC following DDP deliver drops 4/5 once more customer data is available to consume via DDP
Why are we recommending this approach?: | To maximise the benefit for customers from the Analysis, we should carry out the activity post DDP drop 4/5 when there is a more substantial amount of data available for customers We’re expecting the amount of customers using DDP to increase over the next year, therefore a wider set of customers will experience the benefit of the analysis activities

## Slide 38: Appendix

## Slide 39: Option 1 - Analysis
Description: | The team will perform detailed analysis on reporting provisioned to customers, and identify reports which could be candidates for decommissioning based on the same data being provisioned via DDP or API. They will also work with customers to understand why the reports are required, and what they’re being used for.
Benefits: | Working with customers identifies which reports contain data which could be obtained via DDP/API, enabling us to start having conversations with Shippers on decommissioning reports/training Helps identify where we could add value to our existing reporting services Helps ensure future developments are aligned to the report purpose Customer insight for Xoserve on to the purposes of the reporting and how we potentially improve the experience for our customers Potential identified opportunities to remove manual effort at the customer end Identifies a clear roadmap of opportunities in improving and removing duplication
Outputs: | Complete list of reports which are candidates for decommissioning or potential improvements Customer Improvement and Decommissioning Roadmaps Documented view on why/how Shippers use their reports, building on the report review output
Total Cost: | £96k
Timescale: | 4 month delivery, following an 8 week mobilisation period planned to start post new year
Risks: | Risk that no decommissioning opportunities will be identified Recruitment is around 8 weeks, delay will effect timelines. To mitigate this risk, we’re intending to begin mobilisation post new year Risk that Shippers will be unable to support due to industry priorities changing, which will put the analysis timelines at risk
Dependencies: | Dependency on Shippers to provide the relevant information on their reports, i.e. why the reports are needed, and how are they used
 | Resource | Day rate | Duration | Total Cost
1 | Platform Delivery Specialist | N/A | 4 months | BAU
2 | Business Analyst | £600 | 4 months | £48k
3 | Data Analyst | £600 | 4 months | £48k
4 | Total Cost for Analysis Team |  |  | £96k

## Slide 40: Must Do - Continue DDP Delivery
Description: | Recommendations provided by KPMG have been built in to the DDP product backlog. This option is to continue progressing with the DDP drops which are being released to Shippers this year, and will continue to be released next year.
Benefits: | There will be no additional investment required to deliver this option KPMG recommendations will be aligned with the DDP drops, ensuring consistency across the delivery Shippers will experience all benefits of DDP utilisation
Outputs: | More data being exposed via DDP KPMG recommendations have been included in the DDP delivery process
Total Cost: | Funding in place as part of BP20/21
Timescale: | Funding is in place until April 2021
Risks: | Risk that funding for DDP in BP20/21 will not cover all product backlog items Risk that priority of industry deliverables will change
Dependencies: | Delivery of backlog items is dependant on priority