## Actions
Meeting | Agenda item | Action Ref | Action | Owner | Target Date | Updates | Status
2019-05-09 | Recap of current DSC Change management process | 090519_01 | Xoserve to provide stats around Change proposals progressing through Change Management committee (ChMC) in respect of approvals vs send for initial review vs rejections at all stages of governance process. | Xoserve | 2019-06-17 | 14/06 - CS - The statistics have been collated for the Governance Review group members to view. | Closed
2019-05-09 | Recap of current DSC Change management process | 090519_02 | Xoserve to ensure Change Pack distribution list contains a representative from all DSC customers following the annual review. | Xoserve | 2019-07-01 | 14/06 - CS - The process and timing of how this annual review will be undertaken is being formulated and is in the process. | Open
2019-05-09 | Recap of current DSC Change management process | 090519_03 | Xoserve to provide a walkthrough of the on-line Change pack process at next Governance review group meeting. | Xoserve - Chan | 2019-06-25 | 14/06 - CS - Slides have been updated with link to the new walkthrough. | Closed
2019-05-09 | Fast track governance for Requests for Data | 090519_04 | Xoserve to update the ‘medium’ option to add in Initial review Change pack and take this as a recommendation from the group to Change management committee. | Xoserve - Alison | 2019-06-05 | 17/06 - CS - This has been approved at chanfe management. | Closed
2019-05-09 | Fast track governance for Requests for Data | 090519_05 | A review of the current Change process to be included as an agenda item at the next Governance Review Group meeting | Xoserve | 2019-06-17 | 17/06 - CS - The materials have been added to the slide deck. | Closed
2019-05-09 | Review of Change Management Guidelines (XRN4852) | 090519_06 | Xoserve to issue the revised DSC Change Management procedures document out in a Change pack for review | Xoserve - Emma | 2019-06-14 | 14/06 - CS - This has been added to the June Change Pack for industry consultation. | Open
2019-05-09 | Review of Change Management Guidelines (XRN4852) | 090519_07 | All to review the revised DSC Change Management procedure and provide any comments in the response to the Change pack. | All | 2019-06-25 | 17/06 - CS - For all to discuss and rpvides feedback and comments. | Open
2019-05-09 | Review of Change Management Guidelines (XRN4852) | 090519_08 | Review of Change Management Guidelines (XRN4852) to return as an agenda item at the next Governance Review Group. | Xoserve - Emma | 2019-06-17 | 17/06 - CS Agenda items have been created and added to the slide deck. | Open
2019-05-09 | Urgent Change Proposal process | 090519_09 | Xoserve to revise slides changing Urgent to Accelerated and bring back to Governance review group as an agenda item at next meeting. | Xoserve - Alison | 2019-06-17 | 17/06 - CS - Slides have been updated to relflect the changes mentioned. | Closed
2019-05-09 | Urgent Change Proposal process | 090519_10 | Xoserve to update the definition of Accelerated process to clarify the system change sentence. | Xoserve - Alison | 2019-06-17 | 17/06 - CS - This has been completed and ready for review at the next meeting. | Closed
2019-05-09 | Urgent Change Proposal process | 090519_11 | Xoserve to update the Change proposal template to include criteria and text box for proposer to state why accelerated route needed if an accelerated process is approved by ChMC. | Xoserve | 2019-07-30 | 17/06 - CS This is still ongoing if/once an accelerated Change Proposal procees is approved at ChMC. | on-going
2019-05-09 | Urgent Change Proposal process | 090519_12 | Xoserve to update accelerated process proposal to include a proposed timetable | Xoserve - Alison | 2019-06-17 | 17/06 - CS - This has been completed and added into the process for the next meeting. | Closed
2019-05-09 | Definition of External Impacts | 090519_13 | Xoserve to investigate ways to communicate out internal changes for customers to identify those they believe had impacts on them. | Xoserve | 2019-06-17 | 17/06 - CS - Materials have been created and added to the slide deck for the agenda item | Closed
2019-05-09 | Initiatives log | 090519_14 | Xoserve create proposal for Business plan delivery updates and bring to next Governance review meeting. | Xoserve | 2019-06-17 | 17/06 - CS - Materials have been created and added to the slide deck. | Closed
2019-05-09 | Updates to the Change proposal template | 090519_15 | Xoserve to update Change proposal template to add back in Change description and issue to ChMC for approval. | Xoserve - Alison | 2019-06-03 | 14/5 - AC - completed | Closed
2019-05-09 | • Hosting of all relevant information for a Release | 090519_16 | Xoserve to ensure all relevant information about an XRN and its release are easily accessible on Xoserve.com | Xoserve - Chan | on-going | 14/06 - CS - All release pages now link to each CP (Vice Versa) and have been updated with the ChMC RAG status slides (Release Pages). | on-going
2019-05-09 | • Proposal for shortening or lengthening Change Pack timescales | 090519_17 | Proposal for shortening or lengthening Change Pack timescales - To be added to agenda of next Review Group meeting | Xoserve | 2019-06-17 | 14/06 - CS - As per ChMC the new Change proposal template V7 has been approved and now offers 3 options of 10,15 & 20 WD Change Pack period compared to the 10, 20 & 30 WD Period. | Closed