## Slide 1: 7.1 XRN4996 - June 20 Release - Status Update
11th December 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: Delivery timeline under replan following descope of 3 changes Scope: Revised BER (removing 3 descoped changes) and Market Trials Option 4 approved Implementation: Implementation date of Saturday 20th June proposed |  |  | 
Risks and Issues | Risk – There is a risk that for xrn4941 a number of assumptions will be required in design which may not be validated until after build because MOD0692 has not been approved leading to rework and delays |  |  | 
Cost | BER for full delivery approved at eChMC on 22nd November. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 

## Slide 2: XRN4996 - June 20 Release Timelines
Key Milestone Dates:
Capture completion – 19/09/19
Design Completion – 13/12/19
Build & Unit Test Completion – 31/01/20 (provisional)
System & UAT Completion – 24/04/20 (provisional)
Regression Test Completion – 29/05/20 (provisional)
Implementation – 20/06/20 (proposed)
PIS Completion – 25/09/20 (provisional)

## Slide 3: June 20 Release Summary
June 20 Release consists of 7 changes, Implementation is planned for June 2020:
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4850 - Notification of Customer Contact Details to Transporters
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4830 – Requirement to Inform Shipper of Meter Link Code Change
XRN4941* - Auto updates to meter read frequency (MOD0692)
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
* Pending Solution/MOD approval by ChMC/DSG for remaining CRs.
** Descoped at eChMC on 22/11/19

## Slide 4: 7.2 XRN4996 - June 20 Implementation Date
The proposed implementation date for June 20 is the weekend of 19th – 21st June 2020 with the changes going live on 20th June.
A contingency date of 26th – 28th June is also proposed.
Approval of these dates is requested.
Please note: A high level implementation timeline and the file format transition plan will be shared for your information closer to the implementation date.

## Slide 5: 8.1 XRN4665 – EUC Release
11/12/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Post Implementation Support (PIS) PIS activities (including First Usage monitoring) continue to be monitored as per plan First Usage evidence continues to be provided to and assured by both Xoserve SME’s & Tech Ops Application Handover Document walkthrough completed with Tech Ops. To be submitted for Approval Production of a required Impact Assessment underway to provide solution option & fix plan for raised issue on the BW ‘Network Throughput Data’ weekly report Closedown Closedown preparation commenced Closedown milestone to be assessed and re-planned based on receipt of fix plan associated to BW report issue |  |  | 
Risks and Issues | One open issue Re: recently identified impacted BW report defect requiring resolution by the Project team. Resulting in an extended PIS period and delay to the Closedown milestone |  |  | 
Cost | Project delivery costs are tracking to approved internal budgets (Revised BER to include Financial Risk margin approved at ChMC on 10/07/19) |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 6: XRN 4665 - EUC Release Timelines
Key Milestone Dates:
PIS & First Usage monitoring activities ongoing
Application Handover to be submitted for Approval
Closedown milestone movement assessment underway
NRL Issued
T67 Issued

## Slide 7: 8.2 XRN4828 - Nov 19 Release - Status Update
11/12/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Deployment of in scope changes successfully completed on 09/11/19 PIS and First Usage monitoring commenced and currently tracking to plan Required data fix to resolve a backlog of BI40 exceptions has been identified and accepted by the project to resolve. Project team currently working on an Impact Assessment to clearly articulate the issue, all solution options and associated fix plan(s) |  |  | 
Risks and Issues | Risk raised that the required data fix to resolve the BI40 exceptions backlog will go past the current planned date for completion of PIS and could potentially delay the Closedown milestone |  |  | 
Cost | The BER with full delivery costs were approved at ChMC in April 2019, BER for XRN4866 UIG Recommendation approved by ChMC on 12th June |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 

## Slide 8: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Successful Implementation – 09/11/19
PIS Completion – 20/12/19
Closedown – 17/01/20 (to be assessed. Milestone may need to move out based on timescales for BI40 Exceptions Backlog FIX)
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
XRN4828
Nov-19
HLD & Change Pack Production
Design
Build & FUT
ST & SIT
UAT
PIS
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Approval
GO LIVE 09/11/19
RT & PT / Implementation Prep

## Slide 9: 8.3 XRN4914 MOD 0651- Retrospective Data Update Provision

## Slide 10: XRN4914 MOD 0651- Retrospective Data Update Provision – Proof of Concept Progress update
11th December 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Delivery: Design Documents for Step 1 to be finalised Business and Validation Rules for Step 1 of PoC completed File and Connectivity testing being completed ahead of start of PoC part 1 execution in early December Detailed requirements workshops for Steps 2 of data comparison and root cause to be scheduled w/c 2nd Dec Customer Engagement and Communications: Web page now live and we will be providing fortnightly updates As of 28th November 3 shippers have confirmed participation in Step 1 of the PoC with several others expressing an interest. PoC execution due to commence in early December. |  |  | 
Risks and Issues | There is a risk that there will not be sufficient volume received from Shippers in the proof of concept to be able to quantify the size of the data mis-match activity. At present 3 shippers have confirmed participation with a data set of approx. 2.6m expected |  |  | 
Cost | Approval received from DN’s for BER of £270k for proof of concept |  |  | 
Resources | Security resource allocated to proof of concept Working with SME team to agree resource allocation as required Concerns raised about availability of Customer Change Team resource to support delivery and specifically Customer Engagement activities |  |  | 
XRN4914 MOD 0651 - Retrospective Data Update Provision - ChMC Update 11th December

## Slide 11: XRN4914 – Retro proof of concept - timeline
2019/2020
November | December | January | February
Customer Engagement
Key:
Completed
Slipped / High risk
Medium risk
On-target
Support
Analysis
Customer / Advocates encouraging participation
Checkpoint 2
24th Jan
Checkpoint 1
29th Nov
Design
Test files can be accepted
Initial Customer engagement
kick-off 4th Nov
today
Planning
Develop
Testing
Kick-off prep
Actual data
files in
Step 1 Compare / Outcome / Aggregate
Initial Customer engagement of File receipt
ends 3rd Jan
Actual data files can be accepted
Support
Step 2 – deep dive / Outcome / Aggregate
Weekly project update via external communication methods
Test data
files in
Checkpoint 3
3rd Feb
Date for slicing data
4th Dec
Output from Step 1
Output from Step 2
Recommendations
XRN4914 MOD 0651 - Retrospective Data Update Provision – 27th November 2019

## Slide 12: 8.4 Minor Release Drop 6
Feb 2020 – Scope Approval Required

## Slide 13: Minor Release Drop 6
Release implementation date proposed as 29th Feb 2020.
In Scope:
XRN | Desc | HLSO Complexity | Points
4955 | MDD PSR needs codes descriptions | Medium | 8
4992 | Creation of new change type to recover Last Resort supplier payment (MOD687) | Small | 5
4997 | Introducing new charge codes for pro-active payment for GSOP 3 and GSOP 13 | Small | 5
 |  | Total | 13
Assumptions:
That 4997 solution will be agreed with DSG 2nd Dec and approved for the 11th Dec ChMC
That AMT and BW changes will be accommodated
XRN4992 is out of scope as agreed at ChMC 22nd Nov 2019.

## Slide 14: 8.5 UK Link Release Update
11th December 2019 CHMC

## Slide 15: 2019 / 2020 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
Assumes RETRO will deliver in Nov 2020
Assumes that there will be a Major Release in Nov 2020
Please note that this includes potential activity within UK Link over the next 24 months
Nov-19
BER Approval
10/04/18
EQR Approval
06/02/19
RETRO
Potential Activity
Governance Approval dates tbc
On track
At risk
Key
Complete
Feb-20
BER Approval / Change Pack Issue
10/04/19
Jun - 20
Change Pack Issue
Dec-19
Scope Approval
10/07/19
MiR 5
ChMC Scope Approval
10/07/19
EQR Approval
Aug-19
Scope Approval
10/07/19
MiR 6
Scope Approval
Nov-19
MOD 700
Imp Plan / BER Approval Sept-19
BER Approval
Nov-19
Nov -20
Scope Approval Dec 19 ChMC
BER Approval May 2020
EQR Approval Feb 19

## Slide 16: Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | In Delivery | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | In Delivery | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | In Delivery | November 2019 | High | Shipper
 | 4866 | UIG Recommendation – removal of validation on uncorrected read | In Delivery | November 2019 | Low | Shipper
MiR D6 Feb-20 | 4955 | Amendments of MDD PSR needs code descriptions | In Delivery | February - 2020 | Medium | Shippers / GT/IGTs
 | 4997 | Introducing new charge codes for pro-active payment of GSOP 3 and GSOP 13 | Awaiting ChMC approval | MiR D6 | Small | DNO
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June-2020 | Small | Shippers / DNO
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June-2020 | X-Large | Shippers / DNO
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June-2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June-2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June-2020 | X-Large | IGTs / DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June-2020 | Medium | IGTs
 | 4941 | Auto updates to meter read frequency (MOD0692) | In Project Delivery - awaiting MOD approval (Jan 20) | June-2020 | Large | Shippers
 | 4780b | MAP ID Part B | Awaiting Solution Approval | June 2021 | Large | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | June 2021 | XXXXL | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | November 2020 | tbd | DNs

## Slide 17: November 20 Major Release
Year | 2019 |  | 2020 |  |  |  |  |  |  |  |  |  | 
Month | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Phase | Start-Up |  | Init | Design |  |  | Build / Test / Implement |  |  |  |  |  | 
Points Available | 120 |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 100 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 75 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 34 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 21 |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 5 |  |  |  |  |  |  | 
Scope Approval
Change Packs issued for review
Change Packs issued
Implementation

## Slide 18: Change Index – UK Link Unallocated External Impacting Changes
XRN |  | Change Title | Current Status | Points | Indicative Release | Complexity
4851 |  | Moving Market Participant Ownership from SPAA to UNC/DSC (Documentation only) | CP in Capture | 5 | Major Release | TBC
4645 |  | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CP in Capture | 8 | Major Release | TBC
4801 |  | Additional information to be made viewable on DES | HLSO in Review | 13 | Major Release | TBC
4896 |  | Failure to Supply Gas System and Template Amendment | CP in Capture | 5 | Major Release | TBC
4923 |  | AQ Calculation for RGMA (ONUPD) Estimate Reads | CP in Capture | 8 | Major Release | TBC
4931 |  | Submission of Space in Mandatory Data on Multiple SPA Files | CP in Capture | 8 | Major Release | Small
4978 |  | Notification of Rolling AQ value (following transfer of ownership between M5 and M) | CP in Capture | 8 | Major Release | TBC
4990 |  | Transfer of sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (Mod 664) | CP in Capture | 13 | Major Release | TBC
4992 |  | Creation of new change type to recover last resort supply payment (Mod 0687) | CP in Capture | 8 | Major Release | Medium
4914 |  | Mod 651 - Retrospective Data Update Provisions | Solution Approval | N/A | Major Release 2020 | TBC
4716 |  | Increased Field Length – ‘Updated by’ data item | On Hold | 8 | On Hold | Medium
4854 |  | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | In Capture | 13 | Unallocated | TBC
4780c |  | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Solution Approval | 13 | Nov 20 or CSSC | Large
4871 – B |  | Modification 0665 – Changes to Ratchet Regime | Scope Approval (descoped from June 20) | 21 | Nov 20 | Large
4691 |  | CSEPs: IGT and GT File Formats (CGI Files) | Scope Approval (descoped from June 20) | 8 | Nov 20 | Small
4692 |  | CSEPs: IGT and GT File Formats (CIN Files) | Scope Approval (descoped from June 20) | 8 | Nov 20 | Medium
5027 |  | UK Link Data Cleanse of Conversion Factor in line with MOD681S | CP in Capture | 8 | TBC | TBC
4897, 4899 |  | Resolution of deleted Contact Details at a Change of Supplier event / Treatment of PSR data and contact details on a change of supplier event | Awaiting Scope Approval | 8 | TBC | Medium
KEY:
Retro
Nov 20 Candidate
Unallocated

## Slide 19: 8.6 UK Link POAP

## Slide 20: 8.8 Data Office Changes

## Slide 21
Customer Impacting Data Changes: XRNs
Change Proposals | Sept 19 | Oct 19 | Nov 19 | Dec 19 | Jan 19 | Comments
4738: Shipper portfolio update of proposed Formula Year AQ/SOQ |  |  |  |  |  | 
4859: Increasing MAM Access to CDSP Data to Mitigate Reduced MAM Appointment Timescales |  |  |  |  |  | 
4860: National ‘Temporary’ UIG Monitoring |  |  |  |  |  | Data Strategy to confirm start up for product user case
XRN4928: BG Request for iGT Elected sites |  |  |  |  |  | 
4779: UNC Modification 0657S - Adding AQ reporting to the PARR |  |  |  |  |  | Change due for delivery for January PARR Report run
4980: Change Supply Point Enquiry API to add in extra field and make certain other fields visible. |  |  |  |  |  | 
4713: Actual read following estimated transfer read calculating AQ of 1 |  |  |  |  |  | 
5004 – Golden Bullet Report |  |  |  |  |  | 
Capture
**Estimated Delivery
Delivery
**Estimated delivery dates will be confirmed on completion of Capture and align to the chosen solution.
PART A
PART B

## Slide 22: 10. UIG Task Force Progress Report

## Slide 23: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a Task Force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task Force dashboard
  POAP
  Recommendation stats
  Reporting on budget
  UIG Task Force Activities migration post October 19

## Slide 24: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Date | Status
Attend November UIG Work Group | 26/11/19 | Complete
Attend November Change Management Committee | 13/11/19 | Complete
Attend November Contract Management Committee | 20/11/19 | Complete
Executive Summary Update | w/c 18/11/19 | Complete
Attend Work Group 674 | 11/12/19 | On track
Priorities for next month – key milestones | Date | Status
Overall RAG status:*
Support Mod development (All) | 01/03/19 | G
Development of automated UIG reporting | End of June | R
Commence UIG Task Force close down/extension options | 01/07/19 | G
Attend December Change Management Committee | 11/12/19 | G
Attend December Contract Management Committee | 18/12/19 | G
Executive Summary Update | w/c 16/12/19 | G
Attend December UIG Work Group | 12/12/19 | G

## Slide 25: Plan on Page Updated
Delivery team milestone
Advanced Analytics
I
Governance
C
Completed activity
 | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January 2020 |  |  |  | 
 | 05/08 | 12/08 | 19/08 | 26/08 | 02/09 | 09/09 | 16/09 | 23/09 | 30/09 | 07/10 | 14/10 | 21/10 | 28/10 | 04/11 | 11/11 | 18/11 | 25/11 | 2/12 | 09/12 | 16/12 | 20/12 | 06 | 06/01 | 13/01 | 20/01 | 27/01
Issue analysis and tracking (Investigation Tracker updated and published bi-weekly)
Develop Findings template and Recommendation Packs
Investigation Analysis
Develop Xoserve owned Recommendation options – update and publish recommendation tracker in line with UIG working group meetings
Support Mod development
I
07/08 DSC ChMC
I
11/09 DSC ChMC
I
14/08 CoMC
I
18/09 CoMC
I
20/08 UIG WG
I
23/09 UIG WG
w/c 05/08 Exec Summary
w/c 09/09 Exec Summary
Review/draft updates to UIG user guide ongoing
BAU Publish UIG Investigation guide V.2
w/c 01/07 create close out activity plan
I
09/10 DSC ChMC
I
16/10 CoMC
w/c 11/11 Exec Summary
I
22/10 UIG WG
I
20/11 CoMC
I
26/11 UIG WG
I
13/11 DSC ChMC
Rescheduled
w/c 16/12 Exec Summary
I
11/12 DSC ChMC
I
18/12 CoMC
I
12/12 UIG WG
I
08/01 DSC ChMC
I
15/01 CoMC
I
21/01 UIG WG

## Slide 26: Recommendations - where we are
4 lines MOD – (3.2.1) = 3 MODS – 1 sponsored Total 0692), 2 sponsored British Gas 0690 & 0691
22 review at December Workgroup
4 lines MOD 0681 – EON
53 CLOSED
9 lines MOD – Scottish Power (12.2) = 1 MOD – sponsored 0693R
11 do nothing
2 BAU
13 completed
27 other options progressed
8 carried over from November meeting
8 review December
14 finding & recommendations = 95 recommendation lines
2 lines Xoserve drafted MODs 3.2.5
1 line MOD 0699 Scottish Power
6 carried over from October meeting

## Slide 27: Overview Of Task Force Funding

## Slide 28: Reminder – UIG Task Force Activities migration post October 19
Pre November Task Force | Post October Customer Support Services Team | Post Oct Customer Change Team
Existing activities which will migrate Daily UIG Box account management Monthly UIG Executive Summary Creation of UIG monthly dashboard stats Web page ownership updates & maintenance UIG Work Group attendance UIG Work Group Task Force recommendation tracking UIG data sources creation UIG modification alignment creation & publication Machine Learning new analysis Budget mapping and forecast . Support development of new online UIG interactive reporting Activities which will cease Representation at ChMC & CoMC | Existing activities which will be migrated Daily UIG Box account management Monthly UIG Executive Summary Creation of UIG monthly dashboard stats Web page ownership updates & maintenance UIG Work Group attendance UIG Work Group Task Force recommendation tracking UIG data sources maintenance UIG modification alignment pack maintenance Machine Learning outstanding analysis Budget monitoring for UIG activities Outstanding CP 4853 Interim process to monitor and manually load rejected reads into UK Link where the read was rejected for reason MRE00458 only. Manual work around to be closed out end of October 19. UIG brochure version 2 creation & publication Re-purpose the existing "Lines of investigation tracker" Work with Customer Change team to develop formal project close down New activities which will commence Support maintenance of new online UIG interactive reporting Adhoc new UIG related requests One off activities e.g. simulations/adhoc UIG reporting requests – considered by Customer Support Services and/or directed to raise CP | Live CP4866 Removal of validation on uncorrected read due November release Work with Customer Team complete outstanding UIG related CR's. Newly identified Modifications & CRs

## Slide 29: 11.1 Bubbling Under Report

## Slide 30: 11.2 Gemini Horizon Planning

## Slide 31: 12 Finance and General Change Budget Update

## Slide 32: 13.1 Xoserve IX Refresh

## Slide 33: IX Refresh Customer Update
Our partner Gamma has now been in contact with your organisation’s given IT/ Business contacts and conducted consultation calls.
The Vodafone support of the legacy IX service ends in February 2020 and we will therefore be ramping up our communications to confirm your migration date. All dates will be within the next 3 months to ensure a successful transition to the new Gamma IX service.
To ensure the project completes on time we need your support in committing to the migrations dates. We have observed a number of last minute cancellations which adds additional cost and puts the completion date at risk.
A Communication was submitted last week to all contract managers that set-out the key dates that need to be met as part of this project, including the appointment process.
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com

## Slide 34: 13.2 CDSP Prioritisation and Release Scoping Approach Review

## Slide 35
What we are proposing to change and why
In July 2017 the ChMC reviewed and approved the initial ‘Xoserve Prioritisation and Scoping Approach’ document, which was written in the early days of the post-Nexus landscape
Our approach to prioritisation and release scoping has since evolved (t-shirt sizing, elected body requests)
Improvements and refinement to the process need to be reflected in relevant documentation
We intend to redraft the document for your review (January 2020) and approval (February 2020)

## Slide 36: 13.3 KVI Change Management Survey Feedback
November 2019

## Slide 37: KVI Change Management Survey – July & October 2019
10 responses received by customers:
July – 4
October - 6
July - achieved a KVI of 89.7% against our target of 90% rated as ‘Always’ or ‘Usually’
October - achieved a KVI of 100% against our target of 90% rated as ‘Always’ or ‘Usually’
YTD 95%
6 reviewers provided further comments on the Change management process in July/October – see following slides

## Slide 38: Overview
2nd & 3rd Surveys completed for year 2019/2020 (July)
Issued to approx. 450 Industry contacts
Chart: Customer Change Satisfaction: Target 90%

## Slide 39: I receive timely and fit for purpose information to enable me to manage new changes that impact my organisation
Oct 19 (6)
July 19
(6)
Individual question responses April 19 vs Jan 19
Xoserve presents a range of solution options for each change to enable choice
I trust Xoserve to identify solutions that benefit the whole Industry where possible
Xoserve supports the ability for me to fully engage me in the change process, should I choose to
I trust Xoserve to deliver changes to agreed costs, timescales and quality
Chart: 
| Always | Usually
Total | 1 | 5
Chart: 
| Usually
Total | 6
Chart: 
| Always | Rarely | Usually
Total | 2 | 1 | 2
Chart: 
| Always | Usually
Total | 2 | 4
Chart: 
| Rarely | Usually
Total | 2 | 4
Chart: 
| Usually
Total | 6
Chart: 
| Usually
Total | 6
Chart: 
| Usually
Total | 6
Chart: 
| Always | Usually
Total | 1 | 5
Chart: 
| Usually
Total | 6

## Slide 40: You said – We did – July 2019
You Said | We Did
The increase in cost in Retro Solution is an example of changes to agreed costs. | We acknowledge your concerns regarding the costs associated with the Retro Solution and have spent some time making improvements to the process for high level costs and the transition to locked down costs further through the change lifecycle. We have improved the process around scaling of releases and have recently implemented a ‘t-shirt sizing’ process for change to help plan for change releases and understand better the cost of change as early as possible.
There are still issues where changes are being released and shortly, if not immediately, afterwards falling over and failing. There is an apparent lack of performance testing. | We acknowledge your concerns regarding post implementation defects and performance testing. For major releases there is an element of performance testing carried out but this does come at a cost. We have improved the process around scaling of releases and have recently implemented a ‘t-shirt sizing’ process for change to help plan for change releases. In addition we have been providing further information on choice in terms of releases which includes a view of the costs and risks associated with releases which includes the costs associated with testing from minimal testing, minimal risk to full scale regression testing and market trials, the reasoning being that this gives customers choice in relation to how much they want to spend on a release and what customer risk appetite is. We continually monitor the impacts of change at the point of implementation through the warranty period and hope that you will find the changes that have been made will help alleviate your concerns.

## Slide 41: You said – We did – October 2019
You Said | We Did
The Change Proposal process is clear and transparent, the Change Request process much less so with no real clarity on delivery dates which can suddenly get put back. The Alternative Service Request process which is out of scope of this survey is more opaque again even for those who are fairly familiar with the change process. | Thankyou for your feedback on the Change Proposal process, we are pleased that the process is transparent and hope that you find it quick and easy to raise a CP. We acknowledge that the Change Request process is not so clear and that delivery dates can move some what. This is largely due to the nature of changes that follow this process. Data Changes tend to follow the CR process and as there are no standard releases for those should a change be raised that is deemed to be a higher priority (Housing Association requests for example) then other delivery dates can move. We are reviewing the whole change process including the Change Request process and the Alternative Service Request to understand how those requests can be made more visible to customers and how they feed into the overall Change Prioritisation process.
Improvement still needed in Xoserve's ability to identify all impacted constituency parties (they still tend to just focus on Shippers) and to clearly communicate those impacts. | We acknowledge your concerns in respect of all impacted constituency parties. We are working hard to ensure all of our customers are highly engaged and receive a high level of service from Xoserve. We are currently reviewing all of our change processes and will look at how we can ensure that, where we think there is an impacted constituency this is market clearly and we can articulate the reasons that drive the potential impact to make it clear for customers to identify those changes that they need to review and feed into.

## Slide 42: You said – We did – October 2019
You Said | We Did
I have noticed more and more that comments we make in relations to the change packs more and more receive a response which feels very much like 'it is what it is now'. Of late I have been unable to attend DSG due to other priorities however as a result have found myself in a position that by the point a change pack is issued, the solution seems to have been almost decided upon and any comments seem to receive a response to this nature. It feels unfortunate that if DSG is not attended, we are unable to make any suggestions in design improvements that are taken forward for consideration. Further to this the changes as a result of MOD700 where communicated/summarised via change pack very late in the day leaving us very little time to make any required system changes. I rely on the change packs to drive my system changes and so this proved to be very challenging. (Elly) In addition the quality of the information in change packs could be better to make them more effective. They have improved but could do with improving further so that the change pack is everything you need to be able to assess a change and it’s impacts | We acknowledge the feedback on change pack responses. As discussed solutions are discussed in DSG with a view to recommend preferred solution to Change Management Committee. We are aware that DSG needs to evolve somewhat and are working on the format and frequency of meetings with a view to being solely to discuss solution options and be shortened to ensure that customers are able to attend and feel that the meeting adds value. In relation to the timescales to turn around responses to change packs we are also looking at the schedule for responses in order to allow customers enough time to respond and for Xoserve to provide relevant and valuable feedback on the back of those responses. We also appreciate the feedback on the change pack content and the quality of the information. We will look at the content of future change packs with a view to assessing how we can add information to the packs but ensure that the size of the documentation does not lean to customers not having the time to review.

## Slide 43: You said – We did – October 2019
You Said | We Did
I find the Xoserve change process a lot more difficult to follow than UNC or BSC changes - I'd prefer to see significant changes lifted out of the change packs and tracked individually. In addition, there do not appear to be any obvious processes in place to provide customers information to core activities. If I wanted to find guidance on the AQ process it is hard to navigate to specific documentation and when searching on Xoserve.com a PowerPoint document will be pulled back that suggests a moment in time rather than a baselined process used as a reference point. | We acknowledge your concerns regarding the Change Pack Process and how it can be improved to make it easier to identify significant impacting changes and the solutions being proposed as part of the over all Change Pack. We are currently reviewing all our change processes including the Change Packs and will ensure that your suggestion is used to help improve the process. With regards to documentation, with the change processes we are also looking to improve the navigation around the website to make it quick and easy to get to information.