## Slide 1: UK Link Releases Update
January 2020 CHMC

## Slide 2: 2020/2021 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2020 | 2021
Assumes that there will be a Major Release in Nov 2020
Please note that this includes potential activity within UK Link over the next 24 months
BER Approval
10/04/18
RETRO
Potential Activity
Governance Approval dates tbc…
On track
At risk
Key:
Complete
Feb-20
Jun - 20
Nov 20
4779
MiR 6
BER Approval
May-20
CSSC activity
CSSC
Scope approval – Feb ChMC
EQR Approval – March ChMC

## Slide 3: Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | In Delivery | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | In Delivery | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | In Delivery | November 2019 | High | Shipper
 | 4866 | UIG Recommendation – removal of validation on uncorrected read | In Delivery | November 2019 | Low | Shipper
4779 | 4779 | AQ into PARR reports | In Delivery | Standalone BW | Medium | PAC
MiR D6 Feb-20 | 4955 | Amendments of MDD PSR needs code descriptions | In Delivery | February - 2020 | Medium | Shippers / GT/IGTs
 | 4997 | Introducing new charge codes for pro-active payment of GSOP 3 and GSOP 13 | Awaiting ChMC approval | MiR D6 | Small | DNO
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June-2020 | Small | Shippers / DNO
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June-2020 | X-Large | Shippers / DNO
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June-2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June-2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June-2020 | X-Large | IGTs / DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June-2020 | Medium | IGTs
 | 4941 | Auto updates to meter read frequency (MOD0692) | In Delivery | June-2020 | Large | Shippers
 | 4780b | MAP ID Part B | Awaiting Solution Approval | June 2021 | Large | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | June 2021 | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | November 2020 | N/A | DNO

## Slide 4: November 20 Major Release
Year | 2019 |  | 2020 |  |  |  |  |  |  |  |  |  | 
Month | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Phase | Start-Up |  | Init | Design |  |  | Build / Test / Implement |  |  |  |  |  | 
Points Available | 120 |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 100 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 75 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 34 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 21 |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 5 |  |  |  |  |  |  | 
Scope Approval
Change Packs issued for review
Change Packs issued
Implementation

## Slide 5: UK Link – Unallocated Changes
XRN# | Description | Capture Status | Release Type | Indicative Release | Complexity | Points
4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | In capture | Major | tbc | Tbc | tbc
4691 | CSEPs: IGT and GT File Formats (CGI Files) | Ready | Major | Nov 20 | Medium | 8
4692 | CSEPs: IGT and GT File Formats (CIN Files) | Ready | Major | Nov 20 | Medium | 8
4716 | Increased Field Length – ‘Updated by’ data item | Closed | N/A | N/A | N/A | N/A
4780c | MAP ID (Part C) Inclusion of Meter Asset Provider Identity in the UK Link system (CSSC) | Requirements gathering | Major | Nov 20 | Large | 13
4801 | Additional information to be made viewable on DES | HLSOs in review | Major | Nov 20 | Large | 13
4851 | Moving Market Participant Ownership from SPAA to UNC/DSC | Requirements in review | tbc | tbc | tbc | tbc
4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | In capture | tbc | tbc | tbc | tbc
4871b | Modification 0665 – Changes to Ratchet Regime (Part B) | Ready | Major | Nov 20 | X-Large | 21
4896 | Failure to Supply Gas System and Template Amendment | Requirements in review | Minor | tbc | Small | 5
4897 | Resolution of deleted Contact Details at a Change of Supplier event | HLSOs in review | Major | Nov 20 | Small | 5
4899 | Treatment of PSR data and contact details on a change of supplier event | HLSOs in review | Major | Nov 20 | Small | 5
4914 | Retro (MOD 651) | On hold for POC | Standalone | tbc | tbc | tbc
4923 | AQ Calculation for RGMA (ONUPD) Estimate Reads | Requirements in review | Minor | Tbc | tbc | tbc
4931 | Submission of Space in Mandatory Data on Multiple SPA Files | DSG review | Minor | Nov 20 / Minor | Small | 5
4978 | Notification of Rolling AQ value (following transfer of ownership between M5 and M) | In capture | tbc | tbc | tbc | tbc
4990 | Transfer of sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (Mod 664) | Ready for assignment | Major | tbc | tbc | tbc
4992 | Creation of new change type to recover last resort supply payment (Mod 0687) | DSG review | Major | Nov 20 | Medium | 8
5027 | UK Link data cleanse of conversion factor in line with MOD681s | In capture | tbc | tbc | tbc | tbc