## Slide 1: UIG Task Force Progress Report
Change Management Committee 08/01/2020

## Slide 2: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a Task Force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task Force dashboard
  POAP
  Recommendation stats
  Reporting on budget
  UIG Task Force Activities migration post October 19

## Slide 3: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Date | Status
Attend December UIG Work Group | 12/12/19 | Complete
Attend December Change Management Committee | 11/12/19 | Complete
Attend December Contract Management Committee | 18/12/19 | Complete
Executive Summary Update | 20/12/19 | Complete
Attend Work Group 674 | 11/12/19 | Complete
Approval of UNC Mod 0692S | 19/12/19 | Complete (UKLink June 2020 Release)
Priorities for next month – key milestones | Date | Status
Overall RAG status:*
Support Mod development (All) | 01/03/19 | G
Development of automated UIG reporting | End of June | R
Commence UIG Task Force close down/extension options | 01/07/19 | G
Attend January Change Management Committee | 08/01/20 | G
Attend January Contract Management Committee | 15/01/20 | G
Executive Summary Update | w/c 27/01/20 | G
Attend January UIG Work Group | 21/01/20 | G

## Slide 4: Plan on Page Updated
 | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January 2020 |  |  |  | February 2020 |  |  | 
 | 02/09 | 09/09 | 16/09 | 23/09 | 30/09 | 07/10 | 14/10 | 21/10 | 28/10 | 04/11 | 11/11 | 18/11 | 25/11 | 2/12 | 09/12 | 16/12 | 20/12 | 06/01 | 13/01 | 20/01 | 27/01 | 03/02 | 10/02 | 17/02 | 24/02
Delivery team milestone
Advanced Analytics
I
Governance
C
Completed activity
Issue analysis and tracking
Develop Findings template and Recommendation Packs
Investigation Analysis
Develop Xoserve owned Recommendation options – update and publish recommendation tracker in line with UIG working group meetings
Support Mod development
I
11/09 DSC ChMC
I
18/09 CoMC
I
23/09 UIG WG
w/c 09/09 Exec Summary
Review/draft updates to UIG user guide ongoing
BAU Publish UIG Investigation guide V.2
w/c 01/07 create close out activity plan
I
09/10 DSC ChMC
I
16/10 CoMC
w/c 11/11 Exec Summary
I
22/10 UIG WG
I
20/11 CoMC
I
26/11 UIG WG
I
13/11 DSC ChMC
Rescheduled
w/c 16/12 Exec Summary
I
11/12 DSC ChMC
I
18/12 CoMC
I
12/12 UIG WG
I
15/01 CoMC
I
21/01 UIG WG
w/c 27/01 Exec Summary
I
12/02 DSC ChMC
I
19/02 CoMC
I
18/021UIG WG
Final phase of Machine Learning complete
C
C
C
I
08/01 DSC ChMC

## Slide 5: Recommendations - where we are
4 lines MOD – (3.2.1) = 3 MODS – 1 sponsored Total 0692*), 2 sponsored British Gas 0690 & 0691
5 Future review
4 lines MOD 0681 – EON
70 CLOSED
As at 18/12/19
9 lines MOD – Scottish Power (12.2) = 1 MOD – sponsored 0693R
11 do nothing
3 BAU
19 completed
37 - other options progressed
1 review February
1 review March
14 finding & recommendations = 95 recommendation lines
2 lines Xoserve drafted MODs 3.2.5
1 line MOD 0699 Scottish Power
3 review January
* UNC Mod 0692 now approved, awaiting UKLink Release

## Slide 6: Overview Of Task Force Funding
Note that compared with last month, spend is reprofiled in line with actual invoice dates. Total value is unchanged.

## Slide 7: Reminder – UIG Task Force Activities migration post October 19
Pre November Task Force | Post October Customer Support Services Team | Post Oct Customer Change Team
Existing activities which will migrate Daily UIG Box account management Monthly UIG Executive Summary Creation of UIG monthly dashboard stats Web page ownership updates & maintenance UIG Work Group attendance UIG Work Group Task Force recommendation tracking UIG data sources creation UIG modification alignment creation & publication Machine Learning new analysis Budget mapping and forecast . Support development of new online UIG interactive reporting Activities which will cease Representation at ChMC & CoMC | Existing activities which will be migrated Daily UIG Box account management Monthly UIG Executive Summary Creation of UIG monthly dashboard stats Web page ownership updates & maintenance UIG Work Group attendance UIG Work Group Task Force recommendation tracking UIG data sources maintenance UIG modification alignment pack maintenance Machine Learning outstanding analysis Budget monitoring for UIG activities Outstanding CP 4853 Interim process to monitor and manually load rejected reads into UK Link where the read was rejected for reason MRE00458 only. Manual work around to be closed out end of October 19. UIG brochure version 2 creation & publication Re-purpose the existing "Lines of investigation tracker" Work with Customer Change team to develop formal project close down New activities which will commence Support maintenance of new online UIG interactive reporting Adhoc new UIG related requests One off activities e.g. simulations/adhoc UIG reporting requests – considered by Customer Support Services and/or directed to raise CP | Live CP4866 Removal of validation on uncorrected read due November release Work with Customer Team complete outstanding UIG related CR's. Newly identified Modifications & CRs