## Slide 1: Xoserve IX Refresh
Customer Update
15/04/2020

## Slide 2: IX Refresh Customer Update
There has been a significate impact on the project regarding COVID-19. This is due to customer site access restrictions as part of government recommendations
  85% of all remaining customers have requested a hold on their migration due to business continuity arrangements or restrictions in place with BT Openreach
  Project continuing where possible with remaining customers
Overall project RAG status has moved to Red
  Network Lines, Server and Router installations all require site access which has been limited
  Customer migrations dependent on all physical infrastructure being in place
Project team have engaged with legacy service provider to ensure all customers remain on a fully supported solution
  Agreement in place to extend support past August 2020, if needed
  Minimum 3 month extension
  Extension can be triggered at the end of June 2020
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com